## chihaan
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- ef]tfª\u] lrxfgkfl6 | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for foundation | 4 | 1.5 | 1.5 | 1.5 | 13.5
| -for toe wall | 4 | 1.7781 | 0.23 | 0.5 | 0.81793
| Sub-total |  |  |  |  | 14.3179 | cum | 674.12 | 9652.0054
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for foundation | 4 | 1.5 | 1.5 |  | 9
| -for toe wall | 4 | 1.7781 | 0.23 |  | 1.6359
| -for flooring | 1 | 2.9574 | 2.9574 |  | 8.7463
| -deduction for placement of God | -1 | 2.9574 | 1.8287 |  | -5.4083
| Sub-total |  |  |  |  | 13.9739 | sqm | 1017.47 | 14218.0653
| -13% VAT for brick | [7 empty] | 1155.5289
| -13% VAT for sand | [7 empty] | 409.8822
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd-lk=;L=;L= +!M#M^_
| -for foundation | 4 | 1.5 | 1.5 | 0.075 | 0.675
| -for toe wall | 4 | 1.7781 | 0.23 | 0.075 | 0.12269
| Sub-total |  |  |  |  | 0.79769 | cum | 11620.77 | 9269.7724
| -13% VAT for cement | [7 empty] | 297.2884
| -13% VAT for aggregate | [7 empty] | 297.6897
| -13% VAT for sand | [7 empty] | 140.0568
| -13% VAT for water | [7 empty] | 2.9036
| -13% VAT for diesel | [7 empty] | 40.7457
| -13% VAT for petrol | [7 empty] | 1.4674
4 | d]lzgsf] k¦of]u u/L hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -!M@M$_
| -for flooring | 1 | 2.9574 | 2.9574 | 0.075 | 0.65598
| -deduction for placement of God | -1 | 2.9574 | 1.8287 | 0.075 | -0.40562
| Sub-total |  |  |  |  | 0.25036 | cum | 12884.61 | 3225.7331
| -13% VAT for cement | [7 empty] | 135.7151
| -13% VAT for aggregate | [7 empty] | 89.81
| -13% VAT for sand | [7 empty] | 46.0256
| -13% VAT for water | [7 empty] | 1.1847
| -13% VAT for water | [7 empty] | 12.7881
| -13% VAT for water | [7 empty] | 0.46053
5 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for foundation | 4 | 1.5 | 1.5 | 0.35 | 3.15
| -for neck column | 4 | 0.35 | 0.35 | 1.37 | 0.6713
| -for tie beam | 4 | 2.9574 | 0.23 | 0.23 | 0.62579
| -GF column | 4 | 0.35 | 0.35 | 2.7156 | 1.3307
| -for beam | 4 | 4.1574 | 0.23 | 0.23 | 0.87971
| -for slab | 1 | 3.6574 | 3.6574 | 0.125 | 1.6721
| -for cantilever | 2 | 3.6574 | 0.6 | 0.125 | 0.54861
|  | 2 | 4.8574 | 0.6 | 0.125 | 0.72861
| -for inclined slab | 4 | 2.3621 | 2.235 | 0.075 | 1.5838
| Sub-total |  |  |  |  | 11.1906 | cum | 13957.29 | 156189.7572
| -13% VAT for cement | [7 empty] | 7582.8512
| -13% VAT for aggregate | [7 empty] | 4122.2698
| -13% VAT for sand | [7 empty] | 1964.8145
| -13% VAT for water | [7 empty] | 81.4672
| -13% VAT for diesel | [7 empty] | 571.6088
| -13% VAT for petrol | [7 empty] | 20.585
6 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for neck column | 4 | 0.35 |  | 1.37 | 1.918
| -for tie beam | 4 | 2.9574 |  | 0.46 | 5.4417
| -GF column | 4 | 1.4 |  | 2.7156 | 15.2076
| -for beam | 4 | 4.1574 |  | 0.46 | 7.6497
| -for slab | 1 | 3.6574 | 3.6574 |  | 13.3767
| -for inclined slab | 4 | 2.3621 | 2.235 |  | 21.1169
| -for cantilever | 2 | 3.6574 | 0.6 |  | 4.3889
|  | 2 | 4.8574 | 0.6 |  | 5.8289
| Sub-total |  |  |  |  | 74.9284 | sqm | 922.71 | 69137.1382
| -13% VAT for plyboard | [7 empty] | 1954.1783
| -13% VAT for wood | [7 empty] | 1298.2629
| -13% VAT for iron props | [7 empty] | 987.4717
| -13% VAT for nails | [7 empty] | 321.4426
7 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit Weight (Kg/m) | Total Weight (Kg)
| -for foundation | 10 | 1.5 | 0.88889 | 13.3333 | 0.013333
|  | 10 | 1.5 | 0.88889 | 13.3333 | 0.013333
| -for neck column to 1st floor | 16 | 5.4711 | 0.88889 | 77.8115 | 0.077812
|  | 16 | 5.472 | 1.5802 | 138.3547 | 0.13835
| -for binding stirrups | 108 | 1.118 | 0.39506 | 47.6993 | 0.047699
|  | 108 | 0.952 | 0.39506 | 40.6187 | 0.040619
| -for tie beam | 24 | 4.011 | 0.88889 | 85.5674 | 0.085567
| .-for stirrups | 80 | 0.81439 | 0.39506 | 25.7386 | 0.025739
| -for beam | 24 | 4.011 | 0.88889 | 85.5674 | 0.085567
| .-for stirrups | 112 | 0.81439 | 0.39506 | 36.0341 | 0.036034
| -for slab | 116 | 4.8574 | 0.39506 | 222.6018 | 0.2226
| -for inclined slab | 60 | 2.3621 | 0.61728 | 87.4846 | 0.087485
|  | 64 | 2.235 | 0.61728 | 88.2959 | 0.088296
| Sub-total |  |  |  |  | 0.96244 | MT | 132360 | 127388.6416
| -13% VAT for TMT rod | [7 empty] | 13137.3146
| -13% VAT for binding wire | [7 empty] | 150.1407
8 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -at wall | 4 | 3.4274 |  | 2.3656 | 32.4321
| -roof | 4 | 2.3621 | 2.3621 |  | 22.3178
| Sub-total |  |  |  |  | 54.7499 | sqm | 415.5 | 22748.5821
| -13% VAT for cement | [7 empty] | 498.9835
| -13% VAT for sand | [7 empty] | 330.2322
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for tie beam | 4 | 1.1661 | 0.23 | 1.2 | 1.2874
|  | 4 | 2.3874 | 0.23 | 0.47 | 1.0323
| Sub-total |  |  |  |  | 2.3197 | cum | 14491.84 | 33616.5335
| -13% VAT for brick | [7 empty] | 2557.5849
| -13% VAT for cement | [7 empty] | 275.0734
| -13% VAT for sanda | [7 empty] | 287.4976
| -13% VAT for water | [7 empty] | 8.4437
10 | e'O{+tNnfdf d]l;g d]8 O{+6fsf] uf/f] nufpg] sfd l;d]G6 d;nf -!M^_ df
| -outer wall | 2 | 2.9574 | 0.1 | 2.3656 | 1.3992
|  | 2 | 2.9574 | 0.1 | 2.3656 | 1.3992
| -deduction for door | -1 | 1.2 | 0.1 | 2.4383 | -0.29259
| -deduction for window | -1 | 1.2 | 0.1 | 1.2 | -0.144
| Sub-total |  |  |  |  | 2.3619 | cum | 14759.89 | 34861.071
| -13% VAT for brick | [7 empty] | 2686.4038
| -13% VAT for cement | [7 empty] | 280.0765
| -13% VAT for sand | [7 empty] | 292.7268
| -13% VAT for water | [7 empty] | 8.5972
11 | Knfi6/ dfly @) dL=dL= afSnf] emNn/ jf kfgL k§L agfpg] sfd
| -for cantilever | 2 | 4.8574 |  |  | 9.7148
|  | 2 | 4.8574 |  |  | 9.7148
| Sub-total |  |  |  |  | 19.4297 | rm | 144.41 | 2805.841
| -13% VAT for cement | [7 empty] | 230.3836
| -13% VAT for sand | [7 empty] | 32.1037
| -13% VAT for water-proofing | [7 empty] | 0.050517
12 | #* dL=dL= afSnf] lr/fg cu¦fv sf7sf] k¦m]d xfnL l8nfvfkf agfO{ h8fg ug]{ .
| -door | 1 | 1.2 |  | 2.4383 | 2.9259
| -windows | 1 | 1.2 |  | 1.2 | 1.44
| Sub-total |  |  |  |  | 4.3659 | sqm | 15960.82 | 69683.938
| -13% VAT for cu¦fv sf7 | [7 empty] | 4849.6463
| -13% VAT for !)) dL=dL= sAhf | [7 empty] | 46.7159
| -13% VAT for!%) dL=dL=5]:sLgL | [7 empty] | 19.0623
| -13% VAT for #))dL=dL= 5]:sLgL | [7 empty] | 30.607
| -13% VAT for #)) dL=dL=nlsË ;]6 | [7 empty] | 488.9065
| -13% VAT for XoflG8n | [7 empty] | 18.2568
| -13% VAT for k]r lsnf | [7 empty] | 12.0817
13 | Provisional sum for lab tests and gajur | 1 |  |  |  | 1 | PS | 5000 | 5000
14 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 606074.4666
| Total Estimated | 606074.4666 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 78.3732
| User contribution | 131074.4666 |  | 21.6268
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on D11: Author: between footing size only

## Sheet1
Foundation size |  |  | Footing size |  |  | Plinth size |  |  | Toe wall |  |  |  | Column size |  |  | Tie beam size |  |  | Main beam size
Length | Breadth | Depth from GL | Length in PL area | Breadth in PL area | Depth | Length | Breadth | Depth from GL | Length L1 | Ht. H1 | Length L2 | Ht. H2 | Length/B | Ht. upto plinth | Ht. above PL upto ceiling | Length | Width | Height | Length | Width | Height
1.5 | 1.5 | 1.5 | 0.93965 | 0.93965 | 0.35 | 3.6574 | 3.6574 | 0.45 | 1.7781 | 0.82 | 0.58305 | 1.6 | 0.35 | 1.37 | 2.7156 | 2.9574 | 0.23 | 0.23 | 4.1574 | 0.23 | 0.35
0.58427