## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- dnl;d vfg]kfgL | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/09/07
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork in Excavation in ordinary soil (vGg] k'g{] sfo{)
| -for pipe laying | 1 | 175 | 0.3 | 0.45 | 23.625
|  | 1 | 150 | 0.3 | 0.45 | 20.25 | [5 empty] | 146.2969
|  | 1 | 415 | 0.3 | 0.45 | 56.025 | [5 empty] | 596 | 181.6519
| sub-total |  |  |  |  | 99.9 | cum | 963.05 | 96208.695 |  |  | 1269 | 386.7723
2 | Laying and joining of 32 mmØ HDPE pipe with butt-weld joints
| -for pipe laying | 1 | 1900 |  |  | 1900
| sub-total |  |  |  |  | 1900 | rm | 5.3195 | 10107.05
3 | -High Density Polythene Pipe NS 40 pipe material PE 100, PN 16 |  | Length (m) | Weight (Kg/m) | Total weight (Kg)
| -from source1 to tank 3, 32mm dia pipe | 1 | 400 | 0.338 | 135.2 | 135.2 |  |  |  |  | 97.006
| -from tank 2 to 2 houses, 32mm dia pipe | 1 | 300 | 0.338 | 101.4 | 101.4
| -from tank 3 to daando house, 32mm dia pipe | 1 | 1300 | 0.338 | 439.4 | 439.4
| Sub-total |  |  |  |  | 676 | kg | 287 | 194012 |  | 324.31
| -13% VAT for material | [7 empty] | 25221.56
4 | 32mm GI pipe threaded
| -for pipe laying | 1 | 6 |  |  | 6
| sub-total |  |  |  |  | 6 | rm | 452 | 2712
| -13% VAT for material | [7 empty] | 352.56
5 | Provisional sum for other unforseen works | 1 |  |  |  | 1 | PS | 7000 | 7000
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 336113.865
| Total Estimated | 336113.865 |  | 100
| Budget allocated | 300000
| Municipal payment | 285000 |  | 84.7927
| User contribution | 51113.865 |  | 15.2073
| Contingencies | 9000 |  | 3
| Maintanince | 6000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 336113.865 |  |  |  |  | Total Valuated Amount : |  | 208459.4124
Work Started : | [7 empty] | Work Finished:
Project:- dnl;d vfg]kfgL | [7 empty] | F.Y:2082/2083
Location:- Shankharapur Municipality 1 | [7 empty] | Date:2082/12/09
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork in Excavation in ordinary soil (vGg] k'g{] sfo{) | cum | 99.9 | 963.05 | 96208.695 | 88.2 | 963.05 | 84941.01 | -11267.685 |  | 120260.8688
2 | Laying and joining of 32 mmØ HDPE pipe with butt-weld joints | rm | 1900 | 5.3195 | 10107.05 | 0 | 5.3195 | 0 | -10107.05 |  | 12633.8125
3 | -High Density Polythene Pipe NS 40 pipe material PE 100, PN 16 | kg | 676 | 287 | 194012 | 365.04 | 287 | 104766.48 | -89245.52 |  | 242515
| -13% VAT for material |  |  |  | 25221.56 |  |  | 13619.6424 | -11601.9176 |  | 31526.95
4 | 32mm GI pipe threaded | rm | 6 | 452 | 2712 | 3 | 452 | 1356 | -1356 |  | 3390
| -13% VAT for material |  |  |  | 352.56 |  |  | 176.28 | -176.28 |  | 440.7
5 | Provisional sum for other unforseen works | PS | 1 | 7000 | 7000 | 1 | 3100 | 3100 | -3900 |  | 8750
6 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 336113.865 |  |  | 208459.4124 | -127654.4526

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- dnl;d vfg]kfgL | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/12/09
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork in Excavation in ordinary soil (vGg] k'g{] sfo{)
| -for pipe laying source 1 to tank 2 | 1 | 167 | 0.3 | 0.3 | 15.03
| -for pipe laying water tank 1 to tank 2 | 1 | 81 | 0.3 | 0.3 | 7.29
| -for pipe laying tank 2 to destination 1 | 1 | 150 | 0.3 | 0.3 | 13.5
| -for pipe laying tank 2 to destination 2 | 1 | 56 | 0.3 | 0.3 | 5.04
| -for pipe laying tank 2 to destination 3 | 1 | 8 | 0.3 | 0.3 | 0.72
| -for pipe laying tank 2 to destination 4 | 1 | 518 | 0.3 | 0.3 | 46.62
| sub-total |  |  |  |  | 88.2 | cum | 963.05 | 84941.01
2 | Laying and joining of 32 mmØ HDPE pipe with butt-weld joints
| -for pipe laying | 0 | 977 |  |  | 0
| sub-total |  |  |  |  | 0 | rm | 5.3195 | 0
3 | -High Density Polythene Pipe NS 40 pipe material PE 100, PN 16 |  | Length (m) | Weight (Kg/m) | Total weight (Kg)
| -for pipe laying source 1 to tank 2 | 1 | 168 | 0.338 | 56.784 | 56.784
| -for pipe laying water tank 1 to tank 2 | 1 | 83 | 0.338 | 28.054 | 28.054
| -for pipe laying tank 2 to destination 1 | 1 | 170 | 0.338 | 57.46 | 57.46
| -for pipe laying tank 2 to destination 2 | 1 | 71 | 0.338 | 23.998 | 23.998
| -for pipe laying tank 2 to destination 3 | 1 | 23 | 0.338 | 7.774 | 7.774
| -for pipe laying tank 2 to destination 4 | 1 | 565 | 0.338 | 190.97 | 190.97
| Sub-total |  |  |  |  | 365.04 | kg | 287 | 104766.48
| -13% VAT for material | [7 empty] | 13619.6424
4 | 32mm GI pipe threaded
| -for pipe laying | 1 | 3 |  |  | 3
| sub-total |  |  |  |  | 3 | rm | 452 | 1356
| -13% VAT for material | [7 empty] | 176.28
5 | Provisional sum for other unforseen works | 1 |  |  |  | 1 | PS | 3100 | 3100
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 208459.4124
| Total Valuated | 208459.4124 |  | 100
| Budget allocated | 300000
| Municipal payment | 176752.7358 |  | 84.79
| User contribution | 31706.6766 |  | 15.21
| Contingencies | 9000 |  | 3
| Maintanince | 6000 |  | 2

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- dnl;d vfg]kfgL | [9 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [9 empty] | Date:2082/12/09
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork in Excavation in ordinary soil (vGg] k'g{] sfo{)
| -for pipe laying source 1 to tank 2 | 1 | 167 | 0.3 | 0.3 | 15.03
| -for pipe laying water tank 1 to tank 2 | 1 | 81 | 0.3 | 0.3 | 7.29
| -for pipe laying tank 2 to destination 1 | 1 | 150 | 0.3 | 0.3 | 13.5
| -for pipe laying tank 2 to destination 2 | 1 | 56 | 0.3 | 0.3 | 5.04
| -for pipe laying tank 2 to destination 3 | 1 | 8 | 0.3 | 0.3 | 0.72
| -for pipe laying tank 2 to destination 4 | 1 | 518 | 0.3 | 0.3 | 46.62
| sub-total |  |  |  |  | 88.2 | cum | 963.05 | 84941.01
2 | Laying and joining of 32 mmØ HDPE pipe with butt-weld joints
| -for pipe laying | 0 | 977 |  |  | 0
| sub-total |  |  |  |  | 0 | rm | 5.3195 | 0
3 | -High Density Polythene Pipe NS 40 pipe material PE 100, PN 16 |  | Length (m) | Weight (Kg/m) | Total weight (Kg)
| -for pipe laying source 1 to tank 2 | 1 | 168 | 0.338 | 56.784 | 56.784
| -for pipe laying water tank 1 to tank 2 | 1 | 83 | 0.338 | 28.054 | 28.054
| -for pipe laying tank 2 to destination 1 | 1 | 170 | 0.338 | 57.46 | 57.46
| -for pipe laying tank 2 to destination 2 | 1 | 71 | 0.338 | 23.998 | 23.998
| -for pipe laying tank 2 to destination 3 | 1 | 23 | 0.338 | 7.774 | 7.774
| -for pipe laying tank 2 to destination 4 | 1 | 565 | 0.338 | 190.97 | 190.97
| Sub-total |  |  |  |  | 365.04 | kg | 287 | 104766.48
| -13% VAT for material | [7 empty] | 13619.6424
4 | 32mm GI pipe threaded
| -for pipe laying | 1 | 3 |  |  | 3
| sub-total |  |  |  |  | 3 | rm | 452 | 1356
| -13% VAT for material | [7 empty] | 176.28
5 | Provisional sum for other unforseen works | 1 |  |  |  | 1 | PS | 3100 | 3100
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 208459.4124
| Total Valuated | 208459.4124 |  | 100
| Budget allocated | 300000
| Municipal payment | 176752.7358 |  | 84.79
| User contribution | 31706.6766 |  | 15.21
| Contingencies | 9000 |  | 3
| Maintanince | 6000 |  | 2

## original estimate (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- dnl;d vfg]kfgL | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/09/07
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork in Excavation in ordinary soil (vGg] k'g{] sfo{)
| -for pipe laying | 1 | 175 | 0.3 | 0.45 | 23.625
|  | 1 | 150 | 0.3 | 0.45 | 20.25 | [5 empty] | 146.2969
|  | 1 | 415 | 0.3 | 0.45 | 56.025 | [5 empty] | 596 | 181.6519
| sub-total |  |  |  |  | 99.9 | cum | 963.05 | 96208.695 |  |  | 1269 | 386.7723
2 | Laying and joining of 32 mmØ HDPE pipe with butt-weld joints
| -for pipe laying | 1 | 1900 |  |  | 1900
| sub-total |  |  |  |  | 1900 | rm | 5.3195 | 10107.05
3 | -High Density Polythene Pipe NS 40 pipe material PE 100, PN 16 |  | Length (m) | Weight (Kg/m) | Total weight (Kg)
| -from source1 to tank 3, 32mm dia pipe | 1 | 400 | 0.338 | 135.2 | 135.2 |  |  |  |  | 97.006
| -from tank 2 to 2 houses, 32mm dia pipe | 1 | 300 | 0.338 | 101.4 | 101.4
| -from tank 3 to daando house, 32mm dia pipe | 1 | 1300 | 0.338 | 439.4 | 439.4
| Sub-total |  |  |  |  | 676 | kg | 287 | 194012 |  | 324.31
| -13% VAT for material | [7 empty] | 25221.56
4 | 32mm GI pipe threaded
| -for pipe laying | 1 | 6 |  |  | 6
| sub-total |  |  |  |  | 6 | rm | 452 | 2712
5 | Provisional sum for other unforseen works | 1 |  |  |  | 1 | PS | 7000 | 7000
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 335761.305
| Total Estimated | 335761.305 |  | 100
| Budget allocated | 300000
| Municipal payment | 285000 |  | 84.8817
| User contribution | 50761.305 |  | 15.1183
| Contingencies | 9000 |  | 3
| Maintanince | 6000 |  | 2