## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- v'bf] ksfpg] el6 r'nf] | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/09/13
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 2mm thickness for vertical post | 6 | 4.267 | 4.4 | 112.6486 | 112.6486
|  | 6 | 4.5718 | 4.4 | 120.6949 | 120.6949
|  | 2 | 4.267 | 4.4 | 37.5495 | 37.5495
|  | 2 | 4.5718 | 4.4 | 40.2316 | 40.2316
| -MS square pipe horizontal of 2" * 2" of 2mm thickness for binding post | 6 | 4.5718 | 3.01 | 82.5663 | 82.5663 | [7 empty] | 27.4307 | 89.9956
|  | 6 | 3.9622 | 3.01 | 71.5575 | 71.5575
| -MS square pipe horizontal of 1.5" * 1.5" of 2mm thickness as purlin at mid portion of upper part | 4 | 4.5718 | 2.26 | 41.3289 | 41.3289
| sub-total |  |  |  |  | 506.5773 | Kg | 182.51 | 92455.4163
| -VAT 13% for materials | [7 empty] | 6506.993
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -upper portion | 2 | 3.9622 | 4.5718 |  | 36.2286
|  | 1 | 3.9622 | 3.9622 |  | 15.6991
| sub-total |  |  |  |  | 51.9277 | sqm | 1074.98 | 55821.2724
| -13% VAT for sheet | [7 empty] | 4505.7993
| -13% VAT for nut bolt | [7 empty] | 691.0932
| -13% VAT for j-hook | [7 empty] | 235.0628
| -13% VAT for bitumen washer | [7 empty] | 111.385
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -Masonary wall | 4 | 2.4383 | 0.45 | 0.9 | 3.95
| -for footing of vertical post | 8 | 0.6 | 0.6 | 0.6 | 1.728
| sub-total |  |  |  |  | 5.678 | cum | 674.12 | 3827.6636
4 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| -for footing of vertical post | 8 | 0.6 | 0.6 | 0.15 | 0.432
| -for flooring | 2 | 3.0479 | 3.6574 | 0.15 | 3.3442
| -deduction for tunnel | -2 | 2.4383 | 1.5 | 0.15 | -1.0972
| sub-total |  |  |  |  | 2.679 | cum | 4495.64 | 12043.6244
| -13% VAT for block stone | [7 empty] | 897.6967
| -13% VAT for bond stone | [7 empty] | 179.5372
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing of vertical post | 8 | 0.6 | 0.6 | 0.075 | 0.216
|  | 8 | 0.45 | 0.45 | 0.45 | 0.729
| -for flooring | 2 | 3.0479 | 3.6574 | 0.1 | 2.2295
| -deduction for tunnel | -2 | 3.6574 | 1.5 | 0.1 | -1.0972
| sub-total |  |  |  |  | 2.0772 | cum | 13351.1 | 27733.2908
| -13% VAT for cement | [7 empty] | 1126.0442
| -13% VAT for sand | [7 empty] | 381.8794
| -13% VAT for aggregate | [7 empty] | 739.917
| -13% VAT for water | [7 empty] | 11.3417
6 | 9'Ëfsf] uf/f] df6f] nufpg] sfd
| -Masonary wall | 4 | 2.4383 | 0.45 | 0.9 | 3.95 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 3.95 | cum | 6337.3 | 25032.4316
| -13% VAT for block stone | [7 empty] | 1323.6181
| -13% VAT for bond stone | [7 empty] | 132.3603
| -13% VAT for stone | [7 empty] | 68.5833
| -13% VAT for water | [7 empty] | 10.0646
7 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Total | [7 empty] | 234835.0749
| Total Estimated | 234835.0749 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 80.9078
| User contribution | 44835.0749 |  | 19.0922
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- v'bf] ksfpg] el6 r'nf] | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/11/10
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.6mm thickness for vertical post | 2 | 5.029 | 3.54 | 35.605 | 35.605
|  | 2 | 4.8766 | 3.54 | 34.5261 | 34.5261
| -MS square pipe of 2" * 2" of 1.4mm thickness for vertical post | 2 | 3.9 | 2.14 | 16.692 | 16.692
| -MS square pipe of 2" * 2" of 1.4mm thickness for purlins | 9 | 3.09 | 2.14 | 59.5134 | 59.5134
| -MS square pipe of 66mm*33mm of 1.4mm thickness for vertical post | 1 | 3.9 | 2.35 | 9.165 | 9.165
| -MS square pipe of 3" * 3" of 1.6mm thickness for vertical post for cooking area | 3 | 2.4383 | 3.54 | 25.8945 | 25.8945
|  | 3 | 2.6 | 3.54 | 27.612 | 27.612
| -MS square pipe of 1.5" * 1.5" of 1.2mm thickness for purlins | 5 | 3.09 | 1.39 | 21.4755 | 21.4755
| -MS square pipe of 1.5" * 1.5" of 1.2mm thickness for horizontal support in mid-height section | 5 | 3.7 | 1.39 | 25.715 | 25.715
| -MS square pipe of 2" * 2" of 1.4mm thickness for horizontal support of roof | 3 | 3.9622 | 1.39 | 16.5224 | 16.5224
| -MS square pipe of 3" * 3" of 1.6mm thickness for vertical post | 3 | 3.9622 | 3.54 | 42.0786 | 42.0786
|  | 3 | 2.7431 | 3.54 | 29.1314 | 29.1314
| -MS square pipe of 1.5" * 1.5" of 1.2mm thickness for purlins | 5 | 7.9468 | 1.39 | 55.2302 | 55.2302
| -MS square pipe of 66mm*33mm of 1.4mm thickness for horizontal member | 3 | 3.4288 | 2.35 | 24.1733 | 24.1733
| -MS square pipe of 1.5" * 1.5" of 1.2mm thickness for horizontal support at walls | 3 | 7.1119 | 1.39 | 29.6564 | 29.6564
|  | 3 | 3.4288 | 1.39 | 14.2982 | 14.2982
|  | 6 | 3.4288 | 1.39 | 28.5965 | 28.5965
| sub-total |  |  |  |  | 495.8855 | Kg | 182.51 | 90504.0553
| -VAT 13% for materials | [7 empty] | 6369.6566
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -upper portion | 1 | 3.9622 | 2.1335 |  | 8.4534
| -cooking area | 1 | 3.9622 | 3.5 |  | 13.8677
|  | 1 | 7.2968 | 4.267 |  | 31.1353
| sub-total |  |  |  |  | 53.4564 | sqm | 1074.98 | 57464.5548
| -13% VAT for sheet | [7 empty] | 4638.4423
| -13% VAT for nut bolt | [7 empty] | 711.4378
| -13% VAT for j-hook | [7 empty] | 241.9827
| -13% VAT for bitumen washer | [7 empty] | 114.664
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -Masonary wall | 2 | 2.4383 | 0.45 | 0.9 | 1.975
| -for footing of vertical post | 12 | 0.45 | 0.45 | 0.45 | 1.0935
| -for flooring | 1 | 3.9622 | 3.0479 | 0.1 | 1.2076
| -for footing of vertical post | 6 | 0.3 | 0.3 | 0.3 | 0.162
| for tunnel | 1 | 2.7431 | 0.6 | 0.9 | 1.4813
| sub-total |  |  |  |  | 5.9194 | cum | 674.12 | 3990.3758
4 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| -for footing of vertical post | 12 | 0.45 | 0.45 | 0.075 | 0.18225
| -for flooring | 1 | 3.5 | 3.5 | 0.075 | 0.91875
|  | 1 | 4.2 | 3.2 | 0.075 | 1.008
| -deduction for tunnel | -1 | 3 | 1.5 | 0.075 | -0.3375
| -for flooring | 1 | 3.5 | 3.65 | 0.075 | 0.95813
|  | 1 | 3.5 | 0.65 | 0.075 | 0.17062
| sub-total |  |  |  |  | 2.9002 | cum | 4495.64 | 13038.4799
| -13% VAT for block stone | [7 empty] | 971.8503
| -13% VAT for bond stone | [7 empty] | 194.3678
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing of vertical post | 12 | 0.45 | 0.45 | 0.05 | 0.1215
| -for flooring | 1 | 3.5 | 3.5 | 0.075 | 0.91875
|  | 1 | 4.2 | 3.2 | 0.075 | 1.008
| -deduction for tunnel | -1 | 3 | 1.5 | 0.075 | -0.3375
| -for flooring | 1 | 3.5 | 3.65 | 0.05 | 0.63875
| sub-total |  |  |  |  | 2.3495 | cum | 13351.1 | 31368.4094
| -13% VAT for cement | [7 empty] | 1273.6395
| -13% VAT for sand | [7 empty] | 431.934
| -13% VAT for aggregate | [7 empty] | 836.9011
| -13% VAT for water | [7 empty] | 12.8283
6 | 9'Ëfsf] uf/f] df6f] nufpg] sfd
| -Masonary wall | 2 | 3 | 0.45 | 0.8 | 2.16 |  |  |  |  | 7 | 2 | 160.098
|  | 2 | 2.7431 | 0.45 | 0.8 | 1.975
| Sub-total |  |  |  |  | 4.135 | cum | 6337.3 | 26204.7838
| -13% VAT for block stone | [7 empty] | 1385.6076
| -13% VAT for bond stone | [7 empty] | 138.5591
| -13% VAT for stone | [7 empty] | 71.7953
| -13% VAT for water | [7 empty] | 10.536
7 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Total | [7 empty] | 240974.8613
| Total Valuated | 240974.8613 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 78.8464
| User contribution | 50974.8613 |  | 21.1536
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 234835.0749 |  |  |  |  | Total Valuated Amount : |  | 240974.8613
Work Started : | [7 empty] | Work Finished:
Project:- v'bf] ksfpg] el6 r'nf] | [7 empty] | F.Y:2082/2083
Location:- Shankharapur Municipality 1 | [7 empty] | Date:2082/11/10
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | Kg | 506.5773 | 182.51 | 92455.4163 | 495.8855 | 182.51 | 90504.0553 | -1951.3609 |  | 115569.2703
| -VAT 13% for materials |  |  |  | 6506.993 |  |  | 6369.6566 | -137.3364 |  | 8133.7412
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd | sqm | 51.9277 | 1074.98 | 55821.2724 | 53.4564 | 1074.98 | 57464.5548 | 1643.2824 |  | 69776.5905
| -13% VAT for sheet |  |  |  | 4505.7993 |  |  | 4638.4423 | 132.643 |  | 5632.2492
| -13% VAT for nut bolt |  |  |  | 691.0932 |  |  | 711.4378 | 20.3446 |  | 863.8665
| -13% VAT for j-hook |  |  |  | 235.0628 |  |  | 241.9827 | 6.9198 |  | 293.8285
| -13% VAT for bitumen washer |  |  |  | 111.385 |  |  | 114.664 | 3.279 |  | 139.2312
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | cum | 5.678 | 674.12 | 3827.6636 | 5.9194 | 674.12 | 3990.3758 | 162.7122 |  | 4784.5795
4 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf | cum | 2.679 | 4495.64 | 12043.6244 | 2.9002 | 4495.64 | 13038.4799 | 994.8555 |  | 15054.5305
| -13% VAT for block stone |  |  |  | 897.6967 |  |  | 971.8503 | 74.1536 |  | 1122.1208
| -13% VAT for bond stone |  |  |  | 179.5372 |  |  | 194.3678 | 14.8306 |  | 224.4216
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_ | cum | 2.0772 | 13351.1 | 27733.2908 | 2.3495 | 13351.1 | 31368.4094 | 3635.1186 |  | 34666.6135
| -13% VAT for cement |  |  |  | 1126.0442 |  |  | 1273.6395 | 147.5953 |  | 1407.5552
| -13% VAT for sand |  |  |  | 381.8794 |  |  | 431.934 | 50.0545 |  | 477.3493
| -13% VAT for aggregate |  |  |  | 739.917 |  |  | 836.9011 | 96.984 |  | 924.8963
| -13% VAT for water |  |  |  | 11.3417 |  |  | 12.8283 | 1.4866 |  | 14.1771
6 | 9'Ëfsf] uf/f] df6f] nufpg] sfd | cum | 3.95 | 6337.3 | 25032.4316 | 4.135 | 6337.3 | 26204.7838 | 1172.3522 |  | 31290.5395
| -13% VAT for block stone |  |  |  | 1323.6181 |  |  | 1385.6076 | 61.9894 |  | 1654.5226
| -13% VAT for bond stone |  |  |  | 132.3603 |  |  | 138.5591 | 6.1989 |  | 165.4503
| -13% VAT for stone |  |  |  | 68.5833 |  |  | 71.7953 | 3.212 |  | 85.7292
| -13% VAT for water |  |  |  | 10.0646 |  |  | 10.536 | 0.47136 |  | 12.5808
7 | Information board (सुचना पाटि) | no. | 1 | 1000 | 1000 | 1 | 1000 | 1000 | 0
| Total |  |  |  | 234835.0749 |  |  | 240974.8613 | 6139.7864

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- v'bf] ksfpg] el6 r'nf] | [9 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [9 empty] | Date:2082/11/10
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.6mm thickness for vertical post | 2 | 5.029 | 3.54 | 35.605 | 35.605
|  | 2 | 4.8766 | 3.54 | 34.5261 | 34.5261
| -MS square pipe of 2" * 2" of 1.4mm thickness for vertical post | 2 | 3.9 | 2.14 | 16.692 | 16.692
| -MS square pipe of 2" * 2" of 1.4mm thickness for purlins | 9 | 3.09 | 2.14 | 59.5134 | 59.5134
| -MS square pipe of 66mm*33mm of 1.4mm thickness for vertical post | 1 | 3.9 | 2.35 | 9.165 | 9.165
| -MS square pipe of 3" * 3" of 1.6mm thickness for vertical post for cooking area | 3 | 2.4383 | 3.54 | 25.8945 | 25.8945
|  | 3 | 2.6 | 3.54 | 27.612 | 27.612
| -MS square pipe of 1.5" * 1.5" of 1.2mm thickness for purlins | 5 | 3.09 | 1.39 | 21.4755 | 21.4755
| -MS square pipe of 1.5" * 1.5" of 1.2mm thickness for horizontal support in mid-height section | 5 | 3.7 | 1.39 | 25.715 | 25.715
| -MS square pipe of 2" * 2" of 1.4mm thickness for horizontal support of roof | 3 | 3.9622 | 1.39 | 16.5224 | 16.5224
| -MS square pipe of 3" * 3" of 1.6mm thickness for vertical post | 3 | 3.9622 | 3.54 | 42.0786 | 42.0786
|  | 3 | 2.7431 | 3.54 | 29.1314 | 29.1314
| -MS square pipe of 1.5" * 1.5" of 1.2mm thickness for purlins | 5 | 7.9468 | 1.39 | 55.2302 | 55.2302
| -MS square pipe of 66mm*33mm of 1.4mm thickness for horizontal member | 3 | 3.4288 | 2.35 | 24.1733 | 24.1733
| -MS square pipe of 1.5" * 1.5" of 1.2mm thickness for horizontal support at walls | 3 | 7.1119 | 1.39 | 29.6564 | 29.6564
|  | 3 | 3.4288 | 1.39 | 14.2982 | 14.2982
|  | 6 | 3.4288 | 1.39 | 28.5965 | 28.5965
| sub-total |  |  |  |  | 495.8855 | Kg | 182.51 | 90504.0553
| -VAT 13% for materials | [7 empty] | 6369.6566
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -upper portion | 1 | 3.9622 | 2.1335 |  | 8.4534
| -cooking area | 1 | 3.9622 | 3.5 |  | 13.8677
|  | 1 | 7.2968 | 4.267 |  | 31.1353
| sub-total |  |  |  |  | 53.4564 | sqm | 1074.98 | 57464.5548
| -13% VAT for sheet | [7 empty] | 4638.4423
| -13% VAT for nut bolt | [7 empty] | 711.4378
| -13% VAT for j-hook | [7 empty] | 241.9827
| -13% VAT for bitumen washer | [7 empty] | 114.664
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -Masonary wall | 2 | 2.4383 | 0.45 | 0.9 | 1.975
| -for footing of vertical post | 12 | 0.45 | 0.45 | 0.45 | 1.0935
| -for flooring | 1 | 3.9622 | 3.0479 | 0.1 | 1.2076
| -for footing of vertical post | 6 | 0.3 | 0.3 | 0.3 | 0.162
| for tunnel | 1 | 2.7431 | 0.6 | 0.9 | 1.4813
| sub-total |  |  |  |  | 5.9194 | cum | 674.12 | 3990.3758
4 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| -for footing of vertical post | 12 | 0.45 | 0.45 | 0.075 | 0.18225
| -for flooring | 1 | 3.5 | 3.5 | 0.075 | 0.91875
|  | 1 | 4.2 | 3.2 | 0.075 | 1.008
| -deduction for tunnel | -1 | 3 | 1.5 | 0.075 | -0.3375
| -for flooring | 1 | 3.5 | 3.65 | 0.075 | 0.95813
|  | 1 | 3.5 | 0.65 | 0.075 | 0.17062
| sub-total |  |  |  |  | 2.9002 | cum | 4495.64 | 13038.4799
| -13% VAT for block stone | [7 empty] | 971.8503
| -13% VAT for bond stone | [7 empty] | 194.3678
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing of vertical post | 12 | 0.45 | 0.45 | 0.05 | 0.1215
| -for flooring | 1 | 3.5 | 3.5 | 0.075 | 0.91875
|  | 1 | 4.2 | 3.2 | 0.075 | 1.008
| -deduction for tunnel | -1 | 3 | 1.5 | 0.075 | -0.3375
| -for flooring | 1 | 3.5 | 3.65 | 0.05 | 0.63875
| sub-total |  |  |  |  | 2.3495 | cum | 13351.1 | 31368.4094
| -13% VAT for cement | [7 empty] | 1273.6395
| -13% VAT for sand | [7 empty] | 431.934
| -13% VAT for aggregate | [7 empty] | 836.9011
| -13% VAT for water | [7 empty] | 12.8283
6 | 9'Ëfsf] uf/f] df6f] nufpg] sfd
| -Masonary wall | 2 | 3 | 0.45 | 0.8 | 2.16 |  |  |  |  | 7 | 2 | 160.098
|  | 2 | 2.7431 | 0.45 | 0.8 | 1.975
| Sub-total |  |  |  |  | 4.135 | cum | 6337.3 | 26204.7838
| -13% VAT for block stone | [7 empty] | 1385.6076
| -13% VAT for bond stone | [7 empty] | 138.5591
| -13% VAT for stone | [7 empty] | 71.7953
| -13% VAT for water | [7 empty] | 10.536
7 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Total | [7 empty] | 240974.8613
| Total Valuated | 240974.8613 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 78.8464
| User contribution | 50974.8613 |  | 21.1536
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2