## ESTIMATE
Government of Nepal
Shankharapur Municipality
Shankhu, Kathmandu
Detail Estimate Sheet
| Project:- | gfªn]ef/] :jf:yo rf}sL 5fgf tyf kfgL 6\ofÍL dd{t | [7 empty] | F.Y.:-2080/081
| Location:- Shankharapur Municipality- 1 | [6 empty] | Date: 2081/02/21 |  |  |  |  | Date: 2080/05/21
| S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
| A. | kfgL 6\ofÍL dd{t
| 1 | cf/=l;=l;= jf cf/=lj=l;= sfd eTsfO{ !) dL= k/ x6fpg] sfd | 1 | 4.5 | 3 | 0.1 | 1.35 | cu.m. | 9900 | 13365
| 2 | l;d]G6 jf jh¦ Knfi6/ eTsfO{ !) dL= k/ x6fpg] sfd | 2 | 4.5 |  | 1.4 | 12.6
|  |  | 2 | 3 |  | 1.4 | 8.4
[7 empty] | 21 | sq.m. | 97.2 | 2041.2
| 3 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M$_ df | 2 | 4.5 | 0.1 | 0.9 | 0.81
|  |  | 2 | 3 | 0.1 | 0.9 | 0.54
|  |  | 1 | 5.4878 | 0.23 | 0.45 | 0.56799
[7 empty] | 1.918 | cu.m. | 14911.97 | 28600.9766
|  | vat on cement | [7 empty] | 359.8203
|  | vat on sand | [7 empty] | 175.0256
|  | vat on brick | [7 empty] | 2185.4811
| 4 | cf/=;L=;L= nflu !) ld=ld= kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | 20 | 4.5 |  | 0.61728 | 55.5556
|  |  | 30 | 3 |  | 0.61728 | 55.5556
|  | vat on material |  |  |  |  | 111.1111 | kg | 130.21 | 14467.7778
1880.8111
| 5 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_ | 1 | 4.5 | 3 | 0.075 | 1.0125
|  |  | 2 | 4.5 | 0.15 | 0.9 | 1.215
|  |  | 2 | 3 | 0.15 | 0.9 | 0.81
[7 empty] | 3.0375 | cum | 17107.9 | 51965.2463
|  | vat on cement | [7 empty] | 2279.3765
|  | vat on sand | [7 empty] | 420.7275
|  | vat on aggregate | [7 empty] | 1166.4726
| 6 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_ | 1 | 4.5 | 3 |  | 13.5 | sqm | 692.38 | 9347.13
|  | vat on cement | [7 empty] | 329.2433
|  | vat on sand | [7 empty] | 79.1961
|  | vat on aggregate | [7 empty] | 227.5498
| 7 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | 2 | 4.5 |  | 1.5 | 13.5
|  |  | 2 | 3 |  | 1.5 | 9
[7 empty] | 22.5 | sq.m. | 402.23 | 9050.175
|  | vat on cement | [7 empty] | 227.0932
|  | vat on sand | [7 empty] | 107.0617
| 8 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd | 1 | 4.5 |  | 3 | 13.5
|  |  | 2 | 4.5 |  | 1.5 | 13.5
|  |  | 2 | 3 |  | 1.5 | 9
[7 empty] | 36 | sq.m. | 286.77 | 10323.72
|  | vat on cement | [7 empty] | 359.293
| 9 | square frame medium duty 24"X24 | 1 |  |  |  | 1 | no. | 4659 | 4659 |  | page 196
|  | vat for material | [7 empty] | 605.67
| 10 | 1 HP water pump (mono block |  |  |  |  | 1 | no. | 9938 | 9938 |  | page 175
|  | vat on machine | [7 empty] | 1291.94
| B. | 5fgf dd{t
| 11 | h:tfkftfsf] 5fgf eTsfO{ ;fdfg ;'/lIft /fVg] sfd | 2 | 7.622 | 5.1829 |  | 79.008 | sq.m | 68.4 | 5404.1493
| 12 | dfn;fdfg pknAw u/L k'/fgf] UPVC sheet 5fgf 5fpg] sfd . | 2 | 7.622 | 5.1829 |  | 79.008 | sq.m | 369.1 | 29161.8642
|  | vat on material | [7 empty] | 1279.7721
| 13 | 5fgfdf Ridge cover UPVC PMMA(3MMTHICK) Regular nufpg] sfd lSnk tyf k]r cflb ;d]t k'/f sfo{ ug]{ . | 1 | 7.622 |  |  | 7.622 | m | 2761 | 21044.2073
|  | vat on material | [7 empty] | 2468.2165 |  | 5.1829
#REF!
| 14 | Information Board and photographs | 1 |  |  |  | 1 | no. | 1000 | 1000
225811.1967
[8 empty] | Description |  | Amount | Percent
[8 empty] | Total Estimated |  | 225811.1967
[8 empty] | Budget Allocated |  | 200000 | 100
[8 empty] | Municipal Payment |  | 190000 | 84.1411
[8 empty] | User Contribution |  | 35811.1967 | 17.9056
[8 empty] | Maintenance 2% |  | 4000 | 2
[8 empty] | Contingencies 3% |  | 6000 | 3

## mb
|  | Description | length | breadth | height | Quantity | capacity
|  | water tank | 2.25 | 2.25 | 1.5 | 6.075 | 6075litres
Government of Nepal
Shankharapur Municipality
Shankhu, Kathmandu
Measurement Sheet
| Project:- | hut] vfg]kfgL | [5 empty] | F.Y.:-2079/080
| Location:- Shankharapur Municipality- 1 | [6 empty] | Date: 2079/12/21
| S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Remarks
| 1 | Earthwork in excavaiton | 1 | 8.5 | 0.5 | 1 | 4.25 | cu.m.
| 2 | Dismantle the rcc work on the base of water tank | 1 | 2.7 | 2.7 | 0.1 | 0.729 | cu.m.
| 3 | stone soling | 2 | 8.5 | 0.6 | 0.15 | 1.53 | cu.m.
| 4 | Dry Stone Masonry work | 1 | 5 | 0.6 | 1.5 | 4.5
|  |  | 1 | 3.5 | 0.6 | 0.6 | 1.26
[7 empty] | 5.76 | cu.m.
| 5 | Brick Masonry work in 1:6 | 2 | 2.7 | 0.23 | 0.8 | 0.9936
[7 empty] | 0.9936 | cu.m.
| 6 | RCC works 1:1.5:3 ratio in water collection chamber with all work complete | 1 | 3.6 | 0.15 | 0.8 | 0.432
|  |  | 1 | 2.7 | 2.7 | 0.1 | 0.729
[7 empty] | 1.161 | cum
| 7 | 3mm punning all complete work | 1 | 2.7 | 2.7 |  | 7.29
|  |  | 2 | 3.6 |  | 0.8 | 5.76
[7 empty] | 13.05 | sqm
| 8 | plastering work
|  |  | 2 | 2.7 |  | 0.8 | 4.32
[7 empty] | 4.32 | sq.m.
| 9 | tap and fittings | 1 |  |  |  | 1 | job
| 10 | Iron frame for barbed wire | 7 | 1 |  | 1.5 | 10.5 | kg
| 11 | Barbed wire | 1 | 10 |  |  | 10 | r.m.
| 12 | Roof top PVC Water Tank | 1 |  |  |  | 10000 | ltr
| 13 | Information Board | 1 |  |  |  | 0 | no.

## valuation
|  | Description | length | breadth | height | Quantity | capacity
|  | water tank | 2.25 | 2.25 | 1.5 | 6.075 | 6075litres
Government of Nepal
Shankharapur Municipality
Shankhu, Kathmandu
Valuation Sheet
| Project:- | hut] vfg]kfgL | [7 empty] | F.Y.:-2079/080
| Location:- Shankharapur Municipality- 1 | [6 empty] | Date: 2079/12/21
| S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
| 1 | Earthwork in excavaiton | 1 | 8.5 | 0.5 | 1 | 4.25 | cu.m. | 627.27 | 2665.8975
| 2 | Dismantle the rcc work on the base of water tank | 1 | 2.7 | 2.7 | 0.1 | 0.729 | cu.m. | 9570 | 6976.53
| 3 | stone soling | 2 | 8.5 | 0.6 | 0.15 | 1.53 | cu.m. | 4567.63 | 6988.4739
|  | vat on stone | [7 empty] | 648.9391
| 4 | Dry Stone Masonry work | 1 | 5 | 0.6 | 1.5 | 4.5
|  |  | 1 | 3.5 | 0.6 | 0.6 | 1.26
[7 empty] | 5.76 | cu.m. | 5915.75 | 34074.72
|  | vat on stone | [7 empty] | 2239.4736
| 5 | Brick Masonry work in 1:6 | 2 | 2.7 | 0.23 | 0.8 | 0.9936
[7 empty] | 0.9936 | cu.m. | 14627.37 | 14533.7548
|  | vat on cement | [7 empty] | 1132.173
|  | vat on brick | [7 empty] | 130.4816
|  | vat on sand | [7 empty] | 123.1449
| 6 | RCC works 1:1.5:3 ratio in water collection chamber with all work complete | 1 | 3.6 | 0.15 | 0.8 | 0.432
|  |  | 1 | 2.7 | 2.7 | 0.1 | 0.729
[7 empty] | 1.161 | cum | 17171.03 | 19935.5658
|  | vat on cement | [7 empty] | 871.2283
|  | vat on aggregate | [7 empty] | 445.8517
|  | vat on sand | [7 empty] | 203.8461
| 7 | 3mm punning all complete work | 1 | 2.7 | 2.7 |  | 7.29
|  |  | 2 | 3.6 |  | 0.8 | 5.76
[7 empty] | 13.05 | sqm | 282.27 | 3683.6235
|  | vat on cement | [7 empty] | 126.3553
| 8 | plastering work
|  |  | 2 | 2.7 |  | 0.8 | 4.32
[7 empty] | 4.32 | sq.m. | 386.42 | 1669.3344
|  | vat on cement | [7 empty] | 30.959
|  | vat on sand | [7 empty] | 28.0199
| 9 | tap and fittings | 1 |  |  |  | 1 | job | 2000 | 2000
| 10 | Iron frame for barbed wire | 7 | 1 |  | 1.5 | 10.5 | kg | 177.66 | 1865.43
|  | Vat on iron frame | [7 empty] | 134.8727
| 11 | Barbed wire | 1 | 10 |  |  | 10 | r.m. | 79.47 | 794.7
|  | vat on barbed wire | [7 empty] | 25.8978
| 12 | Roof top PVC Water Tank | 1 |  |  |  | 10000 | ltr | 11 | 110000
|  | vat on pvc water tank | [7 empty] | 14300
| 12 | Information Board | 1 |  |  |  | 1 | no. | 500 | 500
226129.2731
[8 empty] | Description |  | Amount (NRs.) | Percent (%)
[8 empty] | Total Estimated |  | 226129.2731
[8 empty] | Budget Allocated |  | 200000 | 100
[8 empty] | Municipal Payment |  | 190000 | 84.0227
[8 empty] | User Contribution |  | 36129.2731 | 15.9773
[8 empty] | Maintenance 2% |  | 4000 | 2
[8 empty] | Contingencies 3% |  | 6000 | 3

## WCR
Government of Nepal
Shankharapur Municipality Office
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  | Total Valuated Amount : |  | 226129.2731
Project: | hut] vfg]kfgL | [7 empty] | Fiscal Year:079/80
Location:Shankharapur-1 | [8 empty] | Date:2079/12/21
S.No. | Description | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  | Quantity | Rate | Amount (Rs) | Quantity | Rate | Amount(Rs)
1 | Earthwork in excavaiton | #REF! | #REF! | #REF! | 4.25 | 627.27 | 2665.8975 | #REF!
2 | Dismantle the rcc work on the base of water tank | 1.35 | 9900 | 13365 | 0.729 | 9570 | 6976.53 | -0.621
3 | stone soling | 21 | 97.2 | 2041.2 | 1.53 | 4567.63 | 6988.4739 | -19.47
| vat on stone |  |  | 0 |  |  | 648.9391
4 | Dry Stone Masonry work | #REF! | #REF! | #REF! | 5.76 | 5915.75 | 34074.72 | #REF!
| vat on stone |  |  | #REF! |  |  | 2239.4736
5 | Brick Masonry work in 1:6 | 1.918 | 14911.97 | 28600.9766 | 0.9936 | 14627.37 | 14533.7548 | -0.92439
| vat on cement |  |  | 359.8203 |  |  | 1132.173
| vat on brick |  |  | 175.0256 |  |  | 130.4816
| vat on sand |  |  | 2185.4811 |  |  | 123.1449
6 | RCC works 1:1.5:3 ratio in water collection chamber with all work complete | 3.0375 | 17107.9 | 51965.2463 | 1.161 | 17171.03 | 19935.5658 | -1.8765
| vat on cement |  |  | 2279.3765 |  |  | 871.2283
| vat on aggregate |  |  | 420.7275 |  |  | 445.8517
| vat on sand |  |  | 1166.4726 |  |  | 203.8461
7 | 3mm punning all complete work | #REF! | #REF! | #REF! | 13.05 | 282.27 | 3683.6235 | #REF!
| vat on cement |  |  | 329.2433 |  |  | 126.3553
8 | plastering work | 22.5 | 402.23 | 9050.175 | 4.32 | 386.42 | 1669.3344 | -18.18
| vat on cement |  |  | 227.0932 |  |  | 30.959
| vat on sand |  |  | 107.0617 |  |  | 28.0199
9 | tap and fittings | 1 | 4659 | 4659 | 1 | 2000 | 2000 | 0
10 | Iron frame for barbed wire | #REF! | #REF! | #REF! | 10.5 | 177.66 | 1865.43 | #REF!
| Vat on iron frame |  |  | #REF! |  |  | 134.8727
11 | Barbed wire | #REF! | #REF! | #REF! | 10 | 79.47 | 794.7 | #REF!
| vat on barbed wire |  |  | #REF! |  |  | 25.8978
12 | Roof top PVC Water Tank | #REF! | #REF! | #REF! | 10000 | 11 | 110000 | #REF!
| vat on pvc water tank |  |  | #REF! |  |  | 14300
12 | Information Board | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  | #REF! |  |  | 226129.2731