## Estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:-Nanglebhare Police Chauki Marmat | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | UPVC sliding window without net (frame 60 X 60mm sash 66 X 42mm white colour with 5mm Glass)
Ground Floor
| -Lobby | 1 | 1.81 | 1.33 |  | 2.4073
| -main door attached window | 2 | 0.67 | 2.04 |  | 2.7336
| -traffic room | 1 | 1.2 | 1.32 |  | 1.584
| -store room | 3 | 0.62 | 1.22 |  | 2.2692
| -Rooms | 1 | 0.62 | 1.22 |  | 0.7564
| -room near staircase | 1 | 1.81 | 1.32 |  | 2.3892
| -toilet | 2 | 0.9 | 0.55 |  | 0.99
First Floor
| -Civil barrack room | 1 | 0.62 | 1.2 |  | 0.744
| -balcony passage | 1 | 0.45 | 1.27 |  | 0.5715
| -Civil barrack 2nd room | 2 | 1.8 | 1.32 |  | 4.752
|  | 3 | 0.6 | 1.22 |  | 2.196
Second Floor
| -attched window to door at balcony | 1 | 0.715 | 1.38 |  | 0.9867
|  | 1 | 0.715 | 0.52 |  | 0.3718
|  | 1 | 0.79 | 2.03 |  | 1.6037
| -Head room | 1 | 1.8 | 1.32 |  | 2.376
|  | 1 | 1.8 | 1.32 |  | 2.376
| Sub-total |  |  |  |  | 29.1074 | m2 | 6889.4 | 200532.5216
| -13% VAT for materials | [7 empty] | 26069.2278
2 | UPVC Single Door with full pannel (frame 60*60mm sash 60X100mm White Colour With Panel)
Ground Floor
| -Jail toilet door | 2 | 0.74 | 1.89 |  | 2.7972
| -store room | 1 | 0.98 | 2.02 |  | 1.9796
| -Staircase area | 1 | 0.97 | 2.05 |  | 1.9885
| -Room near staircase | 1 | 0.98 | 2.05 |  | 2.009
| -at staircase landing | 1 | 0.91 | 1.96 |  | 1.7836
First Floor
| -Civil barrack room | 1 | 0.93 | 2 |  | 1.86
| -Civil barrack 2nd room | 1 | 0.95 | 2.06 |  | 1.957
| -Balcony on Passage | 1 | 0.94 | 1.98 |  | 1.8612
Second Floor
| -Balcony on Passage | 1 | 0.985 | 2.15 |  | 2.1178
| -Head room | 1 | 0.945 | 2.07 |  | 1.9561
| -door to kitchen room | 1 | 0.94 | 2.05 |  | 1.927
| Sub-total |  |  |  |  | 22.237 | m2 | 8744 | 194440.328
| -13% VAT for materials | [7 empty] | 25277.2426
3 | UPVC Door with half pannel half glass (frame 60*60mm sash 60X104mm White Colour With 5mm glass)
Ground Floor
| -Main door | 1 | 1.22 | 2.04 |  | 2.4888
| Sub-total |  |  |  |  | 2.4888 | m2 | 8516.4 | 21195.6163
| -13% VAT for materials | [7 empty] | 2755.4301
4 | 4mm glass for affected openings
Ground Floor
| -store room | 3 | 0.51 | 1.12 |  | 1.7136
First Floor
| -Civil barrack room | 3 | 0.5 | 1.1 |  | 1.65
|  | 3 | 0.5 | 1.1 |  | 1.65
|  | 3 | 0.5 | 1.1 |  | 1.65
|  | 1 | 0.5 | 1.1 |  | 0.55
Second Floor
| -room along kitchen | 2 | 0.47 | 1.11 |  | 1.0434
|  | 3 | 0.49 | 1.14 |  | 1.6758
| Sub-total |  |  |  |  | 9.9328 | m2 | 742.44 | 7374.508
| -13% VAT for materials | [7 empty] | 958.686
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 479103.5605
| Total Estimated | 479103.5605 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 39.6574
| Police sector contribution | 289103.5605 |  | 60.3426
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2
Note on B22: Author: sliding panel only ie; window without frame
Note on B38: Author: khapa only
Note on B50: Author: only 4mm thick glass used

## Valuation
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:-Nanglebhare Police Chauki Marmat | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | UPVC sliding window without net (frame 60 X 60mm sash 66 X 42mm white colour with 5mm Glass)
Ground Floor
| -Lobby | 1 | 1.81 | 1.33 |  | 2.4073
| -main door attached window | 2 | 0.67 | 2.04 |  | 2.7336
| -traffic room | 1 | 1.2 | 1.32 |  | 1.584
| -store room | 3 | 0.62 | 1.22 |  | 2.2692
| -Rooms | 1 | 0.62 | 1.22 |  | 0.7564
| -room near staircase | 1 | 1.81 | 1.32 |  | 2.3892
| -toilet | 2 | 0.9 | 0.55 |  | 0.99
First Floor
| -Civil barrack room | 1 | 0.62 | 1.2 |  | 0.744
| -balcony passage | 1 | 0.45 | 1.27 |  | 0.5715
| -Civil barrack 2nd room | 2 | 1.8 | 1.32 |  | 4.752
|  | 3 | 0.6 | 1.22 |  | 2.196
Second Floor
| -attched window to door at balcony | 1 | 0.715 | 1.38 |  | 0.9867
|  | 1 | 0.715 | 0.52 |  | 0.3718
|  | 1 | 0.79 | 2.03 |  | 1.6037
| -Head room | 1 | 1.8 | 1.32 |  | 2.376
|  | 1 | 1.8 | 1.32 |  | 2.376
| Sub-total |  |  |  |  | 29.1074 | m2 | 6889.4 | 200532.5216
| -13% VAT for materials | [7 empty] | 26069.2278
2 | UPVC Single Door with full pannel (frame 60*60mm sash 60X100mm White Colour With Panel)
Ground Floor
| -Jail toilet door | 2 | 0.74 | 1.89 |  | 2.7972
| -store room | 1 | 0.98 | 2.02 |  | 1.9796
| -Staircase area | 1 | 0.97 | 2.05 |  | 1.9885
| -Room near staircase | 1 | 0.98 | 2.05 |  | 2.009
| -at staircase landing | 1 | 0.91 | 1.96 |  | 1.7836
First Floor
| -Civil barrack room | 1 | 0.93 | 2 |  | 1.86
| -Civil barrack 2nd room | 1 | 0.95 | 2.06 |  | 1.957
| -Balcony on Passage | 1 | 0.94 | 1.98 |  | 1.8612
Second Floor
| -Balcony on Passage | 1 | 0.985 | 2.15 |  | 2.1178
| -Head room | 1 | 0.945 | 2.07 |  | 1.9561
| -door to kitchen room | 1 | 0.94 | 2.05 |  | 1.927
| Sub-total |  |  |  |  | 22.237 | m2 | 8744 | 194440.328
| -13% VAT for materials | [7 empty] | 25277.2426
3 | UPVC Door with half pannel half glass (frame 60*60mm sash 60X104mm White Colour With 5mm glass)
Ground Floor
| -Main door | 1 | 1.22 | 2.04 |  | 2.4888
| Sub-total |  |  |  |  | 2.4888 | m2 | 8516.4 | 21195.6163
| -13% VAT for materials | [7 empty] | 2755.4301
4 | 4mm glass for affected openings
Ground Floor
| -store room | 3 | 0.51 | 1.12 |  | 1.7136
First Floor
| -Civil barrack room | 3 | 0.5 | 1.1 |  | 1.65
|  | 3 | 0.5 | 1.1 |  | 1.65
|  | 3 | 0.5 | 1.1 |  | 1.65
|  | 1 | 0.5 | 1.1 |  | 0.55
Second Floor
| -room along kitchen | 2 | 0.47 | 1.11 |  | 1.0434
|  | 3 | 0.49 | 1.14 |  | 1.6758
| Sub-total |  |  |  |  | 9.9328 | m2 | 742.44 | 7374.508
| -13% VAT for materials | [7 empty] | 958.686
5 | Information board (सुचना पाटि) | 0 |  |  |  | 0 | no. | 500 | 0
| Total | [7 empty] | 478603.5605
| Total Valuated | 478603.5605 |  | 100
| Budget allocated | 200000
| Municipal payment | 189801.713 |  | 39.6574
| Police sector contribution | 288801.8475 |  | 60.3426
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2
Note on B22: Author: sliding panel only ie; window without frame
Note on B38: Author: khapa only
Note on B50: Author: only 4mm thick glass used

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 0 |  |  |  |  | Total Valuated Amount : |  | 0
Work Started : | [7 empty] | Work Finished:
Project:-Nanglebhare Police Chauki Marmat | [7 empty] | F.Y:2082/2083
Location:- Shankharapur Municipality 9 | [7 empty] | Date:
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | UPVC sliding window without net (frame 60 X 60mm sash 66 X 42mm white colour with 5mm Glass) | m2 | 29.1074 | 6889.4 | 200532.5216 | 29.1074 | 6889.4 | 200532.5216 | 0
| -13% VAT for materials |  |  |  | 26069.2278 |  |  | 26069.2278 | 0
2 | UPVC Single Door with full pannel (frame 60*60mm sash 60X100mm White Colour With Panel) | m2 | 22.237 | 8744 | 194440.328 | 22.237 | 8744 | 194440.328 | 0
| -13% VAT for materials |  |  |  | 25277.2426 |  |  | 25277.2426 | 0
3 | UPVC Door with half pannel half glass (frame 60*60mm sash 60X104mm White Colour With 5mm glass) | m2 | 2.4888 | 8516.4 | 21195.6163 | 2.4888 | 8516.4 | 21195.6163 | 0
| -13% VAT for materials |  |  |  | 2755.4301 |  |  | 2755.4301 | 0
4 | 4mm glass for affected openings | m2 | 9.9328 | 742.44 | 7374.508 | 9.9328 | 742.44 | 7374.508 | 0
| -13% VAT for materials |  |  |  | 958.686 |  |  | 958.686 | 0
5 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 0 | 500 | 0 | -500
| Total |  |  |  | 479103.5605 |  |  | 478603.5605 | -500

## Measure
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:-Nanglebhare Police Chauki Marmat | [9 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 9 | [9 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | UPVC sliding window without net (frame 60 X 60mm sash 66 X 42mm white colour with 5mm Glass)
Ground Floor
| -Lobby | 1 | 1.81 | 1.33 |  | 2.4073
| -main door attached window | 2 | 0.67 | 2.04 |  | 2.7336
| -traffic room | 1 | 1.2 | 1.32 |  | 1.584
| -store room | 3 | 0.62 | 1.22 |  | 2.2692
| -Rooms | 1 | 0.62 | 1.22 |  | 0.7564
| -room near staircase | 1 | 1.81 | 1.32 |  | 2.3892
| -toilet | 2 | 0.9 | 0.55 |  | 0.99
First Floor
| -Civil barrack room | 1 | 0.62 | 1.2 |  | 0.744
| -balcony passage | 1 | 0.45 | 1.27 |  | 0.5715
| -Civil barrack 2nd room | 2 | 1.8 | 1.32 |  | 4.752
|  | 3 | 0.6 | 1.22 |  | 2.196
Second Floor
| -attched window to door at balcony | 1 | 0.715 | 1.38 |  | 0.9867
|  | 1 | 0.715 | 0.52 |  | 0.3718
|  | 1 | 0.79 | 2.03 |  | 1.6037
| -Head room | 1 | 1.8 | 1.32 |  | 2.376
|  | 1 | 1.8 | 1.32 |  | 2.376
| Sub-total |  |  |  |  | 29.1074 | m2 | 6889.4 | 200532.5216
| -13% VAT for materials | [7 empty] | 26069.2278
2 | UPVC Single Door with full pannel (frame 60*60mm sash 60X100mm White Colour With Panel)
Ground Floor
| -Jail toilet door | 2 | 0.74 | 1.89 |  | 2.7972
| -store room | 1 | 0.98 | 2.02 |  | 1.9796
| -Staircase area | 1 | 0.97 | 2.05 |  | 1.9885
| -Room near staircase | 1 | 0.98 | 2.05 |  | 2.009
| -at staircase landing | 1 | 0.91 | 1.96 |  | 1.7836
First Floor
| -Civil barrack room | 1 | 0.93 | 2 |  | 1.86
| -Civil barrack 2nd room | 1 | 0.95 | 2.06 |  | 1.957
| -Balcony on Passage | 1 | 0.94 | 1.98 |  | 1.8612
Second Floor
| -Balcony on Passage | 1 | 0.985 | 2.15 |  | 2.1178
| -Head room | 1 | 0.945 | 2.07 |  | 1.9561
| -door to kitchen room | 1 | 0.94 | 2.05 |  | 1.927
| Sub-total |  |  |  |  | 22.237 | m2 | 8744 | 194440.328
| -13% VAT for materials | [7 empty] | 25277.2426
3 | UPVC Door with half pannel half glass (frame 60*60mm sash 60X104mm White Colour With 5mm glass)
Ground Floor
| -Main door | 1 | 1.22 | 2.04 |  | 2.4888
| Sub-total |  |  |  |  | 2.4888 | m2 | 8516.4 | 21195.6163
| -13% VAT for materials | [7 empty] | 2755.4301
4 | 4mm glass for affected openings
Ground Floor
| -store room | 3 | 0.51 | 1.12 |  | 1.7136
First Floor
| -Civil barrack room | 3 | 0.5 | 1.1 |  | 1.65
|  | 3 | 0.5 | 1.1 |  | 1.65
|  | 3 | 0.5 | 1.1 |  | 1.65
|  | 1 | 0.5 | 1.1 |  | 0.55
Second Floor
| -room along kitchen | 2 | 0.47 | 1.11 |  | 1.0434
|  | 3 | 0.49 | 1.14 |  | 1.6758
| Sub-total |  |  |  |  | 9.9328 | m2 | 742.44 | 7374.508
| -13% VAT for materials | [7 empty] | 958.686
5 | Information board (सुचना पाटि) | 0 |  |  |  | 0 | no. | 500 | 0
| Total | [7 empty] | 478603.5605
| Total Valuated | 478603.5605 |  | 100
| Budget allocated | 200000
| Municipal payment | 189801.713 |  | 39.6574
| Police sector contribution | 288801.8475 |  | 60.3426
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2
Note on B22: Author: sliding panel only ie; window without frame
Note on B38: Author: khapa only
Note on B50: Author: only 4mm thick glass used