## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- तल्लो नाङ्गलेद्वारे चिहानपाटी | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/09/07
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 3mm thickness for vertical post | 4 | 4.5718 | 6.5 | 118.8662 | 118.8662
| -MS square pipe horizontal of 3" * 3" of 3mm thickness for binding post | 4 | 3.6574 | 6.5 | 95.093 | 95.093 | [7 empty] | 14.6297 | 47.9977
| -MS square pipe horizontal of 3" * 3" of 3mm thickness for base of upper portion | 2 | 3.6574 | 6.5 | 47.5465 | 47.5465
| -MS square pipe vertical section of 3" * 3" of 3mm thickness for upper portion | 4 | 1.6245 | 6.5 | 42.2371 | 42.2371
| -MS square pipe horizontal of 2" * 2" of 3mm thickness for diagnol of uppermost portion | 2 | 2.5145 | 4.43 | 22.2783 | 22.2783
| -MS square pipe horizontal of 2" * 2" of 3mm thickness for binding at mid portion of upper part | 8 | 1.8287 | 4.43 | 64.8095 | 64.8095
| -MS square pipe horizontal of 2" * 2" of 3mm thickness as purlin at mid portion of upper part | 4 | 2.8955 | 4.43 | 51.3075 | 51.3075
|  | 4 | 4.2923 | 4.43 | 76.0594 | 76.0594
| -MS square pipe horizontal of 2" * 2" of 3mm thickness at corner of upper part | 8 | 1.9567 | 4.43 | 69.3462 | 69.3462
| -MS square pipe horizontal of 2" * 2" of 3mm thickness as purlin at mid portion of uppermost part | 4 | 2.4383 | 4.43 | 43.2063 | 43.2063
|  | 4 | 0.76196 | 5.43 | 16.5498 | 16.5498
| -MS square pipe horizontal of 2" * 2" of 3mm thickness at corner of uppermost part | 8 | 1.271 | 4.43 | 45.0426 | 45.0426
| -MS square pipe horizontal of 2" * 2" of 2mm thickness for vertical post of railing | 6 | 1.5 | 3.01 | 27.09 | 27.09
| -MS square pipe horizontal of 2" * 2" of 2mm thickness for vertical post of railing | 1 | 10.9723 | 3.01 | 33.0265 | 33.0265
| -MS square pipe horizontal of 1.5" * 1.5" of 2mm thickness for vertical post of railing | 2 | 10.6096 | 2.26 | 47.9553 | 47.9553
| sub-total |  |  |  |  | 800.4142 | Kg | 182.51 | 146083.5878
| -VAT 13% for materials | [7 empty] | 10281.3325
2 | )=$! dL=dL=afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -upper portion | 4 | 3.4034 | 1.6245 |  | 22.1152
| -uppermost portion | 4 | 1.4604 | 1.6763 |  | 9.7922
| sub-total |  |  |  |  | 31.9075 | sqm | 1112.58 | 35499.6243
| -13% VAT for sheet | [7 empty] | 2924.5985
| -13% VAT for nut bolt | [7 empty] | 424.6487
| -13% VAT for j-hook | [7 empty] | 144.4365
| -13% VAT for bitumen washer | [7 empty] | 68.4415
3 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -Masonary wall | 1 | 8.5 | 2 | 0.9 | 15.3
|  | 1 | 5 | 1 | 0.75 | 3.75
| -for footing of vertical post | 4 | 0.6 | 0.6 | 0.6 | 0.864
| -for plinth level | 4 | 3.124 | 0.45 | 0.525 | 2.9522
| -for railing | 6 | 0.3 | 0.3 | 0.6 | 0.324
| sub-total |  |  |  |  | 23.1902 | cum | 62.95 | 1459.8247
| -13% VAT for excavator | [7 empty] | 155.8615
4 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Masonary wall | 1 | 8.5 | 2 | 0.15 | 2.55
|  | 1 | 5 | 1 | 0.15 | 0.75
| -for footing of vertical post | 4 | 0.6 | 0.6 | 0.15 | 0.216
| -for plinth level | 4 | 3.2764 | 0.45 | 0.15 | 0.88464
|  | 1 | 3.2764 | 3.2764 | 0.15 | 1.6103
| -deduction for chihaan | -1 | 1.5 | 1.8 | 0.15 | -0.405
| -for railing | 6 | 0.3 | 0.3 | 0.15 | 0.081
| sub-total |  |  |  |  | 5.6869 | cum | 4458.52 | 25355.1476
| -13% VAT for stone | [7 empty] | 2284.8172
5 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Masonary wall | 1 | 8.5 | 2 | 0.05 | 0.85
|  | 1 | 8.5 | 0.45 | 0.05 | 0.19125
|  | 1 | 5 | 1 | 0.05 | 0.25
|  | 1 | 5 | 0.45 | 0.05 | 0.1125
| -for footing of vertical post | 4 | 0.6 | 0.6 | 0.3 | 0.432
| -for plinth level | 4 | 3.2764 | 0.45 | 0.05 | 0.29488
|  | 1 | 4.1908 | 4.1908 | 0.075 | 1.3172
| -deduction for chihaan | -1 | 1.5 | 1.8 | 0.075 | -0.2025
| -for railing | 6 | 0.3 | 0.3 | 0.45 | 0.243
| sub-total |  |  |  |  | 3.4883 | cum | 10964.46 | 38247.7328
| -13% VAT for cement | [7 empty] | 1627.0404
| -13% VAT for sand | [7 empty] | 647.9558
| -13% VAT for aggregate | [7 empty] | 1317.5102
| -13% VAT for formwork | [7 empty] | 191.2402
| -13% VAT for water | [7 empty] | 28.116
6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer
| -Masonary wall | 1 | 8.5 | 1.225 | 4 | 41.65 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 5 | 0.725 | 2 | 7.25
| -for plinth level | 4 | 3.2764 | 0.45 | 0.6 | 3.5386
| Sub-total |  |  |  |  | 52.4386 | cum | 8987.83 | 471308.8206
| -13% VAT for cement | [7 empty] | 7994.9237
| -13% VAT for sand | [7 empty] | 9004.4769
| -13% VAT for stone | [7 empty] | 20190.3268
| -13% VAT for water | [7 empty] | 422.6548
7 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for chihaan | 1 | 1.5 | 1.6 |  | 2.4
| Sub-total |  |  |  |  | 2.4 | sqm | 1017.47 | 2441.928
| -13% VAT for brick | [7 empty] | 268.8566
8 | -High Density Polythene Pipe NS 40 pipe material PE 100, PN 16 |  | Length (m) | Weight (Kg/m) | Total weight (Kg)
| -for watersupply | 1 | 185 | 0.135 | 24.975 | 24.975
| Sub-total |  |  |  |  | 24.975 | kg | 287 | 7167.825
| -13% VAT for material | [7 empty] | 931.8173
9 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 786973.546
| Total Estimated | 786973.546 |  | 100
| Budget allocated | 700000
| Municipal payment | 665000 |  | 84.5009
| User contribution | 121973.546 |  | 15.4991
| Contingencies | 21000 |  | 3
| Maintanince | 14000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 786973.546 |  |  |  |  | Total Valuated Amount : |  | 789632.0852
Work Started : | [7 empty] | Work Finished:
Project:- तल्लो नाङ्गलेद्वारे चिहानपाटी | [7 empty] | F.Y:2082/2083
Location:- Shankharapur Municipality 1 | [7 empty] | Date:2083/03/15
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | Kg | 800.4142 | 182.51 | 146083.5878 | 880.0606 | 182.51 | 160619.854 | 14536.2661 |  | 182604.4848
| -13% VAT for excavator |  |  |  | 10281.3325 |  |  | 11304.3919 | 1023.0594 |  | 12851.6657
2 | )=$! dL=dL=afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd | sqm | 31.9075 | 1112.58 | 35499.6243 | 32.1549 | 1112.58 | 35774.8734 | 275.2491 |  | 44374.5304
| -13% VAT for sheet |  |  |  | 2924.5985 |  |  | 2947.2746 | 22.6761 |  | 3655.7481
| -13% VAT for nut bolt |  |  |  | 424.6487 |  |  | 427.9412 | 3.2925
| -13% VAT for j-hook |  |  |  | 144.4365 |  |  | 145.5564 | 1.1199
| -13% VAT for bitumen washer |  |  |  | 68.4415 |  |  | 68.9722 | 0.53067
3 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | cum | 23.1902 | 62.95 | 1459.8247 | 22.8822 | 62.95 | 1440.4318 | -19.3928 |  | 1824.7808
| -13% VAT for excavator |  |  |  | 155.8615 |  |  | 153.791 | -2.0705 |  | 194.8269
4 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | cum | 5.6869 | 4458.52 | 25355.1476 | 6.011 | 4458.52 | 26800.2367 | 1445.0891 |  | 31693.9345
| -13% VAT for stone |  |  |  | 2284.8172 |  |  | 2415.0379 | 130.2207 |  | 2856.0215
5 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 | cum | 3.4883 | 10964.46 | 38247.7328 | 3.396 | 10964.46 | 37235.2165 | -1012.5164 |  | 47809.6661
| -13% VAT for cement |  |  |  | 1627.0404 |  |  | 1583.9684 | -43.072 |  | 2033.8005
| -13% VAT for sand |  |  |  | 647.9558 |  |  | 630.8028 | -17.1531
| -13% VAT for aggregate |  |  |  | 1317.5102 |  |  | 1282.6323 | -34.8779
| -13% VAT for formwork |  |  |  | 191.2402 |  |  | 186.1776 | -5.0626
| -13% VAT for water |  |  |  | 28.116 |  |  | 27.3717 | -0.7443
6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer | cum | 52.4386 | 8987.83 | 471308.8206 | 51.0327 | 8987.83 | 458673.1263 | -12635.6944 |  | 589136.0258
| -13% VAT for cement |  |  |  | 7994.9237 |  |  | 7780.5814 | -214.3423 |  | 9993.6547
| -13% VAT for sand |  |  |  | 9004.4769 |  |  | 8763.0687 | -241.4082
| -13% VAT for stone |  |  |  | 20190.3268 |  |  | 19649.0282 | -541.2986
| -13% VAT for water |  |  |  | 422.6548 |  |  | 411.3235 | -11.3313
7 | ;'Vvf O{6f RofK6f] 5fKg] sfd | sqm | 2.4 | 1017.47 | 2441.928 | 2.4 | 1017.47 | 2441.928 | 0 |  | 3052.41
| -13% VAT for brick |  |  |  | 268.8566 |  |  | 268.8566 | 0 |  | 336.0708
8 | -High Density Polythene Pipe NS 40 pipe material PE 100, PN 16 | kg | 24.975 | 287 | 7167.825 | 24.975 | 287 | 7167.825 | 0 |  | 8959.7812
| -13% VAT for material |  |  |  | 931.8173 |  |  | 931.8173
9 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 786973.546 |  |  | 789632.0852 | 2658.5392

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- तल्लो नाङ्गलेद्वारे चिहानपाटी | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2083/03/15
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 3mm thickness for vertical post | 4 | 3.9622 | 6.5 | 103.0174 | 103.0174
| -MS square pipe horizontal of 3" * 3" of 3mm thickness for binding post | 4 | 3.505 | 6.5 | 91.1308 | 91.1308 | [7 empty] | 14.0201 | 45.9978
| -MS square pipe horizontal of 3" * 3" of 3mm thickness for base of upper portion | 2 | 3.505 | 6.5 | 45.5654 | 45.5654
| -MS square pipe vertical section of 3" * 3" of 3mm thickness for upper portion | 4 | 1.5 | 6.5 | 39 | 39
|  | 1 | 0.45 | 6.5 | 2.925 | 2.925
| -MS square pipe horizontal of 2" * 2" of 3mm thickness for diagnol of uppermost portion | 2 | 2.7431 | 4.43 | 24.3036 | 24.3036
| -MS square pipe horizontal of 2" * 2" of 3mm thickness for binding at mid portion of upper part | 4 | 1.7525 | 4.43 | 31.0546 | 31.0546
|  | 4 | 1.9557 | 4.43 | 34.6551 | 34.6551
| -MS square pipe horizontal of 2" * 2" of 3mm thickness as purlin at mid portion of upper part | 4 | 3.2521 | 4.43 | 57.6265 | 57.6265
|  | 4 | 4.5718 | 4.43 | 81.0119 | 81.0119
| -MS square pipe horizontal of 2" * 2" of 3mm thickness at corner of upper part | 4 | 1.9567 | 4.43 | 34.6731 | 34.6731
|  | 8 | 1.9567 | 4.43 | 69.3462 | 69.3462
| -MS square pipe horizontal of 2" * 2" of 3mm thickness as purlin at mid portion of uppermost part | 4 | 0.20319 | 4.43 | 3.6005 | 3.6005
|  | 4 | 1.3715 | 4.43 | 24.3036 | 24.3036
|  | 4 | 2.6669 | 4.43 | 47.2569 | 47.2569
| -MS square pipe horizontal of 2" * 2" of 3mm thickness at corner of uppermost part | 4 | 1.9049 | 4.43 | 33.755 | 33.755
|  | 8 | 1.8541 | 4.43 | 65.7096 | 65.7096
| -MS square pipe horizontal of 2" * 2" of 2mm thickness for vertical post of railing | 1 | 1.8287 | 3.01 | 5.5044 | 5.5044
|  | 4 | 1.5 | 3.01 | 18.06 | 18.06
| -MS square pipe horizontal of 1.5" * 1.5" of 2mm thickness for railing | 1 | 9.4229 | 2.26 | 21.2958 | 21.2958
|  | 2 | 9.1944 | 2.26 | 41.5585 | 41.5585
|  | 1 | 2.0827 | 2.26 | 4.7069 | 4.7069
| sub-total |  |  |  |  | 880.0606 | Kg | 182.51 | 160619.854
| -VAT 13% for materials | [7 empty] | 11304.3919
2 | )=$! dL=dL=afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -upper portion | 4 | 3.2002 | 1.7016 |  | 21.7823
| -uppermost portion | 4 | 1.5239 | 1.7016 |  | 10.3725
| sub-total |  |  |  |  | 32.1549 | sqm | 1112.58 | 35774.8734
| -13% VAT for sheet | [7 empty] | 2947.2746
| -13% VAT for nut bolt | [7 empty] | 427.9412
| -13% VAT for j-hook | [7 empty] | 145.5564
| -13% VAT for bitumen washer | [7 empty] | 68.9722
3 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -Masonary wall | 1 | 9.5245 | 1.7375 | 0.9 | 14.894
|  | 1 | 7.8229 | 0.95 | 0.75 | 5.5738
| -for footing of vertical post | 4 | 0.6 | 0.6 | 0.45 | 0.648
| -for plinth level | 4 | 3.124 | 0.45 | 0.3 | 1.687
| -for railing | 5 | 0.23 | 0.23 | 0.3 | 0.07935
| sub-total |  |  |  |  | 22.8822 | cum | 62.95 | 1440.4318
| -13% VAT for excavator | [7 empty] | 153.791
4 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Masonary wall | 1 | 9.5245 | 1.7375 | 0.15 | 2.4823
|  | 1 | 7.8229 | 0.95 | 0.15 | 1.1148
| -for footing of vertical post | 4 | 0.45 | 0.45 | 0.15 | 0.1215
| -for plinth level | 4 | 3.4044 | 0.45 | 0.15 | 0.9192
|  | 1 | 3.4044 | 3.4044 | 0.15 | 1.7385
| -deduction for chihaan | -1 | 1.5 | 1.8 | 0.15 | -0.405
| -for railing | 5 | 0.23 | 0.23 | 0.15 | 0.039675
| sub-total |  |  |  |  | 6.011 | cum | 4458.52 | 26800.2367
| -13% VAT for stone | [7 empty] | 2415.0379
5 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Masonary wall | 1 | 9.5245 | 1.7375 | 0.05 | 0.82744
|  | 1 | 9.5245 | 0.45 | 0.05 | 0.2143
|  | 1 | 7.8229 | 0.95 | 0.05 | 0.37159
|  | 1 | 7.8229 | 0.45 | 0.05 | 0.17602
| -for footing of vertical post | 4 | 0.45 | 0.45 | 0.3 | 0.243
| -for plinth level | 4 | 3.4044 | 0.45 | 0.05 | 0.3064
|  | 1 | 4.3188 | 4.3188 | 0.075 | 1.3989
| -deduction for chihaan | -1 | 1.5 | 1.8 | 0.075 | -0.2025
| -for railing | 5 | 0.23 | 0.23 | 0.23 | 0.060835
| sub-total |  |  |  |  | 3.396 | cum | 10964.46 | 37235.2165
| -13% VAT for cement | [7 empty] | 1583.9684
| -13% VAT for sand | [7 empty] | 630.8028
| -13% VAT for aggregate | [7 empty] | 1282.6323
| -13% VAT for formwork | [7 empty] | 186.1776
| -13% VAT for water | [7 empty] | 27.3717
6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer
| -Masonary wall | 1 | 9.5245 | 1.1187 | 3.475 | 37.0281 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 7.8229 | 0.725 | 1.9 | 10.7761
| -for plinth level | 2 | 4.3188 | 0.45718 | 0.45718 | 1.8054
|  | 2 | 3.4044 | 0.45718 | 0.45718 | 1.4231
| Sub-total |  |  |  |  | 51.0327 | cum | 8987.83 | 458673.1263
| -13% VAT for cement | [7 empty] | 7780.5814
| -13% VAT for sand | [7 empty] | 8763.0687
| -13% VAT for stone | [7 empty] | 19649.0282
| -13% VAT for water | [7 empty] | 411.3235
7 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for chihaan | 1 | 1.5 | 1.6 |  | 2.4
| Sub-total |  |  |  |  | 2.4 | sqm | 1017.47 | 2441.928
| -13% VAT for brick | [7 empty] | 268.8566
8 | -High Density Polythene Pipe NS 40 pipe material PE 100, PN 16 |  | Length (m) | Weight (Kg/m) | Total weight (Kg)
| -for watersupply | 1 | 185 | 0.135 | 24.975 | 24.975
| Sub-total |  |  |  |  | 24.975 | kg | 287 | 7167.825
| -13% VAT for material | [7 empty] | 931.8173
9 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 789632.0852
| Total Valuated | 789632.0852 |  | 100
| Budget allocated | 700000
| Municipal payment | 665000 |  | 84.2164
| User contribution | 124632.0852 |  | 15.7836
| Contingencies | 21000 |  | 3
| Maintanince | 14000 |  | 2

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Mesurement Sheet
Project:- तल्लो नाङ्गलेद्वारे चिहानपाटी | [9 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [9 empty] | Date:2083/03/15
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 3mm thickness for vertical post | 4 | 3.9622 | 6.5 | 103.0174 | 103.0174
| -MS square pipe horizontal of 3" * 3" of 3mm thickness for binding post | 4 | 3.505 | 6.5 | 91.1308 | 91.1308 | [7 empty] | 14.0201 | 45.9978
| -MS square pipe horizontal of 3" * 3" of 3mm thickness for base of upper portion | 2 | 3.505 | 6.5 | 45.5654 | 45.5654
| -MS square pipe vertical section of 3" * 3" of 3mm thickness for upper portion | 4 | 1.5 | 6.5 | 39 | 39
|  | 1 | 0.45 | 6.5 | 2.925 | 2.925
| -MS square pipe horizontal of 2" * 2" of 3mm thickness for diagnol of uppermost portion | 2 | 2.7431 | 4.43 | 24.3036 | 24.3036
| -MS square pipe horizontal of 2" * 2" of 3mm thickness for binding at mid portion of upper part | 4 | 1.7525 | 4.43 | 31.0546 | 31.0546
|  | 4 | 1.9557 | 4.43 | 34.6551 | 34.6551
| -MS square pipe horizontal of 2" * 2" of 3mm thickness as purlin at mid portion of upper part | 4 | 3.2521 | 4.43 | 57.6265 | 57.6265
|  | 4 | 4.5718 | 4.43 | 81.0119 | 81.0119
| -MS square pipe horizontal of 2" * 2" of 3mm thickness at corner of upper part | 4 | 1.9567 | 4.43 | 34.6731 | 34.6731
|  | 8 | 1.9567 | 4.43 | 69.3462 | 69.3462
| -MS square pipe horizontal of 2" * 2" of 3mm thickness as purlin at mid portion of uppermost part | 4 | 0.20319 | 4.43 | 3.6005 | 3.6005
|  | 4 | 1.3715 | 4.43 | 24.3036 | 24.3036
|  | 4 | 2.6669 | 4.43 | 47.2569 | 47.2569
| -MS square pipe horizontal of 2" * 2" of 3mm thickness at corner of uppermost part | 4 | 1.9049 | 4.43 | 33.755 | 33.755
|  | 8 | 1.8541 | 4.43 | 65.7096 | 65.7096
| -MS square pipe horizontal of 2" * 2" of 2mm thickness for vertical post of railing | 1 | 1.8287 | 3.01 | 5.5044 | 5.5044
|  | 4 | 1.5 | 3.01 | 18.06 | 18.06
| -MS square pipe horizontal of 1.5" * 1.5" of 2mm thickness for railing | 1 | 9.4229 | 2.26 | 21.2958 | 21.2958
|  | 2 | 9.1944 | 2.26 | 41.5585 | 41.5585
|  | 1 | 2.0827 | 2.26 | 4.7069 | 4.7069
| sub-total |  |  |  |  | 880.0606 | Kg | 182.51 | 160619.854
| -VAT 13% for materials | [7 empty] | 11304.3919
2 | )=$! dL=dL=afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -upper portion | 4 | 3.2002 | 1.7016 |  | 21.7823
| -uppermost portion | 4 | 1.5239 | 1.7016 |  | 10.3725
| sub-total |  |  |  |  | 32.1549 | sqm | 1112.58 | 35774.8734
| -13% VAT for sheet | [7 empty] | 2947.2746
| -13% VAT for nut bolt | [7 empty] | 427.9412
| -13% VAT for j-hook | [7 empty] | 145.5564
| -13% VAT for bitumen washer | [7 empty] | 68.9722
3 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -Masonary wall | 1 | 9.5245 | 1.7375 | 0.9 | 14.894
|  | 1 | 7.8229 | 0.95 | 0.75 | 5.5738
| -for footing of vertical post | 4 | 0.6 | 0.6 | 0.45 | 0.648
| -for plinth level | 4 | 3.124 | 0.45 | 0.3 | 1.687
| -for railing | 5 | 0.23 | 0.23 | 0.3 | 0.07935
| sub-total |  |  |  |  | 22.8822 | cum | 62.95 | 1440.4318
| -13% VAT for excavator | [7 empty] | 153.791
4 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Masonary wall | 1 | 9.5245 | 1.7375 | 0.15 | 2.4823
|  | 1 | 7.8229 | 0.95 | 0.15 | 1.1148
| -for footing of vertical post | 4 | 0.45 | 0.45 | 0.15 | 0.1215
| -for plinth level | 4 | 3.4044 | 0.45 | 0.15 | 0.9192
|  | 1 | 3.4044 | 3.4044 | 0.15 | 1.7385
| -deduction for chihaan | -1 | 1.5 | 1.8 | 0.15 | -0.405
| -for railing | 5 | 0.23 | 0.23 | 0.15 | 0.039675
| sub-total |  |  |  |  | 6.011 | cum | 4458.52 | 26800.2367
| -13% VAT for stone | [7 empty] | 2415.0379
5 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Masonary wall | 1 | 9.5245 | 1.7375 | 0.05 | 0.82744
|  | 1 | 9.5245 | 0.45 | 0.05 | 0.2143
|  | 1 | 7.8229 | 0.95 | 0.05 | 0.37159
|  | 1 | 7.8229 | 0.45 | 0.05 | 0.17602
| -for footing of vertical post | 4 | 0.45 | 0.45 | 0.3 | 0.243
| -for plinth level | 4 | 3.4044 | 0.45 | 0.05 | 0.3064
|  | 1 | 4.3188 | 4.3188 | 0.075 | 1.3989
| -deduction for chihaan | -1 | 1.5 | 1.8 | 0.075 | -0.2025
| -for railing | 5 | 0.23 | 0.23 | 0.23 | 0.060835
| sub-total |  |  |  |  | 3.396 | cum | 10964.46 | 37235.2165
| -13% VAT for cement | [7 empty] | 1583.9684
| -13% VAT for sand | [7 empty] | 630.8028
| -13% VAT for aggregate | [7 empty] | 1282.6323
| -13% VAT for formwork | [7 empty] | 186.1776
| -13% VAT for water | [7 empty] | 27.3717
6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer
| -Masonary wall | 1 | 9.5245 | 1.1187 | 3.475 | 37.0281 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 7.8229 | 0.725 | 1.9 | 10.7761
| -for plinth level | 2 | 4.3188 | 0.45718 | 0.45718 | 1.8054
|  | 2 | 3.4044 | 0.45718 | 0.45718 | 1.4231
| Sub-total |  |  |  |  | 51.0327 | cum | 8987.83 | 458673.1263
| -13% VAT for cement | [7 empty] | 7780.5814
| -13% VAT for sand | [7 empty] | 8763.0687
| -13% VAT for stone | [7 empty] | 19649.0282
| -13% VAT for water | [7 empty] | 411.3235
7 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for chihaan | 1 | 1.5 | 1.6 |  | 2.4
| Sub-total |  |  |  |  | 2.4 | sqm | 1017.47 | 2441.928
| -13% VAT for brick | [7 empty] | 268.8566
8 | -High Density Polythene Pipe NS 40 pipe material PE 100, PN 16 |  | Length (m) | Weight (Kg/m) | Total weight (Kg)
| -for watersupply | 1 | 185 | 0.135 | 24.975 | 24.975
| Sub-total |  |  |  |  | 24.975 | kg | 287 | 7167.825
| -13% VAT for material | [7 empty] | 931.8173
9 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 789632.0852
| Total Valuated | 789632.0852 |  | 100
| Budget allocated | 700000
| Municipal payment | 665000 |  | 84.2164
| User contribution | 124632.0852 |  | 15.7836
| Contingencies | 21000 |  | 3
| Maintanince | 14000 |  | 2

## With measurement (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- तल्लो नाङ्गलेद्वारे चिहानपाटी | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/09/07
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 3mm thickness for vertical post | 4 | 3.9622 | 6.5 | 103.0174 | 103.0174 |  |  | 39kg per pipe
| -MS square pipe horizontal of 3" * 3" of 3mm thickness for binding post | 4 | 3.505 | 6.5 | 91.1308 | 91.1308 |  |  | 6.0957 |  |  |  |  | 14.0201 | 45.9978
| -MS square pipe horizontal of 3" * 3" of 3mm thickness for base of upper portion | 2 | 3.505 | 6.5 | 45.5654 | 45.5654
| -MS square pipe vertical section of 3" * 3" of 3mm thickness for upper portion | 4 | 1.5 | 6.5 | 39 | 39
|  | 1 | 0.45 | 6.5 | 2.925 | 2.925 |  | 1.8333
| -MS square pipe horizontal of 2" * 2" of 3mm thickness for diagnol of uppermost portion | 2 | 2.7431 | 4.43 | 24.3036 | 24.3036 |  | 9.1667
| -MS square pipe horizontal of 2" * 2" of 3mm thickness for binding at mid portion of upper part | 4 | 1.7525 | 4.43 | 31.0546 | 31.0546 |  | 5.9167
|  | 4 | 1.9557 | 4.43 | 34.6551 | 34.6551 |  | 6.4167
| -MS square pipe horizontal of 2" * 2" of 3mm thickness as purlin at mid portion of upper part | 4 | 3.2521 | 4.43 | 57.6265 | 57.6265 |  | 10.6667
|  | 4 | 4.5718 | 4.43 | 81.0119 | 81.0119 |  | 15.25
| -MS square pipe horizontal of 2" * 2" of 3mm thickness at corner of upper part | 4 | 1.9567 | 4.43 | 34.6731 | 34.6731 |  | 6.8333
|  | 8 | 1.9567 | 4.43 | 69.3462 | 69.3462 |  | 6.5833
| -MS square pipe horizontal of 2" * 2" of 3mm thickness as purlin at mid portion of uppermost part | 4 | 0.20319 | 4.43 | 3.6005 | 3.6005 |  | 0.66667
|  | 4 | 1.3715 | 4.43 | 24.3036 | 24.3036 |  | 4.5
|  | 4 | 2.6669 | 4.43 | 47.2569 | 47.2569 |  | 8.75
| -MS square pipe horizontal of 2" * 2" of 3mm thickness at corner of uppermost part | 4 | 1.9049 | 4.43 | 33.755 | 33.755 |  | 6.25
|  | 8 | 1.8541 | 4.43 | 65.7096 | 65.7096 |  | 6.0833
| -MS square pipe horizontal of 2" * 2" of 2mm thickness for vertical post of railing | 1 | 1.8287 | 3.01 | 5.5044 | 5.5044 |  | 6ft
|  | 4 | 1.5 | 3.01 | 18.06 | 18.06
| -MS square pipe horizontal of 1.5" * 1.5" of 2mm thickness for railing | 1 | 9.4229 | 2.26 | 21.2958 | 21.2958
|  | 2 | 9.1944 | 2.26 | 41.5585 | 41.5585
|  | 1 | 2.0827 | 2.26 | 4.7069 | 4.7069
| sub-total |  |  |  |  | 880.0606 | Kg | 182.51 | 160619.854
| -VAT 13% for materials | [7 empty] | 11304.3919
2 | )=$! dL=dL=afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -upper portion | 4 | 3.2002 | 1.7016 |  | 21.7823 |  | 15.25
| -uppermost portion | 4 | 1.5239 | 1.7016 |  | 10.3725
| sub-total |  |  |  |  | 32.1549 | sqm | 1112.58 | 35774.8734
| -13% VAT for sheet | [7 empty] | 2947.2746
| -13% VAT for nut bolt | [7 empty] | 427.9412
| -13% VAT for j-hook | [7 empty] | 145.5564
| -13% VAT for bitumen washer | [7 empty] | 68.9722
3 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -Masonary wall | 1 | 9.5245 | 1.75 | 0.9 | 15.0011
|  | 1 | 7.8229 | 1 | 0.75 | 5.8672
| -for footing of vertical post | 4 | 0.6 | 0.6 | 0.45 | 0.648
| -for plinth level | 4 | 3.124 | 0.45 | 0.3 | 1.687
| -for railing | 5 | 0.3 | 0.3 | 0.3 | 0.135
| sub-total |  |  |  |  | 23.3383 | cum | 62.95 | 1469.1471
| -13% VAT for excavator | [7 empty] | 156.8568
4 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Masonary wall | 1 | 9.5245 | 1.75 | 0.15 | 2.5002
|  | 1 | 7.8229 | 1 | 0.15 | 1.1734
| -for footing of vertical post | 4 | 0.45 | 0.45 | 0.15 | 0.1215
| -for plinth level | 4 | 3.4044 | 0.45 | 0.15 | 0.9192
|  | 1 | 3.4044 | 3.4044 | 0.15 | 1.7385
| -deduction for chihaan | -1 | 1.5 | 1.8 | 0.15 | -0.405
| -for railing | 5 | 0.3 | 0.3 | 0.15 | 0.0675
| sub-total |  |  |  |  | 6.1154 | cum | 4458.52 | 27265.5073
| -13% VAT for stone | [7 empty] | 2456.9646
5 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Masonary wall | 1 | 9.5245 | 1.75 | 0.05 | 0.8334
|  | 1 | 9.5245 | 0.45 | 0.05 | 0.2143
|  | 1 | 7.8229 | 1 | 0.05 | 0.39115
|  | 1 | 7.8229 | 0.45 | 0.05 | 0.17602
| -for footing of vertical post | 4 | 0.45 | 0.45 | 0.3 | 0.243
| -for plinth level | 4 | 3.4044 | 0.45 | 0.05 | 0.3064
|  | 1 | 4.3188 | 4.3188 | 0.075 | 1.3989
| -deduction for chihaan | -1 | 1.5 | 1.8 | 0.075 | -0.2025
| -for railing | 5 | 0.3 | 0.3 | 0.3 | 0.135
| sub-total |  |  |  |  | 3.4957 | cum | 10964.46 | 38328.1005
| -13% VAT for cement | [7 empty] | 1630.4592
| -13% VAT for sand | [7 empty] | 649.3173
| -13% VAT for aggregate | [7 empty] | 1320.2786
| -13% VAT for formwork | [7 empty] | 191.642
| -13% VAT for water | [7 empty] | 28.1751
6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer
| -Masonary wall | 1 | 9.5245 | 1.125 | 3.5 | 37.5029 |  | 9.5245 |  |  | 7 | 2 | 160.098
|  | 1 | 7.8229 | 0.75 | 2 | 11.7344 |  | 7.8482
| -for plinth level | 2 | 4.3188 | 0.45718 | 0.45718 | 1.8054
|  | 2 | 3.4044 | 0.45718 | 0.45718 | 1.4231
| Sub-total |  |  |  |  | 52.4657 | cum | 8987.83 | 471553.1022
| -13% VAT for cement | [7 empty] | 7999.0675
| -13% VAT for sand | [7 empty] | 9009.1439
| -13% VAT for stone | [7 empty] | 20200.7915
| -13% VAT for water | [7 empty] | 422.8738
7 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for chihaan | 1 | 1.5 | 1.6 |  | 2.4
| Sub-total |  |  |  |  | 2.4 | sqm | 1017.47 | 2441.928
| -13% VAT for brick | [7 empty] | 268.8566
8 | -High Density Polythene Pipe NS 40 pipe material PE 100, PN 16 |  | Length (m) | Weight (Kg/m) | Total weight (Kg)
| -for watersupply | 1 | 185 | 0.135 | 24.975 | 24.975
| Sub-total |  |  |  |  | 24.975 | kg | 287 | 7167.825
| -13% VAT for material | [7 empty] | 931.8173
9 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 805286.8139
| Total Estimated | 805286.8139 |  | 100
| Budget allocated | 700000
| Municipal payment | 665000 |  | 82.5793
| User contribution | 140286.8139 |  | 17.4207
| Contingencies | 21000 |  | 3
| Maintanince | 14000 |  | 2