## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- 5fke~Hofª ah¦of]lugL dlGb/ k"jf{wf/ ljsf; | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter and backfilling, all lifts and lead as per Drawing and instruction of the Engineer.
| -for masonary wall | 1 | 5.5 | 1.5 | 1 | 8.25 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 13 | 1.5 | 1 | 19.5
|  | 1 | 5 | 1.075 | 0.6 | 3.225
| Sub-total |  |  |  |  | 30.975 | m3 | 62.95 | 1949.8763
| -13% VAT for materials | [7 empty] | 208.183
2 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | [13 empty] | 20 | 0.3
| -for masonary wall | 1 | 5.5 | 1.5 | 0.15 | 1.2375 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 13 | 1.5 | 0.15 | 2.925
|  | 1 | 5 | 1.075 | 0.15 | 0.80625
| -for steps | 1 | 6 | 1.2 | 0.15 | 1.08
| Sub-total |  |  |  |  | 6.0488 | m3 | 4458.52 | 26968.4729
| -13% VAT for materials | [7 empty] | 2330.3269
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -for masonary wall | 1 | 5.5 | 1.5 | 0.05 | 0.4125 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 5.5 | 0.45 | 0.05 | 0.12375
|  | 1 | 13 | 1.5 | 0.05 | 0.975
|  | 1 | 13 | 0.45 | 0.05 | 0.2925
|  | 1 | 5 | 1.075 | 0.05 | 0.26875
|  | 1 | 5 | 0.45 | 0.05 | 0.1125
| -for steps | 1 | 6 | 1.2 | 0.075 | 0.54
|  | 0.5 | 6 | 0.5 | 0.05 | 0.075
| Sub-total |  |  |  |  | 2.8 | m3 | 10964.46 | 30700.488
| -13% VAT for cement | [7 empty] | 1305.9842
| -13% VAT for sand | [7 empty] | 520.0978
| -13% VAT for aggregate | [7 empty] | 1057.5321
| -13% VAT for formworks | [7 empty] | 153.5037
| -13% VAT for water | [7 empty] | 22.568
4 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer
| -for masonary wall | 1 | 5.5 | 0.975 | 3 | 16.0875 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 13 | 0.975 | 3 | 38.025 | [7 empty] | 3.199 | 9.843
|  | 1 | 5 | 0.7625 | 2.15 | 8.1969
| -for steps | 0.5 | 6 | 0.5 | 1.5 | 2.25
| Sub-total |  |  |  |  | 64.5594 | m3 | 8987.83 | 580248.6874
| -13% VAT for cement | [7 empty] | 9842.8966
| -13% VAT for sand | [7 empty] | 11085.8012
| -13% VAT for stone | [7 empty] | 24857.1851
| -13% VAT for water | [7 empty] | 520.3486
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 692271.9516
| Total Estimated | 692271.9516 |  | 100
| Budget allocated | 600000
| Municipal payment | 570000 |  | 82.3376
| User contribution | 122271.9516 |  | 17.6624
| Contingencies | 18000 |  | 3
| Maintanince | 12000 |  | 2

## for upabhokta (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- 5fke~Hofª ah¦of]lugL dlGb/ k"jf{wf/ ljsf; | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter and backfilling, all lifts and lead as per Drawing and instruction of the Engineer.
| -for masonary wall | 1 | 5.5 | 1.5 | 1 | 8.25 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 13 | 1.5 | 1 | 19.5
|  | 1 | 5 | 1.075 | 0.6 | 3.225
| Sub-total |  |  |  |  | 30.975 | m3 | 62.95 | 1949.8763
| -13% VAT for materials | [7 empty] | 208.183
2 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | [13 empty] | 20 | 0.3
| -for masonary wall | 1 | 5.5 | 1.5 | 0.15 | 1.2375 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 13 | 1.5 | 0.15 | 2.925
|  | 1 | 5 | 1.075 | 0.15 | 0.80625
| -for steps | 1 | 6 | 1.2 | 0.15 | 1.08
| Sub-total |  |  |  |  | 6.0488 | m3 | 4458.52 | 26968.4729
| -13% VAT for materials | [7 empty] | 2330.3269
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -for masonary wall | 1 | 5.5 | 1.5 | 0.05 | 0.4125 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 5.5 | 0.45 | 0.05 | 0.12375
|  | 1 | 13 | 1.5 | 0.05 | 0.975
|  | 1 | 13 | 0.45 | 0.05 | 0.2925
|  | 1 | 5 | 1.075 | 0.05 | 0.26875
|  | 1 | 5 | 0.45 | 0.05 | 0.1125
| -for steps | 1 | 6 | 1.2 | 0.075 | 0.54
|  | 0.5 | 6 | 0.5 | 0.05 | 0.075
| Sub-total |  |  |  |  | 2.8 | m3 | 10964.46 | 30700.488
| -13% VAT for cement | [7 empty] | 1305.9842
| -13% VAT for sand | [7 empty] | 520.0978
| -13% VAT for aggregate | [7 empty] | 1057.5321
| -13% VAT for formworks | [7 empty] | 153.5037
| -13% VAT for water | [7 empty] | 22.568
4 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer
| -for masonary wall | 1 | 5.5 | 0.975 | 3 | 16.0875 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 13 | 0.975 | 3 | 38.025 | [7 empty] | 3.199 | 9.843
|  | 1 | 5 | 0.7625 | 2.15 | 8.1969
| -for steps | 0.5 | 6 | 0.5 | 1.5 | 2.25
| Sub-total |  |  |  |  | 64.5594 | m3 | 8987.83 | 580248.6874
| -13% VAT for cement | [7 empty] | 9842.8966
| -13% VAT for sand | [7 empty] | 11085.8012
| -13% VAT for stone | [7 empty] | 24857.1851
| -13% VAT for water | [7 empty] | 520.3486
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 692271.9516
| Total Estimated | 692271.9516 |  | 100
| Budget allocated | 600000
| Municipal payment | 570000 |  | 82.3376
| User contribution | 122271.9516 |  | 17.6624
| Contingencies | 18000 |  | 3
| Maintanince | 12000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 692271.9516 |  |  |  |  | Total Valuated Amount : |  | 637930.6912
Work Started : | [7 empty] | Work Finished:
Project:- 5fke~Hofª ah¦of]lugL dlGb/ k"jf{wf/ ljsf; | [7 empty] | F.Y:2082/2083
Location:- Shankharapur Municipality 1 | [7 empty] | Date:2082/12/09
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter and backfilling, all lifts and lead as per Drawing and instruction of the Engineer. | cum | 30.975 | 62.95 | 1949.8763 | 27.36 | 62.95 | 1722.312 | -227.5643 |  | 2437.3453
| -13% VAT for materials |  |  |  | 208.183 |  |  | 183.8866 | -24.2964
2 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | m3 | 6.0488 | 4458.52 | 26968.4729 | 4.635 | 4458.52 | 20665.2402 | -6303.2327 |  | 33710.5911
| -13% VAT for materials |  |  |  | 2330.3269 |  |  | 1785.669 | -544.6579
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 | m3 | 2.8 | 10964.46 | 30700.488 | 2.0085 | 10964.46 | 22022.1179 | -8678.3701 |  | 38375.61
| -13% VAT for cement |  |  |  | 1305.9842 |  |  | 936.8104 | -369.1737 |  | 1632.4802
| -13% VAT for sand |  |  |  | 520.0978 |  |  | 373.0773 | -147.0205
| -13% VAT for aggregate |  |  |  | 1057.5321 |  |  | 758.5904 | -298.9417
| -13% VAT for formworks |  |  |  | 153.5037 |  |  | 110.1115 | -43.3922
| -13% VAT for water |  |  |  | 22.568 |  |  | 16.1885 | -6.3795
4 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer | m3 | 64.5594 | 8987.83 | 580248.6874 | 60.675 | 8987.83 | 545336.5853 | -34912.1022 |  | 725310.8593
| -13% VAT for cement |  |  |  | 9842.8966 |  |  | 9250.6743 | -592.2223 |  | 12303.6208
| -13% VAT for sand |  |  |  | 11085.8012 |  |  | 10418.7965 | -667.0047
| -13% VAT for stone |  |  |  | 24857.1851 |  |  | 23361.5909 | -1495.5942
| -13% VAT for water |  |  |  | 520.3486 |  |  | 489.0405 | -31.3081
5 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 692271.9516 |  |  | 637930.6912 | -54341.2604

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- 5fke~Hofª ah¦of]lugL dlGb/ k"jf{wf/ ljsf; | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter and backfilling, all lifts and lead as per Drawing and instruction of the Engineer.
| -for masonary wall | 1 | 5.9 | 1.5 | 0.6 | 5.31 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 7.2 | 1.5 | 1 | 10.8
|  | 1 | 7.5 | 1.5 | 1 | 11.25
| Sub-total |  |  |  |  | 27.36 | m3 | 62.95 | 1722.312
| -13% VAT for materials | [7 empty] | 183.8866
2 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | [13 empty] | 20 | 0.3
| -for masonary wall | 1 | 5.9 | 1.5 | 0.15 | 1.3275 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 7.2 | 1.5 | 0.15 | 1.62
|  | 1 | 7.5 | 1.5 | 0.15 | 1.6875
| -for steps | 0 | 6 | 1.2 | 0.15 | 0
| Sub-total |  |  |  |  | 4.635 | m3 | 4458.52 | 20665.2402
| -13% VAT for materials | [7 empty] | 1785.669
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -for masonary wall | 1 | 5.9 | 1.5 | 0.05 | 0.4425 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 5.9 | 0.45 | 0.05 | 0.13275
|  | 1 | 7.2 | 1.5 | 0.05 | 0.54
|  | 1 | 7.2 | 0.45 | 0.05 | 0.162
|  | 1 | 7.5 | 1.5 | 0.05 | 0.5625
|  | 1 | 7.5 | 0.45 | 0.05 | 0.16875
| -for steps | 0 | 6 | 1.2 | 0.075 | 0
|  | 0 | 6 | 0.5 | 0.05 | 0
| Sub-total |  |  |  |  | 2.0085 | m3 | 10964.46 | 22022.1179
| -13% VAT for cement | [7 empty] | 936.8104
| -13% VAT for sand | [7 empty] | 373.0773
| -13% VAT for aggregate | [7 empty] | 758.5904
| -13% VAT for formworks | [7 empty] | 110.1115
| -13% VAT for water | [7 empty] | 16.1885
4 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer
| -for masonary wall | 1 | 5.9 | 1 | 3 | 17.7 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 7.2 | 1 | 3 | 21.6 | [7 empty] | 3.281 | 9.843
|  | 1 | 7.5 | 0.95 | 3 | 21.375
| -for steps | 0 | 6 | 0.5 | 0.5 | 0
| Sub-total |  |  |  |  | 60.675 | m3 | 8987.83 | 545336.5853
| -13% VAT for cement | [7 empty] | 9250.6743
| -13% VAT for sand | [7 empty] | 10418.7965
| -13% VAT for stone | [7 empty] | 23361.5909
| -13% VAT for water | [7 empty] | 489.0405
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 637930.6912
| Total Valuated | 637930.6912 |  | 100
| Budget allocated | 600000
| Municipal payment | 570000 |  | 89.3514
| User contribution | 67930.6912 |  | 10.6486
| Contingencies | 18000 |  | 3
| Maintanince | 12000 |  | 2