## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- 5fk 9'+ufgf ltjfl/ al:t k}bn dfu{ | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer.
| -l;9L | 1 | 25.2 | 1.5 | 0.25 | 9.45
|  | 0.5 | 5 | 0.6 | 1.5 | 2.25
| sub-total |  |  |  |  | 11.7 | cum | 861.235 | 10076.4495
2 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -l;9L | 1 | 30.2 | 1.5 | 0.15 | 6.795
| -masonary wall | 1 | 25.5 | 0.45 | 0.15 | 1.7212
| sub-total |  |  |  |  | 8.5162 | cum | 5127.298 | 43665.3516
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15, Manual Mixing
| -l;9L | 1 | 30.2 | 1.5 | 0.1 | 4.53
| -masonary wall | 1 | 25.5 | 0.45 | 0.05 | 0.57375
| -for top cover | 1 | 25.5 | 0.45 | 0.05 | 0.57375
| sub-total |  |  |  |  | 5.6775 | cum | 13325.648 | 75656.3665
4 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in the Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -masonary wall | 1 | 25.5 | 0.45 | 1.5 | 17.2125 |  |  |  |  | 266666.6667
| sub-total |  |  |  |  | 17.2125 | cum | 11360.1945 | 195537.3478
5 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications | No. | Length (m) | Unit Weight (Kg/m) | Weight (Kg) | Total Weight (MT)
| -for slab over culvert | 14 | 1.2 | 0.61728 | 10.3704 | 0.01037
| sub-total |  |  |  |  | 0.01037 | tonne | 143008.25 | 1483.0485
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 326918.564
| Total Estimated | 326918.564