## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- 9sfnufpF ;fd'bflos ejg | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for foundation | 4 | 1.5 | 1.5 | 1.5 | 13.5
| -for wall below tie beam | 4 | 0.55867 | 0.23 | 1.04 | 0.53454 |  |  |  |  | 1.0667 | 1.2953
| Sub-total |  |  |  |  | 14.0345 | cum | 775.238 | 10880.106
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for foundation | 4 | 1.5 | 1.5 |  | 9
| -for wall below tie beam | 4 | 1.7272 | 0.23 |  | 1.589
| -for flooring | 1 | 1.9811 | 1.9811 |  | 3.9248
| Sub-total |  |  |  |  | 14.5138 | sqm | 1170.0905 | 16982.4716
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd-lk=;L=;L= +!M#M^_
| -for foundation | 4 | 1.5 | 1.5 | 0.075 | 0.675
| -for wall below tie beam | 4 | 1.7272 | 0.23 | 0.075 | 0.11918
| -for flooring | 1 | 1.9811 | 1.9811 | 0.075 | 0.29436
| Sub-total |  |  |  |  | 1.0885 | cum | 5169.986 | 5627.7147
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for foundation | 4 | 1.5 | 1.5 | 0.45 | 4.05
| -for tie beam | 4 | 1.7272 | 0.23 | 0.23 | 0.36548
| -for neck column | 4 | 0.35 | 0.35 | 1.5239 | 0.74672
| -GF column | 4 | 0.35 | 0.35 | 2.7156 | 1.3307
| -for beam | 4 | 1.7272 | 0.23 | 0.23 | 0.36548
| -for cantilever beam | 2 | 0.6 | 0.23 | 0.23 | 0.06348
| -for inclined slab | 4 | 1.4986 | 1.2191 | 0.075 | 0.54811
| -for cantilever slab | 2 | 3.6574 | 0.6 | 0.125 | 0.54861
|  | 2 | 2.4383 | 0.6 | 0.125 | 0.36574
| Sub-total |  |  |  |  | 8.3843 | cum | 16050.8835 | 134575.2667
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for neck column | 4 | 0.35 |  | 1.2939 | 1.8115
| -for tie beam | 4 | 1.7272 |  | 0.46 | 3.1781
| -GF column | 4 | 1.4 |  | 2.7156 | 15.2076
| -for beam | 4 | 1.7272 |  | 0.46 | 3.1781
| -for cantilever beam | 8 | 0.6 |  | 0.46 | 2.208
| -for inclined slab | 4 | 1.4986 | 1.2191 |  | 7.3082
| -for cantilever slab | 2 | 3.6574 | 0.6 |  | 4.3889
|  | 2 | 2.4383 | 0.6 |  | 2.9259
| Sub-total |  |  |  |  | 40.2062 | sqm | 1061.1165 | 42663.4749
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit Weight (Kg/m) | Total Weight (Kg)
| -for foundation | 10 | 1.5 | 0.88889 | 13.3333 | 0.013333
|  | 10 | 1.5 | 0.88889 | 13.3333 | 0.013333
| -for neck column to 1st floor | 16 | 5.6925 | 0.88889 | 80.9605 | 0.08096
|  | 16 | 5.9025 | 1.5802 | 149.2393 | 0.14924 |  |  |  |  | 5.0777
| -for binding stirrups | 112 | 1.118 | 0.39506 | 49.4659 | 0.049466 |  |  |  |  | 15.49 | 4.7211
|  | 112 | 1.0155 | 0.39506 | 44.9347 | 0.044935
| -for tie beam | 16 | 2.7431 | 0.88889 | 39.0125 | 0.039012
| .-for stirrups | 44 | 0.81439 | 0.39506 | 14.1562 | 0.014156
| -for beam | 16 | 3.9622 | 0.88889 | 56.3514 | 0.056351
|  | 30 | 0.81439 | 0.39506 | 9.652 | 0.009652
| -for inclined slab | 60 | 0.74931 | 0.61728 | 27.7524 | 0.027752
|  | 40 | 1.2191 | 0.61728 | 30.1022 | 0.030102
| -for cantilever | 32 | 3.5538 | 0.39506 | 44.927 | 0.044927
|  | 104 | 0.6 | 0.39506 | 24.6519 | 0.024652
| Sub-total |  |  |  |  | 0.59787 | MT | 152214 | 91004.5852
7 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_
| -for flooring | 1 | 2.4383 | 2.4383 |  | 5.9452
| Sub-total |  |  |  |  | 5.9452 | sqm | 793.477 | 4717.3908
8 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
| -for flooring | 1 | 2.4383 | 2.4383 |  | 5.9452
| Sub-total |  |  |  |  | 5.9452 | sqm | 477.825 | 2840.772
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for tie beam | 4 | 1.7272 | 0.23 | 1.0667 | 1.6951
| -at GF wall | 2 | 1.7272 | 0.23 | 2.4901 | 1.9784
|  | 1 | 1.7272 | 0.23 | 2.4901 | 0.98921
| -deduction for window | -2 | 0.75 | 0.23 | 0.75 | -0.25875
| Sub-total |  |  |  |  | 4.404 | cum | 16665.616 | 73395.3685
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -at GF wall | 4 | 1.7272 |  | 2.4901 | 17.2037
|  | 2 | 1.7272 |  | 2.4901 | 8.6019
| -deduction for window | -4 | 0.75 |  | 0.75 | -2.25
| -for inclined slab | 4 | 1.4986 | 1.2191 |  | 7.3082
| Sub-total |  |  |  |  | 30.8638 | sqm | 477.825 | 14747.4763
11 | Knfi6/ dfly @) dL=dL= afSnf] emNn/ jf kfgL k§L agfpg] sfd
| -for cantilever slab | 4 | 3.6574 |  |  | 14.6297
| Sub-total |  |  |  |  | 14.6297 | rm | 166.0715 | 2429.5739
12 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -at GF wall | 4 | 1.7272 |  | 2.4901 | 17.2037
|  | 2 | 1.7272 |  | 2.4901 | 8.6019
| -deduction for window | -4 | 0.75 |  | 0.75 | -2.25
| Sub-total |  |  |  |  | 23.5556 | cum | 291.87 | 6875.1747
13 | kmnfd] sf]nfK;Lan u]6 k]lG6Ë / h8fg ;d]t ug]{
| -for chain gate | 1 | 1.7251 |  | 2.4901 | 4.2956
| Sub-total |  |  |  |  | 4.2956 | cum | 7350.1445 | 31573.4402
14 | #* dL=dL= afSnf] lr/fg cu¦fv sf7sf] k¦m]d xfnL l8nfvfkf agfO
| -for window | 2 | 0.75 |  | 0.75 | 1.125
| Sub-total |  |  |  |  | 1.125 | sqm | 18354.943 | 20649.3109
15 | Provisional sum for lab tests and other unforseen works | 1 |  |  |  | 1 | PS | 15000 | 15000
16 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 474462.1264
| Total Estimated | 474462.1264