## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:-सुकपानी स्याले सिंचाई कुलो मर्मत | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/09/03
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in ordinary rock by Manual Means ., Roadway Excavation in ordinary rock as per Drawing and Technical specification, including all lift and lead as per Drawing and instruction of the Engineer.
| -for base preparation | 1 | 6 | 1 | 1 | 6 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 6 | m3 | 866.66 | 5199.96
2 | Gabion Structure for Retaining Earth, Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 1.0 X 1 X 1 m ( 6 sqm)
| -for gabion wall | 6 | 2 | 1 | 1 | 12 |  |  |  |  | 7 | 2 | 160.098
|  | 6 | 1.5 | 1 | 1 | 9
|  | 2 | 1 | 1 | 1 | 2
| Sub-total |  |  |  |  | 23 | m3 | 6421.62 | 147697.26
| -13% VAT for stone | [7 empty] | 8122.5144
| -13% VAT for mesh wire | [7 empty] | 4831.1785
| -13% VAT for selvedge wire | [7 empty] | 635.7786
| -13% VAT for binding wire | [7 empty] | 255.346
3 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.
| -at back of gabion wall | 1 | 6 |  | 2 | 12
| Sub-total |  |  |  |  | 12 | m2 | 161.58 | 1938.96
| -13% VAT for stone | [7 empty] | 235.872
4 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 169416.8695
| Total Estimated | 169416.8695 |  | 100
| Budget allocated | 150000
| Municipal payment | 142500 |  | 84.112
| User contribution | 26916.8695 |  | 15.888
| Contingencies | 4500 |  | 3
| Maintanince | 3000 |  | 2

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:-सुकपानी स्याले सिंचाई कुलो मर्मत | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/10/13
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in ordinary rock by Manual Means ., Roadway Excavation in ordinary rock as per Drawing and Technical specification, including all lift and lead as per Drawing and instruction of the Engineer.
| -for base preparation | 1 | 6 | 1 | 1 | 6 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 6 | m3 | 866.66 | 5199.96
2 | Gabion Structure for Retaining Earth, Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 1.0 X 1 X 1 m ( 6 sqm)
| -for gabion wall | 7 | 3 | 1 | 1 | 21 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 2 | 1 | 1 | 2
| Sub-total |  |  |  |  | 23 | m3 | 6421.62 | 147697.26
| -13% VAT for stone | [7 empty] | 8122.5144
| -13% VAT for mesh wire | [7 empty] | 4831.1785
| -13% VAT for selvedge wire | [7 empty] | 635.7786
| -13% VAT for binding wire | [7 empty] | 255.346
3 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.
| -at back of gabion wall | 1 | 6 |  | 2 | 12
| Sub-total |  |  |  |  | 12 | m2 | 161.58 | 1938.96
| -13% VAT for stone | [7 empty] | 235.872
4 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 169416.8695
| Total Valuated | 169416.8695 |  | 100
| Budget allocated | 150000
| Municipal payment | 142500 |  | 84.112
| User contribution | 26916.8695 |  | 15.888
| Contingencies | 4500 |  | 3
| Maintanince | 3000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 169416.8695 |  |  |  |  | Total Valuated Amount : |  | 169416.8695
Work Started : | [7 empty] | Work Finished:
Project:-सुकपानी स्याले सिंचाई कुलो मर्मत | [7 empty] | F.Y:2082/2083
Location:- Shankharapur Municipality 1 | [7 empty] | Date:2082/10/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in ordinary rock by Manual Means ., Roadway Excavation in ordinary rock as per Drawing and Technical specification, including all lift and lead as per Drawing and instruction of the Engineer. | m3 | 6 | 866.66 | 5199.96 | 6 | 866.66 | 5199.96 | 0
2 | Gabion Structure for Retaining Earth, Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 1.0 X 1 X 1 m ( 6 sqm) | m3 | 23 | 6421.62 | 147697.26 | 23 | 6421.62 | 147697.26 | 0
| -13% VAT for stone |  |  |  | 8122.5144 |  |  | 8122.5144 | 0
| -13% VAT for mesh wire |  |  |  | 4831.1785 |  |  | 4831.1785 | 0
| -13% VAT for selvedge wire |  |  |  | 635.7786 |  |  | 635.7786 | 0
| -13% VAT for binding wire |  |  |  | 255.346 |  |  | 255.346 | 0
3 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications. | m2 | 12 | 161.58 | 1938.96 | 12 | 161.58 | 1938.96 | 0
| -13% VAT for stone |  |  |  | 235.872 |  |  | 235.872 | 0
4 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 169416.8695 |  |  | 169416.8695 | 0

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:-सुकपानी स्याले सिंचाई कुलो मर्मत | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/10/13
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in ordinary rock by Manual Means ., Roadway Excavation in ordinary rock as per Drawing and Technical specification, including all lift and lead as per Drawing and instruction of the Engineer.
| -for base preparation | 1 | 0.43178 | 0.99055 |  | 0.4277 |  |  |  |  | 7 | 2 | 160.098 |  | 14 | 0.60957 | 1.2191
|  | 3 | 0.43178 | 0.99055 |  | 1.2831
|  | 1 | 1.132 | 0.325 |  | 0.3679
|  | 1 | 0.43 | 0.98 |  | 0.4214 | [9 empty] | 27990
|  | 1 | 0.43 | 0.98 |  | 0.4214
|  | 1 | 0.43 | 0.98 |  | 0.4214 | [7 empty] | 159.51
|  | 1 | 0.44 | 0.965 |  | 0.4246 | [7 empty] | 14.819
|  | 1 | 0.43 | 0.3 |  | 0.129
|  | 10 | 0.40638 | 0.465 |  | 1.8897
|  | 3 | 1.12 | 0.32 |  | 1.0752
| Sub-total |  |  |  |  | 6.8614 | m3 | 866.66 | 5946.4707 |  |  |  |  | 73.8551
2 | Gabion Structure for Retaining Earth, Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 1.0 X 1 X 1 m ( 6 sqm)
| -for gabion wall | 7 | 3 | 1 | 1 | 21 |  |  |  |  | 7 | 2 | 160.098
|  | 1 | 2 | 1 | 1 | 2
| Sub-total |  |  |  |  | 23 | m3 | 6421.62 | 147697.26
| -13% VAT for stone | [7 empty] | 8122.5144
| -13% VAT for mesh wire | [7 empty] | 4831.1785
| -13% VAT for selvedge wire | [7 empty] | 635.7786
| -13% VAT for binding wire | [7 empty] | 255.346
3 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.
| -at back of gabion wall | 1 | 6 |  | 2 | 12
| Sub-total |  |  |  |  | 12 | m2 | 161.58 | 1938.96
| -13% VAT for stone | [7 empty] | 235.872
4 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 170163.3802
| Total Valuated | 170163.3802 |  | 100
| Budget allocated | 150000
| Municipal payment | 142500 |  | 83.743
| User contribution | 27663.3802 |  | 16.257
| Contingencies | 4500 |  | 3
| Maintanince | 3000 |  | 2