## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- dnl;d vfg]kfgL | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/09/07
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork in Excavation in ordinary soil (vGg] k'g{] sfo{)
| -for pipe laying | 1 | 175 | 0.3 | 0.45 | 23.625
|  | 1 | 150 | 0.3 | 0.45 | 20.25 | [5 empty] | 146.2969
|  | 1 | 400 | 0.3 | 0.45 | 54 | [5 empty] | 596 | 181.6519
| sub-total |  |  |  |  | 97.875 | cum | 963.05 | 94258.5187 |  |  | 1269 | 386.7723
2 | Laying and joining of 32 mmØ HDPE pipe with butt-weld joints
| -for pipe laying | 1 | 1900 |  |  | 1900
| sub-total |  |  |  |  | 1900 | rm | 6.12 | 11628
3 | -High Density Polythene Pipe NS 40 pipe material PE 100, PN 16 |  | Length (m) | Weight (Kg/m) | Total weight (Kg)
| -from source1 to tank 3, 32mm dia pipe | 1 | 400 | 0.338 | 135.2 | 135.2 |  |  |  |  | 97.006
| -from tank 2 to 2 houses, 32mm dia pipe | 1 | 300 | 0.338 | 101.4 | 101.4
| -from tank 3 to daando house, 32mm dia pipe | 1 | 1300 | 0.338 | 439.4 | 439.4
| Sub-total |  |  |  |  | 676 | kg | 287 | 194012 |  | 324.31
| -13% VAT for material | [7 empty] | 25221.56
4 | 32mm GI pipe threaded
| -for pipe laying | 1 | 6 |  |  | 6
| sub-total |  |  |  |  | 6 | rm | 452 | 2712
5 | Provisional sum for other unforseen works | 1 |  |  |  | 1 | PS | 7000 | 7000
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 335332.0787
| Total Estimated | 335332.0787 |  | 100
| Budget allocated | 300000
| Municipal payment | 285000 |  | 84.9904
| User contribution | 50332.0787 |  | 15.0096
| Contingencies | 9000 |  | 3
| Maintanince | 6000 |  | 2