## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- nfdf la;f}gf d]n8fF8f lj;/fd] ;8s | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date: 208306/26
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -for masonry wall | 0.5 | 15 | 0.9 | 0.6 | 4.05 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 4.05 | m3 | 73.88 | 299.214
2 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -for masonry wall | 1 | 15 | 0.9 | 0.15 | 2.025 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 2.025 | m3 | 4646.19 | 9408.5347
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -for masonry wall | 1 | 15 | 0.9 | 0.05 | 0.675 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 0.675 | m3 | 11500.47 | 7762.8173
4 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer
| -for masonry wall | 1 | 15 | 0.675 | 1.8 | 18.225 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 18.225 | m3 | 9526.75 | 173625.0188
5 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
@Æx@Æ sfnf] kmnfd] kfO{ksf] x\of08/]ndf @ ld6/sf] b"/Ldf @Æx@Æ sfnf] kmnfd] kfO{ks} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf b'O{ tx t];f]{ !=%Æx!=%Æ sfnf] kmnfd] kfO{ksf] d]Da/ /fvL /]lnË agfO{ h8fg u/L /+u ;d]t nufpg] sfd .
| -MS square pipe horizontal of 2" * 2" of 2mm thickness for vertical post of railing | 13 | 1 | 3.01 | 39.13 | 39.13
| -MS square pipe horizontal of 2" * 2" of 2mm thickness for vertical post of railing | 1 | 25 | 3.01 | 75.25 | 75.25
| -MS square pipe horizontal of 1.5" * 1.5" of 2mm thickness for vertical post of railing | 2 | 24.35 | 2.26 | 110.062 | 110.062
| sub-total |  |  |  |  | 224.442 | Kg | 188.28 | 42257.9398
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 233853.5245
| Total Estimated | 233853.5245 |  | 100
| Budget allocated | 250000
| Municipal payment | 237500 |  | 101.5593
| User contribution | -3646.4755 |  | -1.5593
| Contingencies | 7500 |  | 3
| Maintanince | 5000 |  | 2