## bhotange chihaanpaati
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- k~rkfn] led;]g dlGb/ cw'/f] | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
3 | d]lzgsf] k¦of]u u/L hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -!M@M$_
| -for lintel | 2 | 4.5718 | 0.35 | 0.1 | 0.32002
|  | 2 | 2.9717 | 0.35 | 0.1 | 0.20802
| Sub-total |  |  |  |  | 0.52804 | cum | 12884.61 | 6803.5924
| -13% VAT for cement | [7 empty] | 286.2451
| -13% VAT for aggregate | [7 empty] | 189.4238
| -13% VAT for sand | [7 empty] | 97.0753
| -13% VAT for water | [7 empty] | 2.4987
| -13% VAT for water | [7 empty] | 26.9721
| -13% VAT for water | [7 empty] | 0.97133
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -beam | 2 | 4.5718 | 0.23 | 0.23 | 0.48369
|  | 4 | 2.9717 | 0.23 | 0.23 | 0.6288
| -upper beam | 2 | 2.4901 | 0.23 | 0.23 | 0.26345
|  | 2 | 1.1429 | 0.23 | 0.23 | 0.12092
| -slab | 2 | 3.9374 | 1.9293 | 0.075 | 1.1394
|  | 2 | 3.0479 | 1.9293 | 0.075 | 0.88203
| -column | 4 | 0.23 | 0.23 | 0.68577 | 0.14511
| Sub-total |  |  |  |  | 3.6635 | cum | 13957.29 | 51131.9232
| -13% VAT for cement | [7 empty] | 2482.402
| -13% VAT for aggregate | [7 empty] | 1349.5096
| -13% VAT for sand | [7 empty] | 643.2223
| -13% VAT for water | [7 empty] | 26.67
| -13% VAT for diesel | [7 empty] | 187.1279
| -13% VAT for petrol | [7 empty] | 6.7389
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -beam | 2 | 4.5718 |  | 0.46 | 4.206
|  | 4 | 2.9717 |  | 0.46 | 5.4678
| -upper beam | 2 | 2.4901 |  | 0.46 | 2.2909
|  | 2 | 1.1429 |  | 0.46 | 1.0515
| -slab | 2 | 3.9374 | 1.9293 |  | 15.1926
|  | 2 | 3.0479 | 1.9293 |  | 11.7604
| -column | 4 | 0.92 |  | 0.68577 | 2.5236
| Sub-total |  |  |  |  | 42.4929 | sqm | 922.71 | 39208.6389
| -13% VAT for plyboard | [7 empty] | 1108.2419
| -13% VAT for wood | [7 empty] | 736.2631
| -13% VAT for iron props | [7 empty] | 560.009
| -13% VAT for nails | [7 empty] | 182.2946
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit Weight (Kg/m) | Total Weight (Kg)
| -beam | 12 | 4.9272 | 0.88889 | 52.5563 | 0.052556
| -stirrups | 64 | 0.81439 | 0.39506 | 20.5909 | 0.020591
| -beam | 12 | 3.787 | 0.88889 | 40.395 | 0.040395
| -stirrups | 88 | 0.81439 | 0.39506 | 28.3125 | 0.028312
| -upper beam | 12 | 2.8455 | 0.88889 | 30.3517 | 0.030352
| -stirrups | 30 | 0.81439 | 0.39506 | 9.652 | 0.009652
| -upper beam | 12 | 1.9583 | 0.88889 | 20.8888 | 0.020889
| -stirrups | 16 | 0.81439 | 0.39506 | 5.1477 | 0.0051477
| -slab | 12 | 13.9704 | 0.39506 | 66.2302 | 0.06623
|  | 50 | 1.9293 | 0.39506 | 38.1094 | 0.038109
|  | 38 | 1.9293 | 0.39506 | 28.9632 | 0.028963
| -column | 8 | 1.9424 | 0.88889 | 13.8124 | 0.013812
|  | 24 | 0.71117 | 0.39506 | 6.7429 | 0.0067429
|  | 24 | 0.50798 | 0.39506 | 4.8164 | 0.0048164
| Sub-total |  |  |  |  | 0.36657 | MT | 132360 | 48519.1245
| -13% VAT for TMT rod | [7 empty] | 5003.6722
| -13% VAT for binding wire | [7 empty] | 57.1848
7 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_
| #REF! | 1 | 3.8607 | 2.9717 |  | 11.4727
| Sub-total |  |  |  |  | 11.4727 | sqm | 689.98 | 7915.9388
| -13% VAT for cement | [7 empty] | 252.6564
| -13% VAT for sand | [7 empty] | 70.3995
| -13% VAT for aggregate | [7 empty] | 180.1077
8 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
| #REF! | 1 | 3.8607 | 2.9717 |  | 11.4727
| Sub-total |  |  |  |  | 11.4727 | sqm | 415.5 | 4766.91
| -13% VAT for cement | [7 empty] | 104.5608
| -13% VAT for sand | [7 empty] | 69.1993
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for wall continue | 2 | 2.9717 | 0.35 | 1.8805 | 3.9118
|  | 2 | 4.5718 | 0.35 | 1.8805 | 6.0181
| -deduction for door | -1 | 1.5 | 0.35 | 1.0667 | -0.56004
| -deduction for window | -2 | 1.0667 | 0.35 | 1.0667 | -0.79657
| Sub-total |  |  |  |  | 8.5733 | cum | 14491.84 | 124243.1239
| -13% VAT for brick | [7 empty] | 9452.561
| -13% VAT for cement | [7 empty] | 1016.6418
| -13% VAT for sanda | [7 empty] | 1062.5605
| -13% VAT for water | [7 empty] | 31.2069
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -for wall continue | 1 | 16.5133 |  | 3.0479 | 50.33
|  | 1 | 13.6605 |  | 3.0479 | 41.6351
| -deduction for door | -2 | 1.5 |  | 2.1335 | -6.4005
| -deduction for window | -4 | 1.0667 |  | 1.0667 | -4.5518
| Sub-total |  |  |  |  | 81.0127 | sqm | 415.5 | 33660.794
| -13% VAT for cement | [7 empty] | 738.3397
| -13% VAT for sand | [7 empty] | 488.6404
11 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as plaster | 1 |  |  |  | 81.0127
| Sub-total |  |  |  |  | 81.0127 | sqm | 253.8 | 20561.0337
| -13% VAT for aster | [7 empty] | 242.6494
| -13% VAT for weather coat | [7 empty] | 1098.6624
17 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
18 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 370065.7881
| Total Estimated | 370065.7881 |  | 100
| Budget allocated | 700000
| Municipal payment | 665000 |  | 179.6978
| User contribution | -294934.2119 |  | -79.6978
| Contingencies | 21000 |  | 3
| Maintanince | 14000 |  | 2

## chihaan
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- ef]tfª\u] lrxfgkfl6 | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter and backfilling, all lifts and lead as per Drawing and instruction of the Engineer.
| -for wall | 0.5 | 7.5 | 3 | 1.5 | 16.875
| Sub-total |  |  |  |  | 16.875 | m3 | 62.95 | 1062.2812
| -13% VAT for materials | [7 empty] | 113.4169
2 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -for wall | 1 | 7.6 | 1.25 | 0.15 | 1.425
| Sub-total |  |  |  |  | 1.425 | m3 | 4458.52 | 6353.391
| -13% VAT for materials | [7 empty] | 548.9921
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -for wall | 1 | 7.6 | 1.25 | 0.05 | 0.475
| Sub-total |  |  |  |  | 0.475 | m3 | 10964.46 | 5208.1185
| -13% VAT for cement | [7 empty] | 221.5509
| -13% VAT for sand | [7 empty] | 88.2309
| -13% VAT for aggregate | [7 empty] | 179.4028
| -13% VAT for formworks | [7 empty] | 26.0408
| -13% VAT for water | [7 empty] | 3.8285
4 | Providing and laying Plum concrete ( Boulder mixed concrete) including form work and 110mm dia PN6 HDPE pipe for Weep hole as per Drawing and Specifications, 60% M 15 concrete and 40% boulders/stones, using Mechanical Aids
| -for wall | 1 | 7.6 | 0.85 | 2.5 | 16.15
| Sub-total |  |  |  |  | 16.15 | m3 | 9860.43 | 159245.9445
| -13% VAT for cement | [7 empty] | 4650.9594
| -13% VAT for sand | [7 empty] | 1999.8997
| -13% VAT for boulder | [7 empty] | 2379.14
| -13% VAT for aggregate | [7 empty] | 3877.5833
| -13% VAT for formwork and 110mm PN6 HDPEpipe | [7 empty] | 748.2639
5 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for foundation | 4 | 1.5 | 1.5 | 1.5 | 13.5
| -for toe wall | 4 | 2.3877 | 0.23 | 0.5 | 1.0983
| Sub-total |  |  |  |  | 14.5983 | cum | 674.12 | 9841.0302
6 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for foundation | 4 | 1.5 | 1.5 |  | 9
| -for toe wall | 4 | 2.3877 | 0.23 |  | 2.1967
| -for flooring | 1 | 3.567 | 3.567 |  | 12.7234
| -for peti works | 2 | 4.267 | 0.45 |  | 3.8403
|  | 2 | 4.717 | 0.45 |  | 4.2453
| Sub-total |  |  |  |  | 32.0057 | sqm | 1017.47 | 32564.8266
| -13% VAT for brick | [7 empty] | 2646.6047
| -13% VAT for sand | [7 empty] | 938.7876
7 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd-lk=;L=;L= +!M#M^_
| -for foundation | 4 | 1.5 | 1.5 | 0.075 | 0.675
| -for toe wall | 4 | 2.3877 | 0.23 | 0.075 | 0.16475
| Sub-total |  |  |  |  | 0.83975 | cum | 11620.77 | 9758.546
| -13% VAT for cement | [7 empty] | 312.9637
| -13% VAT for aggregate | [7 empty] | 313.3862
| -13% VAT for sand | [7 empty] | 147.4417
| -13% VAT for water | [7 empty] | 3.0567
| -13% VAT for diesel | [7 empty] | 42.8941
| -13% VAT for petrol | [7 empty] | 1.5447
8 | d]lzgsf] k¦of]u u/L hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -!M@M$_
| -for flooring | 1 | 3.567 | 3.567 | 0.1 | 1.2723
| -for peti works | 2 | 4.267 | 0.45 | 0.075 | 0.28802
|  | 2 | 4.717 | 0.45 | 0.075 | 0.3184
| Sub-total |  |  |  |  | 1.8788 | cum | 12884.61 | 24207.1146
| -13% VAT for cement | [7 empty] | 1018.4573
| -13% VAT for aggregate | [7 empty] | 673.9679
| -13% VAT for sand | [7 empty] | 345.3931
| -13% VAT for water | [7 empty] | 8.8903
| -13% VAT for water | [7 empty] | 95.9664
| -13% VAT for water | [7 empty] | 3.456
9 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for foundation | 4 | 1.5 | 1.5 | 0.35 | 3.15
| -for neck column | 4 | 0.35 | 0.35 | 1.37 | 0.6713
| -for tie beam | 4 | 3.567 | 0.23 | 0.23 | 0.75478
| -GF column | 4 | 0.35 | 0.35 | 3.0722 | 1.5054
| -for beam | 4 | 3.567 | 0.23 | 0.23 | 0.75478
| -for support beam | 2 | 3.567 | 0.23 | 0.35 | 0.57429
| -for column over support beam | 4 | 0.23 | 0.23 | 1.8 | 0.38088
| -beam for inclined support | 4 | 1.9811 | 0.23 | 0.23 | 0.4192
| -for inclined slab | 4 | 3.0859 | 0.91436 | 0.1 | 1.1287
| -for cantilever | 2 | 4.267 | 0.6 | 0.1 | 0.51204
|  | 2 | 5.467 | 0.6 | 0.1 | 0.65604
| -beam for top roof inclined support | 4 | 1.9811 | 0.23 | 0.23 | 0.4192
| -top roof | 4 | 1.0149 | 1.2191 | 0.075 | 0.3712
| -for cantilever | 2 | 3.505 | 0.53337 | 0.1 | 0.3739
|  | 2 | 2.4383 | 0.53337 | 0.1 | 0.2601
| Sub-total |  |  |  |  | 11.9318 | cum | 13957.29 | 166535.0304
| -13% VAT for cement | [7 empty] | 8085.1036
| -13% VAT for aggregate | [7 empty] | 4395.3095
| -13% VAT for sand | [7 empty] | 2094.9545
| -13% VAT for water | [7 empty] | 86.8632
| -13% VAT for diesel | [7 empty] | 609.4695
| -13% VAT for petrol | [7 empty] | 21.9485
10 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for neck column | 4 | 0.35 |  | 1.37 | 1.918
| -for tie beam | 4 | 3.567 |  | 0.46 | 6.5633
| -GF column | 4 | 1.4 |  | 3.0722 | 17.2045
| -for beam | 4 | 3.567 |  | 0.46 | 6.5633
| -for support beam | 2 | 3.567 |  | 0.46 | 3.2816
| -for column over support beam | 4 | 0.23 |  | 1.8 | 1.656
| -beam for inclined support | 4 | 1.9811 |  | 0.46 | 3.6452
| -for inclined slab | 4 | 3.0859 | 0.91436 |  | 11.2866
| -for cantilever | 2 | 4.267 | 0.6 |  | 5.1204
|  | 2 | 5.467 | 0.6 |  | 6.5604
| -beam for top roof inclined support | 4 | 1.9811 |  | 0.46 | 3.6452
| -top roof | 4 | 1.0149 | 1.2191 |  | 4.9494
| -for cantilever | 2 | 3.505 | 0.53337 |  | 3.739
|  | 2 | 2.4383 | 0.53337 |  | 2.601
| Sub-total |  |  |  |  | 78.7339 | sqm | 922.71 | 72648.5899
| -13% VAT for plyboard | [7 empty] | 2053.4303
| -13% VAT for wood | [7 empty] | 1364.2013
| -13% VAT for iron props | [7 empty] | 1037.6251
| -13% VAT for nails | [7 empty] | 337.7686
11 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit Weight (Kg/m) | Total Weight (Kg)
| -for foundation | 10 | 1.5 | 0.88889 | 13.3333 | 0.013333
|  | 10 | 1.5 | 0.88889 | 13.3333 | 0.013333
| -for neck column to 1st floor | 16 | 5.8277 | 0.88889 | 82.8831 | 0.082883
|  | 16 | 5.8277 | 1.5802 | 147.3478 | 0.14735
| -for binding stirrups | 116 | 1.118 | 0.39506 | 51.2326 | 0.051233
|  | 116 | 0.952 | 0.39506 | 43.6275 | 0.043627
| -for tie beam | 24 | 4.6205 | 0.88889 | 98.5716 | 0.098572
| .-for stirrups | 96 | 0.81439 | 0.39506 | 30.8863 | 0.030886
| -for beam | 24 | 4.6205 | 0.88889 | 98.5716 | 0.098572
| .-for stirrups | 96 | 0.81439 | 0.39506 | 30.8863 | 0.030886
| -for support beam | 12 | 4.7242 | 0.88889 | 50.3911 | 0.050391
| .-for stirrups | 48 | 0.81439 | 0.39506 | 15.4432 | 0.015443
| -for column over support beam | 32 | 2.4 | 0.88889 | 68.2667 | 0.068267
| -for binding stirrups | 36 | 0.60957 | 0.39506 | 8.6694 | 0.0086694
|  | 36 | 0.40597 | 0.39506 | 5.7738 | 0.0057738
| -beam for inclined support | 40 | 2.7431 | 0.88889 | 97.5312 | 0.097531
| .-for stirrups | 52 | 0.81439 | 0.39506 | 16.7301 | 0.01673
| -for inclined slab | 24 | 3.0859 | 0.61728 | 45.7178 | 0.045718
|  | 80 | 0.91436 | 0.61728 | 45.1534 | 0.045153
| -for cantilever | 8 | 5.3846 | 0.61728 | 26.5908 | 0.026591
|  | 66 | 0.6 | 0.61728 | 24.4444 | 0.024444
|  | 8 | 4.1664 | 0.61728 | 20.5749 | 0.020575
|  | 50 | 0.6 | 0.61728 | 18.5185 | 0.018519
| -top roof | 32 | 1.0149 | 0.61728 | 20.0481 | 0.020048
|  | 28 | 1.2191 | 0.61728 | 21.0716 | 0.021072
| -for cantilever | 6 | 3.4035 | 0.61728 | 12.6057 | 0.012606
|  | 38 | 0.53337 | 0.61728 | 12.5112 | 0.012511
|  | 6 | 2.3377 | 0.61728 | 8.6582 | 0.0086582
|  | 24 | 0.53337 | 0.61728 | 7.9018 | 0.0079018
| Sub-total |  |  |  |  | 1.1373 | MT | 132360 | 150529.7692
| -13% VAT for TMT rod | [7 empty] | 15523.8089
| -13% VAT for binding wire | [7 empty] | 177.415
12 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -at column | 4 | 1.4 |  | 2.7222 | 15.2445
| -for column over support beam | 4 | 0.92 |  | 0.91436 | 3.3648
| -for beam | 4 | 3.5538 |  | 0.69 | 9.8085
|  | 2 | 3.5538 |  | 0.69 | 4.9042
| -beam for top roof inclined support | 4 | 1.9811 |  | 0.69 | 5.4678
| -for inclined slab | 4 | 3.0859 | 0.91436 |  | 11.2866
| -for cantilever | 2 | 4.267 | 0.6 |  | 5.1204
|  | 2 | 5.467 | 0.6 |  | 6.5604
| -top roof | 4 | 1.0149 | 1.2191 |  | 4.9494
| -for cantilever | 2 | 3.505 | 0.53337 |  | 3.739
|  | 2 | 2.4383 | 0.53337 |  | 2.601
| Sub-total |  |  |  |  | 73.0467 | sqm | 415.5 | 30350.9022
| -13% VAT for cement | [7 empty] | 665.7382
| -13% VAT for sand | [7 empty] | 440.592
13 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for tie beam | 4 | 1.1685 | 0.23 | 1.2 | 1.2901
|  | 4 | 2.3874 | 0.23 | 0.47 | 1.0323
| -for peti works | 2 | 4.717 | 0.1 | 0.3 | 0.28302
|  | 2 | 4.717 | 0.1 | 0.3 | 0.28302
| Sub-total |  |  |  |  | 2.8884 | cum | 14491.84 | 41858.4904
| -13% VAT for brick | [7 empty] | 3184.6425
| -13% VAT for cement | [7 empty] | 342.5147
| -13% VAT for sanda | [7 empty] | 357.985
| -13% VAT for water | [7 empty] | 10.5138
14 | Knfi6/ dfly @) dL=dL= afSnf] emNn/ jf kfgL k§L agfpg] sfd
| -for cantilever | 2 | 5.467 |  |  | 10.934
|  | 2 | 5.467 |  |  | 10.934
| -for cantilever | 2 | 3.505 |  |  | 7.0101
|  | 2 | 3.505 |  |  | 7.0101
| Sub-total |  |  |  |  | 35.8881 | rm | 144.41 | 5182.5981
| -13% VAT for cement | [7 empty] | 425.5358
| -13% VAT for sand | [7 empty] | 59.2979
| -13% VAT for water-proofing | [7 empty] | 0.093309
15 | Provisional sum for lab tests | 1 |  |  |  | 1 | PS | 5000 | 5000
16 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 783511.5633
| Total Estimated | 783511.5633 |  | 100
| Budget allocated | 700000
| Municipal payment | 665000 |  | 84.8743
| User contribution | 118511.5633 |  | 15.1257
| Contingencies | 21000 |  | 3
| Maintanince | 14000 |  | 2
Note on D39: Author: between footing size only

## Sheet1
Foundation size |  |  | Footing size |  |  | Plinth size |  |  | Toe wall |  |  |  | Column size |  |  | Tie beam size |  |  | Tie beam size
Length | Breadth | Depth from GL | Length in PL area | Breadth in PL area | Depth | Length | Breadth | Depth from GL | Length L1 | Ht. H1 | Length L2 | Ht. H2 | Length/B | Ht. upto plinth | Ht. above PL upto ceiling | Length | Width | Height | Length | Width | Height
1.5 | 1.5 | 1.5 | 0.93965 | 0.93965 | 0.35 | 4.267 | 4.267 | 0.45 | 2.3877 | 0.82 | 0.58305 | 1.6 | 0.35 | 1.37 | 3.0722 | 3.567 | 0.23 | 0.23 | -4.7463 | 0.23 | 0.35