## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:-x}j'ª 8fF8f3/]6f]n klx/f] ;+/If0f | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/10/21
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer.
| -for base preparation | 15 | 1 | 1 | 1 | 15 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 15 | m3 | 748.9 | 11233.5
2 | Gabion Structure for Retaining Earth, Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 1.0 X 1 X 1 m ( 6 sqm)
| -for gabion wall | 15 | 3 | 1 | 1 | 45 |  |  |  |  | 7 | 2 | 160.098
|  | 15 | 2.5 | 1 | 1 | 37.5
| Sub-total |  |  |  |  | 82.5 | m3 | 6421.62 | 529783.65
| -13% VAT for stone | [7 empty] | 29135.106
| -13% VAT for mesh wire | [7 empty] | 17329.2271
| -13% VAT for selvedge wire | [7 empty] | 2280.5104
| -13% VAT for binding wire | [7 empty] | 915.915
3 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.
| -at back of gabion wall | 15 | 1 |  | 2 | 30
| Sub-total |  |  |  |  | 30 | m2 | 161.58 | 4847.4
| -13% VAT for geotextile | [7 empty] | 589.68
4 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 596614.9885
| Total Estimated | 596614.9885 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 79.6158
| User contribution | 121614.9885 |  | 20.3842
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2

## estimate (2)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:-x}j'ª 8fF8f3/]6f]n klx/f] ;+/If0f | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:2082/10/21
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer.
| -for base preparation | 1 | 13 | 3 | 1 | 39 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 39 | m3 | 748.9 | 29207.1
2 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -for base preparation | 1 | 13 | 3 | 0.15 | 5.85 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 5.85 | m3 | 4458.52 | 26082.342
| -13% VAT for materials | [7 empty] | 2253.757
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -for base preparation | 1 | 13 | 3 | 0.05 | 1.95 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 1.95 | m3 | 10964.46 | 21380.697
| -13% VAT for cement | [7 empty] | 909.5247
| -13% VAT for sand | [7 empty] | 362.2109
| -13% VAT for aggregate | [7 empty] | 736.4956
| -13% VAT for formworks | [7 empty] | 106.9043
| -13% VAT for water | [7 empty] | 15.717
4 | Gabion Structure for Retaining Earth, Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 1.0 X 1 X 1 m ( 6 sqm)
| -for gabion wall | 13 | 3 | 1 | 1 | 39 |  |  |  |  | 7 | 2 | 160.098
|  | 13 | 2.5 | 1 | 1 | 32.5
| Sub-total |  |  |  |  | 71.5 | m3 | 6421.62 | 459145.83
| -13% VAT for stone | [7 empty] | 25250.4252
| -13% VAT for mesh wire | [7 empty] | 15018.6635
| -13% VAT for selvedge wire | [7 empty] | 1976.4423
| -13% VAT for binding wire | [7 empty] | 793.793
5 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.
| -at back of gabion wall | 13 | 1 |  | 2 | 26
| Sub-total |  |  |  |  | 26 | m2 | 161.58 | 4201.08
| -13% VAT for geotextile | [7 empty] | 511.056
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 588452.0385
| Total Estimated | 588452.0385 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 80.7203
| User contribution | 113452.0385 |  | 19.2797
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2