## WCR (hidden)
Government of Nepal
Shankharapur Municipality Office
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  | Total Valuated Amount : |  | #REF!
Project: | #REF! | [7 empty] | Fiscal Year:079/80
Location:Shankharapur-1 | [8 empty] | Date:2079/12/21
S.No. | Description | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  | Quantity | Rate | Amount (Rs) | Quantity | Rate | Amount(Rs)
1 | Earthwork in excavaiton | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Dismantle the rcc work on the base of water tank | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | stone soling | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| vat on stone |  |  | #REF! |  |  | #REF!
4 | Dry Stone Masonry work | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| vat on stone |  |  | #REF! |  |  | #REF!
5 | Brick Masonry work in 1:6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| vat on cement |  |  | #REF! |  |  | #REF!
| vat on brick |  |  | #REF! |  |  | #REF!
| vat on sand |  |  | #REF! |  |  | #REF!
6 | RCC works 1:1.5:3 ratio in water collection chamber with all work complete | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| vat on cement |  |  | #REF! |  |  | #REF!
| vat on aggregate |  |  | #REF! |  |  | #REF!
| vat on sand |  |  | #REF! |  |  | #REF!
7 | 3mm punning all complete work | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| vat on cement |  |  | #REF! |  |  | #REF!
8 | plastering work | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| vat on cement |  |  | #REF! |  |  | #REF!
| vat on sand |  |  | #REF! |  |  | #REF!
9 | tap and fittings | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | Iron frame for barbed wire | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Vat on iron frame |  |  | #REF! |  |  | #REF!
11 | Barbed wire | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| vat on barbed wire |  |  | #REF! |  |  | #REF!
12 | Roof top PVC Water Tank | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| vat on pvc water tank |  |  | #REF! |  |  | #REF!
12 | Information Board | 1 | 500 | 500 | #REF! | #REF! | #REF! | #REF!
| Total |  |  | #REF! |  |  | #REF!

## Sheet1 (hidden)
152 | ;'Vvf O{6f RofK6f] 5fKg] sfd .
H 15 | b/ ljZn]if0fsf] nflu !) j=dL= lnOPsf]
| ;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
| >lds | s_ l;kfn' | 0.5 | hjfg | 1330 | 665
|  | v_ HofdL | 1 | hjfg | 1000 | 1000 | 1665
| lgdf{0f ;fdu¦L | O{6f | 0 | uf]6f | 15.145 | 0
|  | jfn'jf vf]nfsf] | 0 | 3=dL= | 3389.76 | 0 | 0
[5 empty] | jf:tljs b//]6 |  | 1665
| b/ k¦lt j=dL=sf] |  |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 249.75
| 1914.75 | Ö ?= | 191.47 | k}= | hDdf b/ /]6 |  | 1914.75
10
=

## include dhara marmat (hidden)
Government of Nepal
Shankharapur Municipality
Shankhu, Kathmandu
Detail Estimate Sheet
Project:-gfªn]ef/] :jf:yo rf}sL kfgL 6\ofÍL dd{t tyf j8f sfof{no sDkfp08 /+u/f]ug | [8 empty] | F.Y.:-2082/083
Location:- Shankharapur Municipality- 1 | [6 empty] | Date: 2082/04/01
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
A. | kfgL 6\ofÍL dd{t
1 | Kn]g l;d]G6 sqmL6 jf jh¦ s+qmL6 eTsfO{ !) dL= k/ x6fpg] sfd
| -water tank | 1 | 5 | 3.3526 | 0.075 | 1.2572
[6 empty] | 1.2572 | cum | 3740 | 4702.0725
2 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL
| -water tank | 2 | 5 | 0.23 | 1.4 | 14
|  | 2 | 2.8926 | 0.23 | 1.4 | 8.0994
|  | 1 | 5 | 0.23 | 0.45 | 2.25
[6 empty] | 24.3494 | cum | 1982.2 | 48265.3448
3 | ;fx¦f] k¦sf/sf] Sn], g/d d'/d 9'+uf -#) ;]=dL=;Dd_ ld;]sf] df6f]df ;j} lsl;dsf] vGg] sfd
|  | 1 | 5 | 3.3526 | 0.075 | 1.2572
[6 empty] | 1.2572 | cum | 770.43 | 968.6144
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for flooring | 1 | 5 | 3.3526 |  | 16.7632
[6 empty] | 16.7632 | sqm | 166.5 | 2791.0698
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for flooring | 1 | 5 | 3.3526 | 0.075 | 1.2572
[6 empty] | 1.2572 | cum | 13351.1 | 16785.5189
| vat on cement | [7 empty] | 681.536
| vat on sand | [7 empty] | 231.1318
| vat on aggregate | [7 empty] | 447.8333
6 | cf/=;L=;L= nflu !) ld=ld= kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd
| -Along long length | 33 | 9.7543 |  | 0.61728 | 198.6996
|  | 32 | 9.3468 |  | 0.61728 | 184.629
| -Along short length | 23 | 8.1024 |  | 0.61728 | 115.0342
|  | 22 | 7.6958 |  | 0.61728 | 104.5112
| -binder | 12 | 16.4096 |  | 0.39506 | 77.7938
|  | 11 | 15.7982 |  | 0.39506 | 68.654
| -Slab | 42 | 4.9284 |  | 0.39506 | 81.7745
|  | 64 | 3.2764 |  | 0.39506 | 82.8413
| -deduction for opening | -10 | 0.6 |  | 0.39506 | -2.3704
|  | -10 | 0.6 |  | 0.39506 | -2.3704
| -for fillet | 90 | 1.0424 |  | 0.39506 | 37.0619
[6 empty] | 946.2589 | kg | 132.36 | 125246.8243
| vat on material | [7 empty] | 13064.05
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -For shear wall | 1 | 16.7144 |  | 1.3968 | 23.3472
|  | 1 | 15.4953 |  | 1.271 | 19.6938
| -for slab | 1 | 4.6998 | 3.0479 |  | 14.3243
| -deduction for opening | -1 | 0.6 | 0.6 |  | -0.36
[6 empty] | 57.0052 | sqm | 922.71 | 52599.3006
| vat on material | [7 empty] | 3470.2639
8 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -floor and slab | 2 | 5 | 3.3526 | 0.12801 | 4.2917
| -shear wall | 2 | 5 | 0.15 | 1.6001 | 2.4002
|  | 2 | 3.0479 | 0.15 | 1.6001 | 1.4631
| -fillet | 0.5 | 13.057 | 0.30479 | 0.30479 | 0.60646
| -deduction for opening | -1 | 0.6 | 0.6 | 0.12801 | -0.046084
[6 empty] | 8.7153 | cum | 13957.29 | 121642.5149
| vat on cement | [7 empty] | 5905.6183
| vat on sand | [7 empty] | 1530.2218
| vat on aggregate | [7 empty] | 3210.4747
| vat on diesel | [7 empty] | 445.176
| vat on petrol | [7 empty] | 16.0319
9 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -At shear wall | 2 | 4.6998 |  | 1.6001 | 15.0405
|  | 2 | 3.0479 |  | 1.6001 | 9.7539
[6 empty] | 24.7943 | sqm | 415.5 | 10302.0443
| vat on cement | [7 empty] | 225.9723
| vat on sand | [7 empty] | 149.5507
10 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_
| -at water tank | 1 | 4.0902 | 2.4383 |  | 9.9731 | sqm | 689.98 | 6881.2375
| vat on cement | [7 empty] | 219.6314
| vat on sand | [7 empty] | 74.1625
| vat on aggregate | [7 empty] | 156.5657
11 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
| -At shear wall | 2 | 4.6998 |  | 2.2001 | 20.6802
|  | 2 | 3.0479 |  | 2.2001 | 13.4113
| -at floor | 1 | 4.0902 | 2.4383 |  | 9.9731
[6 empty] | 44.0646 | sqm | 287.32 | 12660.6388
| vat on cement | [7 empty] | 397.1154
12 | square frame medium duty 24"X24 | 1 |  |  |  | 1 | no. | 4659 | 4659
| vat for material | [7 empty] | 605.67
13 | -!M@ efudf jf6/ k¦'km sDkfp08 ld;fO{ 8]Dk k¦'lkm+Ë ug
| -at water tank | 1 | 15.4953 |  | 1.6001 | 24.7943
|  | 1 | 4.0902 | 2.4383 |  | 9.9731
[6 empty] | 34.7674 | sqm | 452.86 | 15744.7772
| vat on cement | [7 empty] | 795.1081
| vat on sand | [7 empty] | 258.5396
| vat on water-proofing compound | [7 empty] | 233.0843
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -ward compound | 2 | 3.415 |  | 1.43 | 9.7669
|  | 2 | 0.96 |  | 2.2 | 4.224
|  | 2 | 4 |  | 1.39 | 11.12
|  | 2 | 0.96 |  | 2.2 | 4.224
|  | 2 | 3.91 |  | 1.3 | 10.166
|  | 2 | 0.96 |  | 2.31 | 4.4352
|  | 2 | 3.96 |  | 1.37 | 10.8504
|  | 2 | 0.96 |  | 2.29 | 4.3968
|  | 2 | 3.875 |  | 1.265 | 9.8037
|  | 2 | 0.96 |  | 2.19 | 4.2048
|  | 2 | 3.69 |  | 1.28 | 9.4464
|  | 2 | 0.96 |  | 2.19 | 4.2048
|  | 2 | 4.17 |  | 1.12 | 9.3408
|  | 2 | 0.68 |  | 2.26 | 3.0736
|  | 2 | 0.68 |  | 2.15 | 2.924
|  | 2 | 2.5 |  | 1.16 | 5.8
|  | 2 | 0.96 |  | 2.18 | 4.1856
|  | 2 | 3.94 |  | 1.2 | 9.456
|  | 2 | 0.96 |  | 2.15 | 4.128
|  | 2 | 4 |  | 1.15 | 9.2
|  | 2 | 0.96 |  | 2.08 | 3.9936
|  | 2 | 3.97 |  | 1.25 | 9.925
|  | 2 | 0.96 |  | 2.25 | 4.32
|  | 2 | 4 |  | 1.23 | 9.84
|  | 2 | 0.96 |  | 2.25 | 4.32
|  | 2 | 4.06 |  | 1.32 | 10.7184
|  | 2 | 0.96 |  | 2.18 | 4.1856
|  | 2 | 3.92 |  | 1.32 | 10.3488
|  | 2 | 0.96 |  | 2.28 | 4.3776
|  | 2 | 3.62 |  | 1.32 | 9.5568
|  | 2 | 0.96 |  | 2.2 | 4.224
|  | -32 | 0.23 |  | 1.35 | -9.936
[6 empty] | 200.8248 | sqm | 253.8 | 50969.3469
| vat on aster | [7 empty] | 601.5106
| vat on weather coat | [7 empty] | 2723.5063
15 | 20mm GI Pipe threaded -Medium class
| - for kitchen | 1 | 0.9 |  |  | 0.9
| -for outside dhara | 1 | 1.5 |  |  | 1.5
| -for water tank inlet and overflow | 2 | 0.9 |  |  | 1.8
[6 empty] | 4.2 | rm | 248 | 1041.6
| -13% VAT on materials | [7 empty] | 135.408
16 | PPR pipe (PN-16) 20mm OD 2.80mm thick 0.148kg/m
| -for kitchen | 1 | 9 |  |  | 9
[6 empty] | 9 | rm | 75 | 675
| -13% VAT on materials | [7 empty] | 87.75
17 | Porcelain clay white glaze wash basin large size regular complete set
| -for kitchen | 1 |  |  |  | 1
[6 empty] | 1 | set | 1070 | 1070
| -13% VAT on materials | [7 empty] | 139.1
18 | Brass tap-1'2" ordinary
| -for kitchen and outside dhara | 2 |  |  |  | 2
[6 empty] | 2 | set | 750 | 1500
| -13% VAT on materials | [7 empty] | 195
19 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 15000 | 15000
20 | Information Board and photographs | 1 |  |  |  | 1 | no. | 500 | 500
530004.9174
| Description | Amount |  | Percent
| Total Estimated | 530004.9174
| Budget Allocated | 480000 |  | 100
| Municipal Payment | 456000 |  | 86.0369
| User Contribution | 74004.9174 |  | 15.4177
| Maintenance 2% | 9600 |  | 2
| Contingencies 3% | 14400 |  | 3
Note on E11: DELL: need to verify
Note on F11: DELL: need to verify

## Size of water tank (hidden)
Length | Breadth | Height | Slab thickness | Cover for slab | Shear wall thickness | Cover for shear wall | Soiling thickness | PCC | Vertical rebar | Opening |  | Fillet
[10 empty] | Length | Breadth | Length | Height
4.4194 | 4.267 | 1.6763 | 0.125 | 0.025 | 0.20319 | 0.038098 | 0.05 | 0.075 | 8 | 0.60957 | 0.60957 | 0.30479 | 0.30479
[9 empty] | 0.456 |  |  | 0.43103
Note on J4: User: 57*dia
Note on M4: User: hypoteneous

## water tank estimate
Government of Nepal
Shankharapur Municipality
Shankhu, Kathmandu
Detail Estimate Sheet
Project:-gfªn]ef/] :jf:yo rf}sL kfgL 6\ofÍL dd{t tyf j8f sfof{no sDkfp08 /+u/f]ug | [8 empty] | F.Y.:-2082/083
Location:- Shankharapur Municipality- 1 | [6 empty] | Date: 2082/04/01
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
A. | kfgL 6\ofÍL dd{t
1 | Kn]g l;d]G6 sqmL6 jf jh¦ s+qmL6 eTsfO{ !) dL= k/ x6fpg] sfd
| -water tank | 1 | 5 | 3.3526 | 0.075 | 1.2572
[6 empty] | 1.2572 | cum | 3740 | 4702.0725
2 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL
| -water tank | 2 | 5 | 0.23 | 1.4 | 3.22
|  | 2 | 2.8926 | 0.23 | 1.4 | 1.8629
|  | 1 | 5 | 0.23 | 0.45 | 0.5175
[6 empty] | 5.6004 | cum | 1982.2 | 11101.0293
3 | 3fF; sf6\g] To;sf] h/f lemSg], l9:sf] k'm6fpg] / n]en ldnfpg] sfo{
| -for levelling | 1 | 13.9948 | 7.6196 |  | 106.6353
|  | 1 | 2.2859 | 9.1568 |  | 20.9315
|  | 1 | 2.6669 | 8.788 |  | 23.4365
|  | 1 | 3.9622 | 8.3054 |  | 32.9077
[6 empty] | 183.911 | sqm | 23 | 4229.9522
4 | ;fx¦f] k¦sf/sf] Sn], g/d d'/d 9'+uf -#) ;]=dL=;Dd_ ld;]sf] df6f]df ;j} lsl;dsf] vGg] sfd
|  | 1 | 4.5694 | 4.417 | 0.125 | 2.5229
[6 empty] | 2.5229 | cum | 770.43 | 1943.6921
5 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for flooring | 1 | 4.5694 | 4.417 |  | 20.1829
[6 empty] | 20.1829 | sqm | 166.5 | 3360.4583
6 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for flooring | 1 | 4.5694 | 4.417 | 0.075 | 1.5137
[6 empty] | 1.5137 | cum | 13351.1 | 20209.8268
| vat on cement | [7 empty] | 820.5719
| vat on sand | [7 empty] | 278.2835
| vat on aggregate | [7 empty] | 539.193
7 | cf/=;L=;L= nflu !) ld=ld= kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd
| -Along long length | 29 | 8.7554 |  | 0.61728 | 156.733
|  | 28 | 8.5014 |  | 0.61728 | 146.9385
| -Along short length | 28 | 8.9078 |  | 0.61728 | 153.9624
|  | 27 | 8.6538 |  | 0.61728 | 144.2306
| -binder | 12 | 17.068 |  | 0.39506 | 80.9148
|  | 12 | 16.052 |  | 0.39506 | 76.0984
| -Slab | 56 | 4.4194 |  | 0.39506 | 97.7721
|  | 58 | 4.267 |  | 0.39506 | 97.7721
| -deduction for opening | -10 | 0.60957 |  | 0.39506 | -2.4082
|  | -10 | 0.60957 |  | 0.39506 | -2.4082
| -for fillet | 50 | 1.343 |  | 0.39506 | 26.529
|  | 48 | 1.343 |  | 0.39506 | 25.4679
| -binder | 1 | 14.5281 |  | 0.39506 | 5.7395
| -for kitchen setup at ward office | 5 | 1.5 |  | 0.88889 | 6.6667
|  | 11 | 0.71015 |  | 0.88889 | 6.9437
[6 empty] | 1020.9523 | kg | 132.36 | 135133.2486
| vat on material | [7 empty] | 14095.2677
8 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -For shear wall | 1 | 17.3728 |  | 1.8013 | 31.2939
|  | 1 | 15.7472 |  | 1.4965 | 23.5663
| -for slab | 1 | 4.013 | 3.8606 |  | 15.4927
| -deduction for opening | -1 | 0.60957 | 0.60957 |  | -0.37158
| -for kitchen setup at ward office | 1 | 1.5 | 0.71015 |  | 1.0652
[6 empty] | 71.0464 | sqm | 922.71 | 65555.2293
| vat on material | [7 empty] | 4325.0374
9 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -floor and slab | 2 | 4.4194 | 4.267 | 0.125 | 4.7144
| -shear wall | 2 | 4.4194 | 0.20319 | 1.6763 | 3.0106
|  | 2 | 3.8606 | 0.20319 | 1.6763 | 2.6299
| -fillet | 1 | 3.7082 | 0.30479 | 0.30479 | 0.34447
|  | 1 | 3.5558 | 0.30479 | 0.30479 | 0.33031
| -deduction for opening | -1 | 0.6 | 0.6 | 0.12801 | -0.046084
| -for kitchen setup at ward office | 1 | 1.5 | 0.71015 | 0.125 | 0.13315
[6 empty] | 11.1167 | cum | 13957.29 | 155159.6196
| vat on cement | [7 empty] | 7532.8391
| vat on sand | [7 empty] | 1951.8557
| vat on aggregate | [7 empty] | 4095.0816
| vat on diesel | [7 empty] | 567.8388
| vat on petrol | [7 empty] | 20.4493
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -At shear wall | 2 | 4.013 |  | 1.3715 | 11.0079
|  | 2 | 3.8606 |  | 1.3715 | 10.5899
| -at fillet | 1 | 14.5281 |  | 0.43103 | 6.2621
| -for kitchen | 3 | 0.71015 |  | 0.8 | 1.7044
[6 empty] | 29.5643 | sqm | 415.5 | 12283.9536
| vat on cement | [7 empty] | 269.4449
| vat on sand | [7 empty] | 178.3213
11 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_
| -at water tank | 1 | 3.4034 | 3.251 |  | 11.0647
| -at roof of ward office | 1 | 4.1399 | 5.1052 |  | 21.1348
| -at cantilever | 1 | 23.189 | 0.45 |  | 10.435
|  | 1 | 6.4005 | 0.9 |  | 5.7604
|  | 1 | 15.2393 | 0.6 |  | 9.1436
|  | 1 | 10.3374 | 0.6 |  | 6.2024
[6 empty] | 63.741 | sqm | 689.98 | 43979.9917
| vat on cement | [7 empty] | 1403.7284
| vat on sand | [7 empty] | 473.9944
| vat on aggregate | [7 empty] | 1000.6567
12 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
| -At shear wall | 2 | 4.013 |  | 1.3715 | 11.0079
|  | 2 | 3.8606 |  | 1.3715 | 10.5899
| -for fillet | 1 | 14.5281 |  | 0.43103 | 6.2621
| -at floor | 1 | 3.4034 | 3.251 |  | 11.0647
| -at roof of ward office | 1 | 4.1399 | 5.1052 |  | 21.1348
| -at cantilever | 1 | 23.189 | 0.45 |  | 10.435
|  | 1 | 6.4005 | 0.9 |  | 5.7604
|  | 1 | 15.2393 | 0.6 |  | 9.1436
|  | 1 | 10.3374 | 0.6 |  | 6.2024
[6 empty] | 91.6009 | sqm | 287.32 | 26318.7637
| vat on cement | [7 empty] | 825.5181
13 | square frame medium duty 24"X24 | 1 |  |  |  | 1 | no. | 4659 | 4659
| vat for material | [7 empty] | 605.67
14 | -!M@ efudf jf6/ k¦'km sDkfp08 ld;fO{ 8]Dk k¦'lkm+Ë ug
| -as of item no. 11 | 1 | 91.6009 |  |  | 91.6009
[6 empty] | 91.6009 | sqm | 452.86 | 41482.3728
| vat on cement | [7 empty] | 2094.8516
| vat on sand | [7 empty] | 681.1679
| vat on water-proofing compound | [7 empty] | 614.1014
15 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M$_ df
| -for kitchen | 3 | 0.71015 | 0.1 | 0.8 | 0.17044
[6 empty] | 0.17044 | cum | 15170.83 | 2585.6532
| vat on brick | [7 empty] | 187.9151
| vat on cement | [7 empty] | 28.8723
| vat on sand | [7 empty] | 21.0296
| vat on water | [7 empty] | 0.8065
16 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -for kitchen | 1 | 3.23 | 4.0628 |  | 13.1228
| -deduction for kitchen part | -1 | 1.5239 | 0.71015 |  | -1.0822
| -at wall | 1 | 1.5239 | 0.76196 |  | 1.1612
[6 empty] | 13.2018 | sqm | 2988.15 | 39448.8326
| vat on porcelain glazed tile | [7 empty] | 1150.9318
| vat on cement | [7 empty] | 125.2383
| vat on sand | [7 empty] | 88.427
| vat on white cement | [7 empty] | 17.1726
17 | !^ dL=dL=u¦]gfO{6, l;d]G6 d;nfdf 5fkL 3f]6\g] / kflnz ;d]t ug{
| -for kitchen | 1 | 1.5239 | 0.71015 |  | 1.0822
[6 empty] | 1.0822 | sqm | 7012.25 | 7588.7607
| vat on 16mm granite | [7 empty] | 609.4567
| vat on cement | [7 empty] | 23.833
| vat on sand | [7 empty] | 8.7272
| vat on cShflns Pl;8 | [7 empty] | 0.65068
| vat on d}g kflnz | [7 empty] | 0.60918
| vat on tf/k]G6fOg | [7 empty] | 1.6726
| vat on sfaf]{/08d 9'+uf | [7 empty] | 1.6883
18 | dfn;fdfg pknAw u/L %) dL=dL= df]6f] x]eL 8o"6L OG6/nls+u s+lqm6Ans %) dL=dL=df]6fOsf] qm;/ 8:6 dfyL /fvL la5ofpg]] sfd k'/f .
| -for ward compound area | 1 | 13.9948 | 7.6196 |  | 106.6353
|  | 1 | 2.2859 | 9.1568 |  | 20.9315
|  | 1 | 2.6669 | 8.788 |  | 23.4365
|  | 1 | 3.9622 | 8.3054 |  | 32.9077
| -deduction | -25 | 0.76196 | 0.063497 |  | -3.7999
[6 empty] | 180.111 | sqm | 1832.98 | 330139.917
| vat on interlock block | [7 empty] | 8367.9589
| vat on 9'+ufsf] 3"nf] -Pl/ofX% ;]=dL=_ | [7 empty] | 84.1281
| vat on 9'+ufsf] 3"nf] | [7 empty] | 2171.8995
19 | ;'Vvf O{6f 7f8f] 5fKg] sfd
| -for rounding around plants | 50 | 0.76196 | 0.063497 |  | 7.5999
[6 empty] | 7.5999 | sqm | 1834.54 | 13942.2663
| vat on materials | [7 empty] | 1360.0052
20 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -ward compound | 2 | 3.415 |  | 1.43 | 9.7669
|  | 2 | 0.96 |  | 2.2 | 4.224
|  | 2 | 4 |  | 1.39 | 11.12
|  | 2 | 0.96 |  | 2.2 | 4.224
|  | 2 | 3.91 |  | 1.3 | 10.166
|  | 2 | 0.96 |  | 2.31 | 4.4352
|  | 2 | 3.96 |  | 1.37 | 10.8504
|  | 2 | 0.96 |  | 2.29 | 4.3968
|  | 2 | 3.875 |  | 1.265 | 9.8037
|  | 2 | 0.96 |  | 2.19 | 4.2048
|  | 2 | 3.69 |  | 1.28 | 9.4464
|  | 2 | 0.96 |  | 2.19 | 4.2048
|  | 2 | 4.17 |  | 1.12 | 9.3408
|  | 2 | 0.68 |  | 2.26 | 3.0736
|  | 2 | 0.68 |  | 2.15 | 2.924
|  | 2 | 2.5 |  | 1.16 | 5.8
|  | 2 | 0.96 |  | 2.18 | 4.1856
|  | 2 | 3.94 |  | 1.2 | 9.456
|  | 2 | 0.96 |  | 2.15 | 4.128
|  | 2 | 4 |  | 1.15 | 9.2
|  | 2 | 0.96 |  | 2.08 | 3.9936
|  | 2 | 3.97 |  | 1.25 | 9.925
|  | 2 | 0.96 |  | 2.25 | 4.32
|  | 2 | 4 |  | 1.23 | 9.84
|  | 2 | 0.96 |  | 2.25 | 4.32
|  | 2 | 4.06 |  | 1.32 | 10.7184
|  | 2 | 0.96 |  | 2.18 | 4.1856
|  | 2 | 3.92 |  | 1.32 | 10.3488
|  | 2 | 0.96 |  | 2.28 | 4.3776
|  | 2 | 3.62 |  | 1.32 | 9.5568
|  | 2 | 0.96 |  | 2.2 | 4.224
|  | -32 | 0.23 |  | 1.35 | -9.936
| -at roof parapet of ward office | 1 | 19.7092 |  | 0.52 | 10.2488
|  | 1 | 18.4901 |  | 0.52 | 9.6148
| - at toilet renovated | 2 | 0.76196 |  | 2.1335 | 3.2513
[6 empty] | 223.9398 | sqm | 253.8 | 56835.9188
| vat on aster | [7 empty] | 670.7445
| vat on weather coat | [7 empty] | 3036.9819
21 | leQf Pjd\ l;lnËdf @ ld=ld= Kn]g XjfO{6 k'§L Knfi6/ ug]{ sfo{
| -at ward office room 1 | 1 | 15.4404 |  | 2.6669 | 41.1776
| -ceiling | 1 | 3.758 | 3.9622 |  | 14.89
| -room 2 | 1 | 18.6955 |  | 2.6669 | 49.8585
| -ceiling | 1 | 5.2575 | 4.0902 |  | 21.5045
| -room 3 | 1 | 14.7839 |  | 2.6669 | 39.4268
| -ceiling | 1 | 3.3017 | 4.0902 |  | 13.5048
| -deduction for door | -3 | 1.0667 |  | 2.1335 | -6.8277
| -deduction for window | -6 | 1.8287 |  | 1.2191 | -13.3767
|  | -1 | 1.2191 |  | 1.2191 | -1.4863
[6 empty] | 158.6714 | sqm | 300.03 | 47606.1781
| vat on white patty | [7 empty] | 1382.6879
22 | Ps sf]6 jf6/ k¦'km l;d]G6 sf]6 nufpg] sfd
| -room 2 | 1 | 5.2575 |  | 2.6669 | 14.0212
| -room 3 | 1 | 6.6035 |  | 2.6669 | 17.6106
| -deduction for door | -1 | 1.0667 |  | 2.1335 | -2.2759
| -deduction for window | -2 | 1.8287 |  | 1.2191 | -4.4589
|  | -1 | 1.2191 |  | 1.2191 | -1.4863
[6 empty] | 23.4107 | sqm | 60.3 | 1411.6637
| vat on cement paint | [7 empty] | 62.9981
23 | k¦fO{d/ afx]s b'O{ sf]6 tof/L jf;]jn l8:6]Dk/ nufpg] sfd .
-at Ground Floor
| -at ward sadasya room | 1 | 25.4008 |  | 2.6669 | 67.7406
| -at passage, toilet and staircase area | 1 | 25.1954 |  | 2.6669 | 67.1928
| -deduction for door | -1 | 1.2 |  | 2.4383 | -2.9259
|  | -1 | 1.0667 |  | 2.1 | -2.2402
|  | -1 | 0.75 |  | 1.8 | -1.35
| -deduction for window | -1 | 0.9 |  | 1.8 | -1.62
|  | -6 | 1.8 |  | 1.2 | -12.96
|  | -1 | 1.2 |  | 1.2 | -1.44
-at first floor
| -at passage and staircase area | 1 | 17.4233 |  | 2.6669 | 46.4658
| -deduction for door | -4 | 1.0667 |  | 2.1 | -8.9607
|  | -1 | 0.75 |  | 1.8 | -1.35
| -deduction for window | -1 | 0.9 |  | 1.8 | -1.62
-at top floor
| -at passage and staircase area | 1 | 14.6297 |  | 2.6669 | 39.0155
| -at kitchen | 1 | 10.6687 |  | 2.6416 | 28.1821
|  | 1 | 4.014 | 3.3273 |  | 13.356
| -deduction for kitchen rack area | -1 | 1.5 |  | 0.9 | -1.35
| -deduction for door | -1 | 1.0667 |  | 1.8 | -1.9201
| -deduction for window | -1 | 1.8 |  | 1.3715 | -2.4688
[6 empty] | 221.7471 | sqm | 125.5 | 27829.2601
| vat on washable distemper | [7 empty] | 1065.4504
24 | c:t/ jfx]s b'O{ sf]6 j]b/ sf]6 ug]{ sfd
-at Ground Floor
| -at outer face | 1 | 35.6093 |  | 2.8436 | 101.2601
| -deduction for door | -1 | 1.2 |  | 2.4383 | -2.9259
| -deduction for window | -1 | 0.9 |  | 1.8 | -1.62
|  | -6 | 1.8 |  | 1.2 | -12.96
|  | -1 | 1.2 |  | 1.2 | -1.44
|  | -1 | 0.9 |  | 1.2 | -1.08
-at first floor
| -at outer face | 1 | 35.6093 |  | 2.8436 | 101.2601
| -deduction for door | -1 | 1.0667 |  | 2.1 | -2.2402
| -deduction for window | -1 | 0.9 |  | 1.8 | -1.62
|  | -6 | 1.8 |  | 1.2 | -12.96
|  | -1 | 1.2 |  | 1.2 | -1.44
|  | -1 | 0.9 |  | 1.2 | -1.08
-at top floor
| -at outer face of staircase area | 1 | 8.1274 |  | 2.8436 | 23.1114
[6 empty] | 186.2656 | sqm | 192.85 | 35921.3153
| vat on washable distemper | [7 empty] | 2526.0592
25 | 20mm GI Pipe threaded -Medium class
| - for kitchen | 1 | 0.9 |  |  | 0.9
| -for outside dhara | 1 | 1.5 |  |  | 1.5
| -for water tank inlet and overflow | 2 | 0.9 |  |  | 1.8
[6 empty] | 4.2 | rm | 248 | 1041.6
| -13% VAT on materials | [7 empty] | 135.408
26 | PPR pipe (PN-16) 20mm OD 2.80mm thick 0.148kg/m
| -for kitchen | 1 | 9 |  |  | 9
[6 empty] | 9 | rm | 75 | 675
| -13% VAT on materials | [7 empty] | 87.75
27 | Porcelain clay white glaze wash basin large size regular complete set
| -for kitchen | 1 |  |  |  | 1
[6 empty] | 1 | set | 1070 | 1070
| -13% VAT on materials | [7 empty] | 139.1
28 | Brass tap-1'2" ordinary
| -for kitchen and outside dhara | 2 |  |  |  | 2
[6 empty] | 2 | set | 750 | 1500
| -13% VAT on materials | [7 empty] | 195
29 | White glazed porcelain clay EWC floor mounted commode without cistern all complete set.
| -for toilet at swasthya | 1 |  |  |  | 1
[6 empty] | 1 | set | 8656 | 8656
| -13% VAT on materials | [7 empty] | 1125.28
30 | Provisional sum for unforseen works at kitchen and water tank | 1 |  |  |  | 1 | PS | 25000 | 25000
31 | Information Board and photographs | 1 |  |  |  | 1 | no. | 500 | 500
1198923.9313
| Description | Amount |  | Percent
| Total Estimated | 1198923.9313
| Budget Allocated | 1050000 |  | 100
| Municipal Payment | 997500 |  | 83.1996
| User Contribution | 201423.9313 |  | 19.1832
| Maintenance 2% | 21000 |  | 2
| Contingencies 3% | 31500 |  | 3
Note on E11: DELL: need to verify
Note on F11: DELL: need to verify

## measurement (hidden)
No. | L | B | H | Quantity | Unit | Area
1 | 3.4 | 0.23 | 1.3 | 1.0166 | m3 | 4.42 | m2
1 | 4 | 0.35 | 1.3 | 1.82 | m3 | 5.2 | m2
1 | 3.9 | 0.23 | 1.2 | 1.0764 | m3 | 4.68 | m2
1 | 3.97 | 0.23 | 1.35 | 1.2327 | m3 | 5.3595 | m2
1 | 3.89 | 0.23 | 1.2 | 1.0736 | m3 | 4.668 | m2
1 | 3.7 | 0.23 | 1.2 | 1.0212 | m3 | 4.44 | m2
1 | 3.95 | 0.23 | 1.04 | 0.94484 | m3 | 4.108 | m2
6 | 0.45 | 0.45 | 2.25 | 2.7338 | m3 | 6.075 | m2
1 | 29.51 | 0.35 | 0.45 | 4.6478 | m3 | 13.2795 | m2
1 | 2.45 | 0.23 | 1.1 | 0.61985 | m3 | 2.695 | m2
1 | 3.92 | 0.23 | 1.13 | 1.0188 | m3 | 4.4296 | m2
1 | 3.95 | 0.23 | 1.25 | 1.1356 | m3 | 4.9375 | m2
1 | 4 | 0.23 | 1.25 | 1.15 | m3 | 5 | m2
1 | 4 | 0.23 | 1.1 | 1.012 | m3 | 4.4 | m2
1 | 3.97 | 0.23 | 1.1 | 1.0044 | m3 | 4.367 | m2
1 | 3.95 | 0.23 | 1.15 | 1.0448 | m3 | 4.5425 | m2
1 | 3.65 | 0.23 | 1.17 | 0.98221 | m3 | 4.2705 | m2
8 | 0.45 | 0.45 | 2.2 | 3.564 | m3 | 7.92 | m2
1 | 33.49 | 0.35 | 0.45 | 5.2747 | m3 | 15.0705 | m2
|  |  |  | 32.3733 | m3 | 109.8626 | m2 | 1182.5512 | 1234.66 | 52.1088
[5 empty] | plaster | 187.39 |  | 2017.0492 | 2129 | 111.9508
5.55