## estimate (2)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:-बाटो सरसफाई तथा मर्मत कार्य (बा २ क ७०६८) | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 9 | [6 empty] | Date: 2082/07/11
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter and backfilling, levelling, clearance and maintainance of road all lifts and lead as per Drawing and instruction of the Engineer. |  | Meter Reading at Start (hrs.) | Meter reading at Stop (hrs.) |  | Total metered hours (hrs.) |  |  |  | as per approved log sheet paper attached herewith
| -For road clearance | 1 | 7391.9 | 7427.4 |  | 35.5 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 35.5 | m3 | 2137 | 75863.5
| Total | [7 empty] | 75863.5
| Total Estimated | 75863.5
| 13% VAT | 9862.255
| Grand Total | 85725.755

## Valuation
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:-बाटो सरसफाई तथा मर्मत कार्य (बा २ क ७०६८) | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 9 | [6 empty] | Date: 2082/07/24
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter and backfilling, levelling, clearance and maintainance of road all lifts and lead as per Drawing and instruction of the Engineer. |  | Meter Reading at Start (hrs.) | Meter reading at Stop (hrs.) |  | Total metered hours (hrs.) |  |  |  | as per approved log sheet paper attached herewith
| -For road clearance | 1 | 7391.9 | 7427.4 |  | 35.5 |  |  |  |  | 7 | 2 | 160.098
| Sub-total |  |  |  |  | 35.5 | m3 | 2137 | 75863.5
| Total | [7 empty] | 75863.5
| Total Valuated | 75863.5
| 13% VAT | 9862.255
| Grand Total | 85725.755