## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- lhDjfn 6f]n b]jLyfg lgdf{0f l;l8 af6f] | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3"*3" of 1.6mm thickness for vertical post | 3 | 2.7431 | 3.54 | 29.1314 | 29.1314
| -MS square pipe of 3"*3" of 1.6mm thickness for vertical post | 3 | 3.9622 | 3.54 | 42.0786 | 42.0786
| -MS square pipe of 3"*3" of 1.6mm thickness for horizontal purlin | 2 | 6.0957 | 3.54 | 43.1576 | 43.1576
|  | 2 | 3.6574 | 3.54 | 25.8945 | 25.8945
| -MS black pipe of 1.5"*1.5" of 2mm thickness for horizontal purlin | 2 | 3.6574 | 2.26 | 16.5315 | 16.5315
|  | 1 | 6.0957 | 2.26 | 13.7763 | 13.7763
| sub-total |  |  |  |  | 170.5699 | Kg | 182.51 | 31130.7212
| -VAT 13% for materials | [7 empty] | 2190.9737
2 | )=$! dL=dL=afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -truss 1 | 1 | 6.0957 | 3.6574 |  | 22.2946
| sub-total |  |  |  |  | 22.2946 | sqm | 1112.58 | 24804.4744
| -13% VAT for sheet | [7 empty] | 2043.49
| -13% VAT for nut bolt | [7 empty] | 296.7126
| -13% VAT for j-hook | [7 empty] | 100.9214
| -13% VAT for bitumen washer | [7 empty] | 47.8218
3 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer.
| -for masonary wall | 1 | 5.4861 | 0.5 | 0.3 | 0.82292
| -for footing of vertical post | 6 | 0.3 | 0.3 | 0.45 | 0.243
| -for plinth | 0.5 | 5.4861 | 3.0479 | 0.15 | 1.2541
| sub-total |  |  |  |  | 2.32 | cum | 748.9 | 1737.4394
4 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -for masonary wall | 1 | 5.4861 | 0.45 | 0.15 | 0.37031
| -for plinth | 1 | 5.4861 | 3.0479 | 0.15 | 2.5081
| -for footing of vertical post | 6 | 0.3 | 0.3 | 0.15 | 0.081
| sub-total |  |  |  |  | 2.9595 | cum | 4458.52 | 13194.7724
| -13% VAT for stone | [7 empty] | 1189.0147
5 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M15
| -for masonary wall | 1 | 5.4861 | 0.45 | 0.075 | 0.18516
| -for plinth | 1 | 5.4861 | 3.0479 | 0.075 | 1.2541
| -for footing of vertical post | 6 | 0.3 | 0.3 | 0.35 | 0.189
| sub-total |  |  |  |  | 1.6282 | cum | 10964.46 | 17852.6145
| -13% VAT for cement | [7 empty] | 759.4418
| -13% VAT for sand | [7 empty] | 302.4416
| -13% VAT for aggregate | [7 empty] | 614.9646
| -13% VAT for formwork | [7 empty] | 89.2638
| -13% VAT for water | [7 empty] | 13.1235
6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer
| -for masonary wall | 1 | 5.4861 | 0.45 | 0.9 | 2.2219
| Sub-total |  |  |  |  | 2.2219 | m3 | 8987.83 | 19969.9118
| -13% VAT for cement | [7 empty] | 338.7544
| -13% VAT for sand | [7 empty] | 381.5303
| -13% VAT for stone | [7 empty] | 855.488
| -13% VAT for water | [7 empty] | 17.9084
7 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 118431.7844
| Total Estimated | 118431.7844 |  | 100
| Budget allocated | 100000
| Municipal payment | 95000 |  | 80.215
| User contribution | 23431.7844 |  | 19.785
| Contingencies | 3000 |  | 3
| Maintanince | 2000 |  | 2