## ESTIMATE
Government of Nepal
Shankharapur Municipality
Shankhu, Kathmandu
Detail Estimate Sheet
| Project:- | gfªn]ef/] :jf:yo rf}sL 5fgf tyf kfgL 6\ofÍL dd{t | [7 empty] | F.Y.:-2080/081
| Location:- Shankharapur Municipality- 1 | [6 empty] | Date: 2081/02/21 |  |  |  |  | Date: 2080/05/21
| S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
| A. | kfgL 6\ofÍL dd{t
| 1 | cf/=l;=l;= jf cf/=lj=l;= sfd eTsfO{ !) dL= k/ x6fpg] sfd | 1 | 4.5 | 3 | 0.1 | 1.35 | cu.m. | 9900 | 13365
| 2 | l;d]G6 jf jh¦ Knfi6/ eTsfO{ !) dL= k/ x6fpg] sfd | 2 | 4.5 |  | 1.4 | 12.6
|  |  | 2 | 3 |  | 1.4 | 8.4
[7 empty] | 21 | sq.m. | 97.2 | 2041.2
| 3 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M$_ df | 2 | 4.5 | 0.1 | 0.9 | 0.81
|  |  | 2 | 3 | 0.1 | 0.9 | 0.54
|  |  | 1 | 5.4878 | 0.23 | 0.45 | 0.56799
[7 empty] | 1.918 | cu.m. | 14911.97 | 28600.9766
|  | vat on cement | [7 empty] | 359.8203
|  | vat on sand | [7 empty] | 175.0256
|  | vat on brick | [7 empty] | 2185.4811
| 4 | cf/=;L=;L= nflu !) ld=ld= kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | 20 | 4.5 |  | 0.61728 | 55.5556
|  |  | 30 | 3 |  | 0.61728 | 55.5556
|  | vat on material |  |  |  |  | 111.1111 | kg | 130.21 | 14467.7778
1880.8111
| 5 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_ | 1 | 4.5 | 3 | 0.075 | 1.0125
|  |  | 2 | 4.5 | 0.15 | 0.9 | 1.215
|  |  | 2 | 3 | 0.15 | 0.9 | 0.81
[7 empty] | 3.0375 | cum | 17107.9 | 51965.2463
|  | vat on cement | [7 empty] | 2279.3765
|  | vat on sand | [7 empty] | 420.7275
|  | vat on aggregate | [7 empty] | 1166.4726
| 6 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_ | 1 | 4.5 | 3 |  | 13.5 | sqm | 692.38 | 9347.13
|  | vat on cement | [7 empty] | 329.2433
|  | vat on sand | [7 empty] | 79.1961
|  | vat on aggregate | [7 empty] | 227.5498
| 7 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | 2 | 4.5 |  | 1.5 | 13.5
|  |  | 2 | 3 |  | 1.5 | 9
[7 empty] | 22.5 | sq.m. | 402.23 | 9050.175
|  | vat on cement | [7 empty] | 227.0932
|  | vat on sand | [7 empty] | 107.0617
| 8 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd | 1 | 4.5 |  | 3 | 13.5
|  |  | 2 | 4.5 |  | 1.5 | 13.5
|  |  | 2 | 3 |  | 1.5 | 9
[7 empty] | 36 | sq.m. | 286.77 | 10323.72
|  | vat on cement | [7 empty] | 359.293
| 9 | square frame medium duty 24"X24 | 1 |  |  |  | 1 | no. | 4659 | 4659 |  | page 196
|  | vat for material | [7 empty] | 605.67
| 10 | 1 HP water pump (mono block |  |  |  |  | 1 | no. | 9938 | 9938 |  | page 175
|  | vat on machine | [7 empty] | 1291.94
| B. | 5fgf dd{t
| 11 | h:tfkftfsf] 5fgf eTsfO{ ;fdfg ;'/lIft /fVg] sfd | 2 | 7.622 | 5.1829 |  | 79.008 | sq.m | 68.4 | 5404.1493
| 12 | dfn;fdfg pknAw u/L k'/fgf] UPVC sheet 5fgf 5fpg] sfd . | 2 | 7.622 | 5.1829 |  | 79.008 | sq.m | 369.1 | 29161.8642
|  | vat on material | [7 empty] | 1279.7721
| 13 | 5fgfdf Ridge cover UPVC PMMA(3MMTHICK) Regular nufpg] sfd lSnk tyf k]r cflb ;d]t k'/f sfo{ ug]{ . | 1 | 7.622 |  |  | 7.622 | m | 2761 | 21044.2073
|  | vat on material | [7 empty] | 2468.2165 |  | 5.1829
#REF!
| 14 | Information Board and photographs | 1 |  |  |  | 1 | no. | 1000 | 1000
225811.1967
[8 empty] | Description |  | Amount | Percent
[8 empty] | Total Estimated |  | 225811.1967
[8 empty] | Budget Allocated |  | 200000 | 100
[8 empty] | Municipal Payment |  | 190000 | 84.1411
[8 empty] | User Contribution |  | 35811.1967 | 17.9056
[8 empty] | Maintenance 2% |  | 4000 | 2
[8 empty] | Contingencies 3% |  | 6000 | 3

## WCR
Government of Nepal
Shankharapur Municipality Office
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  | Total Valuated Amount : |  | #REF!
Project: | #REF! | [7 empty] | Fiscal Year:079/80
Location:Shankharapur-1 | [8 empty] | Date:2079/12/21
S.No. | Description | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  | Quantity | Rate | Amount (Rs) | Quantity | Rate | Amount(Rs)
1 | Earthwork in excavaiton | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Dismantle the rcc work on the base of water tank | 1.35 | 9900 | 13365 | #REF! | #REF! | #REF! | #REF!
3 | stone soling | 21 | 97.2 | 2041.2 | #REF! | #REF! | #REF! | #REF!
| vat on stone |  |  | 0 |  |  | #REF!
4 | Dry Stone Masonry work | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| vat on stone |  |  | #REF! |  |  | #REF!
5 | Brick Masonry work in 1:6 | 1.918 | 14911.97 | 28600.9766 | #REF! | #REF! | #REF! | #REF!
| vat on cement |  |  | 359.8203 |  |  | #REF!
| vat on brick |  |  | 175.0256 |  |  | #REF!
| vat on sand |  |  | 2185.4811 |  |  | #REF!
6 | RCC works 1:1.5:3 ratio in water collection chamber with all work complete | 3.0375 | 17107.9 | 51965.2463 | #REF! | #REF! | #REF! | #REF!
| vat on cement |  |  | 2279.3765 |  |  | #REF!
| vat on aggregate |  |  | 420.7275 |  |  | #REF!
| vat on sand |  |  | 1166.4726 |  |  | #REF!
7 | 3mm punning all complete work | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| vat on cement |  |  | 329.2433 |  |  | #REF!
8 | plastering work | 22.5 | 402.23 | 9050.175 | #REF! | #REF! | #REF! | #REF!
| vat on cement |  |  | 227.0932 |  |  | #REF!
| vat on sand |  |  | 107.0617 |  |  | #REF!
9 | tap and fittings | 1 | 4659 | 4659 | #REF! | #REF! | #REF! | #REF!
10 | Iron frame for barbed wire | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Vat on iron frame |  |  | #REF! |  |  | #REF!
11 | Barbed wire | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| vat on barbed wire |  |  | #REF! |  |  | #REF!
12 | Roof top PVC Water Tank | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| vat on pvc water tank |  |  | #REF! |  |  | #REF!
12 | Information Board | 1 | 500 | 500 | #REF! | #REF! | #REF! | #REF!
| Total |  |  | #REF! |  |  | #REF!

## me
Government of Nepal
Shankharapur Municipality
Shankhu, Kathmandu
Detail Estimate Sheet
| Project:-gfªn]ef/] :jf:yo rf}sL kfgL 6\ofÍL dd{t tyf cGo lalaw dd{t | [8 empty] | F.Y.:-2082/083
| Location:- Shankharapur Municipality- 1 | [6 empty] | Date: 2082/08/19
| S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
| A. | kfgL 6\ofÍL dd{t
| 1 | Kn]g l;d]G6 sqmL6 jf jh¦ s+qmL6 eTsfO{ !) dL= k/ x6fpg] sfd | 1 | 5 | 3.3526 | 0.075 | 1.2572
|  | -at swasthya prasasan | 1 | 1.5757 | 0.60957 | 0.075 | 0.072039
[7 empty] | 1.3293 | cu.m. | 3740 | 4971.4994
| 2 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL | 2 | 5 | 0.23 | 1.4 | 14
|  |  | 2 | 2.8926 | 0.23 | 1.4 | 8.0994
|  |  | 1 | 5 | 0.23 | 0.45 | 2.25
|  | -near ladder of swasthya | 1 | 1.1429 | 0.23 | 0.60957 | 0.6967
|  | -at swasthya prasasan | 1 | 0.60957 | 0.1 | 0.63497 | 0.038706
|  | -at toilet of ward | 1 | 1.6001 | 0.23 | 2.0314 | 3.2505
|  |  | 1 | 1.3715 | 0.23 | 2.4383 | 3.3442
|  | -deduction for opening | -1 | 0.76196 | 0.23 | 1.9811 | -1.5095
[7 empty] | 30.1699 | cum | 1982.2 | 59802.8248
| 3 | ;fx¦f] k¦sf/sf] Sn], g/d d'/d 9'+uf -#) ;]=dL=;Dd_ ld;]sf] df6f]df ;j} lsl;dsf] vGg] sfd
|  |  | 1 | 5 | 3.3526 | 0.075 | 1.2572
[7 empty] | 1.2572 | cum | 770.43 | 968.6144
| 4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
|  | -for flooring | 1 | 5 | 3.3526 |  | 16.7632
[7 empty] | 16.7632 | sqm | 155.75 | 2610.8656
| 5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
|  | -for flooring | 1 | 5 | 3.3526 | 0.075 | 1.2572
[7 empty] | 1.2572 | cum | 13351.1 | 16785.5189
|  | vat on cement | [7 empty] | 681.536
|  | vat on sand | [7 empty] | 231.1318
|  | vat on aggregate | [7 empty] | 447.8333
| 6 | cf/=;L=;L= nflu !) ld=ld= kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd
|  | -Along short length | 33 | 9.7543 |  | 0.61728 | 198.6996
|  |  | 32 | 9.3468 |  | 0.61728 | 184.629
|  | -Along short length | 23 | 8.1024 |  | 0.61728 | 115.0342
|  |  | 22 | 7.6958 |  | 0.61728 | 104.5112
|  |  | 12 | 16.4096 |  | 0.39506 | 77.7938
|  |  | 11 | 15.7982 |  | 0.39506 | 68.654
|  | -Slab | 42 | 4.9284 |  | 0.39506 | 81.7745
|  |  | 64 | 3.2764 |  | 0.39506 | 82.8413
|  | -deduction for opening | -10 | 0.6 |  | 0.39506 | -2.3704
|  |  | -10 | 0.6 |  | 0.39506 | -2.3704
|  | -for fillet | 90 | 1.0424 |  | 0.39506 | 37.0619
[7 empty] | 946.2589 | kg | 132.36 | 125246.8243
|  | vat on material | [7 empty] | 13064.05
| 7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
|  | -For shear wall | 1 | 16.7144 |  | 1.3968 | 23.3472
|  |  | 1 | 15.4953 |  | 1.271 | 19.6938
|  | -for slab | 1 | 4.6998 | 3.0479 |  | 14.3243
|  | -deduction for opening | -1 | 0.6 | 0.6 |  | -0.36
[7 empty] | 57.0052 | sqm | 922.71 | 52599.3006
|  | vat on material | [7 empty] | 3470.2639
| 8 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
|  | -floor and slab | 2 | 5 | 3.3526 | 0.12801 | 4.2917
|  | -shear wall | 2 | 5 | 0.15 | 1.6001 | 2.4002
|  |  | 2 | 3.0479 | 0.15 | 1.6001 | 1.4631
|  | -fillet | 0.5 | 13.057 | 0.30479 | 0.30479 | 0.60646
|  | -deduction for opening | -1 | 0.6 | 0.6 | 0.12801 | -0.046084
[7 empty] | 8.7153 | cum | 13957.29 | 121642.5149
|  | vat on cement | [7 empty] | 5905.6183
|  | vat on sand | [7 empty] | 1530.2218
|  | vat on aggregate | [7 empty] | 3210.4747
|  | vat on diesel | [7 empty] | 445.176
|  | vat on petrol | [7 empty] | 16.0319
| 9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df as per site engineer
|  | -at toilet of ward | 1 | 1.6245 | 0.23 | 2.6669 | 0.99644
|  | -deduction for opening | -1 | 0.76196 | 0.23 | 1.9811 | -0.34719
[7 empty] | 0.64925 | cu.m. | 14491.84 | 9408.7922
|  | vat on cement | [7 empty] | 76.9891
|  | vat on sand | [7 empty] | 80.4665
|  | vat on brick | [7 empty] | 715.8318
| 10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
|  | -At shear wall | 2 | 4.6998 |  | 1.6001 | 15.0405
|  |  | 2 | 3.0479 |  | 1.6001 | 9.7539
|  | -at toilet of ward | 1 | 1.6245 |  | 1.4477 | 2.3518
|  | -deduction for opening | -1 | 0.76196 |  | 1.9811 | -1.5095
[7 empty] | 25.6366 | sq.m. | 415.5 | 10652.0266
|  | vat on cement | [7 empty] | 233.6491
|  | vat on sand | [7 empty] | 154.6313
| 11 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
|  | -at toilet of ward | 1 | 0.86254 |  | 1.2191 | 1.0516
[7 empty] | 1.0516 | sq.m. | 415.5 | 436.9231
|  | vat on porcelain glazed tile | [7 empty] | 92.2268
|  | vat on sand | [7 empty] | 6.6033
|  | vat on cement | [7 empty] | 9.9756
|  | vat on white cement | [7 empty] | 1.3678
| 12 | Ps sf]6 jf6/ k¦'km l;d]G6 sf]6 nufpg] sfd
|  | -at toilet of ward | 1 | 1.6245 |  | 2.4383 | 3.961
|  | -deduction for opening | -1 | 0.76196 |  | 1.9811 | -1.5095
[7 empty] | 2.4515 | sqm | 57.76 | 141.597
|  | vat on cement | [7 empty] | 6.5969
| 13 | b'O{ sf]6 Knfli6s O{dNzg k]G6 nufpg] sfd -k¦fOd/ ;lxt_
|  | -at toilet of ward | 1 | 1.6245 |  | 2.4383 | 3.961
|  | -deduction for opening | -1 | 0.86254 |  | 1.2191 | -1.0516
|  |  | -1 | 0.65617 |  | 0.76196 | -0.49998
[7 empty] | 2.4095 | sqm | 334.57 | 806.1343
|  | vat on cement | [7 empty] | 34.5706
| 14 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_
|  | -at water tank | 1 | 4.0902 | 2.4383 |  | 9.9731 | sqm | 689.98 | 6881.2375
|  | vat on cement | [7 empty] | 219.6314
|  | vat on sand | [7 empty] | 74.1625
|  | vat on aggregate | [7 empty] | 156.5657
| 15 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
|  | -At shear wall | 2 | 4.6998 |  | 2.2001 | 20.6802
|  |  | 2 | 3.0479 |  | 2.2001 | 13.4113
|  | -at floor | 1 | 4.0902 | 2.4383 |  | 9.9731
[7 empty] | 44.0646 | sq.m. | 287.32 | 12660.6388
|  | vat on cement | [7 empty] | 397.1154
| 16 | square frame medium duty 24"X24 | 1 |  |  |  | 1 | no. | 4659 | 4659
|  | vat for material | [7 empty] | 605.67
| 17 | #*X&% dL=dL=lr/fg ;fn sf7sf] k¦m]d $ dL=dL= P]gf vfkf agfO
|  | -at swasthya prasasan | 1 | 0.53337 |  | 1.0667 | 0.56898
[7 empty] | 0.56898 | sq.m. | 10663.63 | 6067.3451
|  | vat on materials | [7 empty] | 389.1846
| 18 | $ dL=dL= df]6fO{sf] P]gf sf7sf] lni6L nufO{ hf]8\g] sfd
|  | -at ward rooms | 3 | 0.43279 |  | 0.99055 | 1.2861
[7 empty] | 1.2861 | sq.m. | 1063.57 | 1367.8755
|  | vat on materials | [7 empty] | 164.3964
| 19 | kmnfd] 3'Dg] e¥ofË M $Æ–^Æ Ø ;Ddsf] dWod >]0fLsf] sfnf] kfO{k kf]i6 k¦of]u u/ #÷$Æx#÷$Æ sf] :Sjfo/ kfO{k df !!÷$ÆØ sf] dWod >]0fLsf] sfnf] kfO{ksf] x\of08/]n k¦of]u u/L @Ú–)Æ b]lv @Ú–^Æ rf}8fO{;Ddsf] kmnfd] 3'Dg] e¥ofË cfjZos ;fdu¦Lx? ;lxt
|  | -ladder | 1 | 0.91436 |  |  | 0.91436
[7 empty] | 0.91436 | rm | 11197.91 | 10238.8692
|  | vat on materials | [7 empty] | 1331.053
| 20 | -!M@ efudf jf6/ k¦'km sDkfp08 ld;fO{ 8]Dk k¦'lkm+Ë ug
|  | -at water tank | 1 | 15.4953 |  | 1.6001 | 24.7943
|  |  | 1 | 4.0902 | 2.4383 |  | 9.9731
[7 empty] | 34.7674 | sqm | 11197.91 | 389322.5229
|  | vat on materials | [7 empty] | 1286.7321
| 21 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
| 22 | Information Board and photographs | 1 |  |  |  | 1 | no. | 500 | 500
877810.6827
|  | Description | Amount |  | Percent
|  | Total Estimated | 877810.6827
|  | Budget Allocated | 200000 |  | 100
|  | Municipal Payment | 190000 |  | 21.6448
|  | User Contribution | 687810.6827 |  | 343.9053
|  | Maintenance 2% | 4000 |  | 2
|  | Contingencies 3% | 6000 |  | 3
Note on F10: DELL: need to verify
Note on G10: DELL: need to verify

## Sheet1
152 | ;'Vvf O{6f RofK6f] 5fKg] sfd .
H 15 | b/ ljZn]if0fsf] nflu !) j=dL= lnOPsf]
| ;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
| >lds | s_ l;kfn' | 0.5 | hjfg | 1245 | 622.5
|  | v_ HofdL | 1 | hjfg | 935 | 935 | 1557.5
| lgdf{0f ;fdu¦L | O{6f | 0 | uf]6f | 15.145 | 0
|  | jfn'jf vf]nfsf] | 0 | 3=dL= | 3177.9 | 0 | 0
[5 empty] | jf:tljs b//]6 |  | 1557.5
| b/ k¦lt j=dL=sf] |  |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 233.62
| 1791.12 | Ö ?= | 179.11 | k}= | hDdf b/ /]6 |  | 1791.12
10
=

## <1000000
Government of Nepal
Shankharapur Municipality
Shankhu, Kathmandu
Detail Estimate Sheet
| Project:-gfªn]ef/] :jf:yo rf}sL kfgL 6\ofÍL dd{t tyf cGo lalaw dd{t | [8 empty] | F.Y.:-2082/083
| Location:- Shankharapur Municipality- 1 | [6 empty] | Date: 2082/08/19
| S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
| A. | kfgL 6\ofÍL dd{t
| 1 | Kn]g l;d]G6 sqmL6 jf jh¦ s+qmL6 eTsfO{ !) dL= k/ x6fpg] sfd | 1 | 5 | 3.3526 | 0.075 | 1.2572
|  | -at swasthya prasasan | 1 | 1.5757 | 0.60957 | 0.075 | 0.072039
[7 empty] | 1.3293 | cu.m. | 4301 | 5717.2243
| 2 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL | 2 | 5 | 0.23 | 1.4 | 3.22
|  |  | 2 | 2.8926 | 0.23 | 1.4 | 1.8629
|  |  | 1 | 5 | 0.1 | 0.45 | 0.225
|  | -at swasthya prasasan | 1 | 0.60957 | 0.1 | 0.63497 | 0.038706
|  | -at toilet of ward | 1 | 1.6001 | 0.23 | 2.0314 | 0.74761
|  |  | 1 | 1.3715 | 0.23 | 2.4383 | 0.76916
|  | -deduction for opening | -1 | 0.76196 | 0.23 | 1.9811 | -0.34719
[7 empty] | 6.5161 | cum | 2279.53 | 14853.7459
| 3 | ;fx¦f] k¦sf/sf] Sn], g/d d'/d 9'+uf -#) ;]=dL=;Dd_ ld;]sf] df6f]df ;j} lsl;dsf] vGg] sfd
|  |  | 1 | 5 | 3.3526 | 0.15 | 2.5145
[7 empty] | 2.5145 | cum | 885.9945 | 2227.8131
| 4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
|  | -for flooring | 1 | 5 | 3.3526 |  | 16.7632
[7 empty] | 16.7632 | sqm | 179.1125 | 3002.4954
| 5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
|  | -for flooring | 1 | 5 | 3.3526 | 0.075 | 1.2572
[7 empty] | 1.2572 | cum | 15353.765 | 19303.3467
| 6 | cf/=;L=;L= nflu !) ld=ld= kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd
|  | -Along short length | 33 | 9.7543 |  | 0.61728 | 198.6996
|  |  | 32 | 9.3468 |  | 0.61728 | 184.629
|  | -Along long length | 23 | 8.1024 |  | 0.61728 | 115.0342
|  |  | 22 | 7.6958 |  | 0.61728 | 104.5112
|  | -binders | 12 | 16.4096 |  | 0.39506 | 77.7938
|  |  | 11 | 15.7982 |  | 0.39506 | 68.654
|  | -Slab | 42 | 4.9284 |  | 0.39506 | 81.7745
|  |  | 64 | 3.2764 |  | 0.39506 | 82.8413
|  | -deduction for opening | -10 | 0.6 |  | 0.39506 | -2.3704
|  |  | -10 | 0.6 |  | 0.39506 | -2.3704
|  | -for fillet | 90 | 1.0424 |  | 0.39506 | 37.0619
[7 empty] | 946.2589 | kg | 152.214 | 144033.8479
| 7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
|  | -For shear wall | 1 | 16.7144 |  | 1.3968 | 23.3472
|  |  | 1 | 15.4953 |  | 1.271 | 19.6938
|  | -for slab | 1 | 4.6998 | 3.0479 |  | 14.3243
|  | -deduction for opening | -1 | 0.6 | 0.6 |  | -0.36
[7 empty] | 57.0052 | sqm | 1061.1165 | 60489.1957
| 8 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
|  | -floor and slab | 2 | 5 | 3.3526 | 0.12801 | 4.2917
|  | -shear wall | 2 | 5 | 0.15 | 1.6001 | 2.4002
|  |  | 2 | 3.0479 | 0.15 | 1.2953 | 1.1844
|  | -shear wall offset for support | 2 | 0.23 | 0.075 | 1.2953 | 0.044689
|  |  | 4 | 0.075 | 0.075 | 1.6001 | 0.036003
|  | -fillet | 0.5 | 13.057 | 0.30479 | 0.30479 | 0.60646
|  | -deduction for opening | -1 | 0.6 | 0.6 | 0.12801 | -0.046084
[7 empty] | 8.5173 | cum | 16050.8835 | 136710.9768
| 9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df as per site engineer
|  | -at toilet of ward | 1 | 1.6245 | 0.23 | 2.6669 | 0.99644
|  | -deduction for opening | -1 | 0.76196 | 0.23 | 1.9811 | -0.34719
[7 empty] | 0.64925 | cum | 16665.616 | 10820.111
| 10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
|  | -At shear wall | 2 | 4.6998 |  | 1.6001 | 15.0405
|  |  | 2 | 3.0479 |  | 1.6001 | 9.7539
|  | -at toilet of ward | 1 | 1.6245 |  | 1.4477 | 2.3518
|  | -deduction for opening | -1 | 0.76196 |  | 1.9811 | -1.5095
[7 empty] | 25.6366 | sqm | 477.825 | 12249.8306
| 11 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
|  | -at toilet of ward | 1 | 0.86254 |  | 1.2191 | 1.0516
[7 empty] | 1.0516 | sqm | 477.825 | 502.4616
| 12 | Ps sf]6 jf6/ k¦'km l;d]G6 sf]6 nufpg] sfd
|  | -at toilet of ward | 1 | 1.6245 |  | 2.4383 | 3.961
|  | -deduction for opening | -1 | 0.76196 |  | 1.9811 | -1.5095
[7 empty] | 2.4515 | sqm | 66.424 | 162.8366
| 13 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_
|  | -at water tank | 1 | 4.0902 | 2.4383 |  | 9.9731 | sqm | 793.477 | 7913.4231
| 14 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
|  | -At shear wall | 2 | 4.6998 |  | 2.2001 | 20.6802
|  |  | 2 | 3.0479 |  | 1.8953 | 11.5534
|  | -at floor | 1 | 4.0902 | 2.4383 |  | 9.9731
[7 empty] | 42.2067 | sq.m. | 330.418 | 13945.8578
| 15 | square frame medium duty 24"X24 | 1 |  |  |  | 1 | no. | 4659 | 4659
| 16 | #*X&% dL=dL=lr/fg ;fn sf7sf] k¦m]d $ dL=dL= P]gf vfkf agfO
|  | -at swasthya prasasan | 1 | 0.53337 |  | 1.0667 | 0.56898
[7 empty] | 0.56898 | sq.m. | 12263.1745 | 6977.4469
| 17 | $ dL=dL= df]6fO{sf] P]gf sf7sf] lni6L nufO{ hf]8\g] sfd
|  | -at ward rooms | 3 | 0.43279 |  | 0.99055 | 1.2861
[7 empty] | 1.2861 | sq.m. | 1223.1055 | 1573.0569
| 18 | -!M@ efudf jf6/ k¦'km sDkfp08 ld;fO{ 8]Dk k¦'lkm+Ë ug
|  | -at water tank | 1 | 15.4953 |  | 1.6001 | 24.7943
|  |  | 1 | 4.0902 | 2.4383 |  | 9.9731
[7 empty] | 34.7674 | sqm | 520.79 | 18106.5285
| 19 | Information Board and photographs | 1 |  |  |  | 1 | no. | 500 | 500
463749.1988
|  | Total Estimated | 463749.1988
|  | VAT 13% | 60287.3958
|  | Grand total | 524036.5946
Note on F10: DELL: need to verify
Note on G10: DELL: need to verify