## initial 2 storey (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- k~rkfn] led;]g dlGb/ cw'/f] | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark | Water tap size
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | [9 empty] | length | Breadth | thickness | Height 1 | Height 2 | Width of stand tap
| -for stand tap | 1 | 1.6763 | 1.6763 | 0.15 | 0.42151 |  |  |  |  | 1.6763 | 1.6763 | 0.23 | 0.6 | 1.2 | 0.3566
| Sub-total |  |  |  |  | 0.42151 | cum | 674.12 | 284.1459
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for stand tap | 1 | 1.6763 | 1.6763 |  | 2.81
| Sub-total |  |  |  |  | 2.81 | sqm | 1017.47 | 2859.1341
| -13% VAT for brick | [7 empty] | 232.3672
| -13% VAT for sand | [7 empty] | 82.4239
3 | d]lzgsf] k¦of]u u/L hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -!M@M$_
| -for lintel | 2 | 4.5718 | 0.35 | 0.1 | 0.32002
|  | 2 | 2.9717 | 0.35 | 0.1 | 0.20802
| -for stand tap | 1 | 1.6763 | 1.6763 | 0.1 | 0.281
| Sub-total |  |  |  |  | 0.80904 | cum | 12884.61 | 10424.2229
| -13% VAT for cement | [7 empty] | 438.5746
| -13% VAT for aggregate | [7 empty] | 290.2284
| -13% VAT for sand | [7 empty] | 148.7354
| -13% VAT for water | [7 empty] | 3.8284
| -13% VAT for water | [7 empty] | 41.3257
| -13% VAT for water | [7 empty] | 1.4882
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -beam | 2 | 4.5718 | 0.23 | 0.23 | 0.48369
|  | 4 | 2.9717 | 0.23 | 0.23 | 0.6288
| -upper beam | 2 | 2.4901 | 0.23 | 0.23 | 0.26345
|  | 2 | 1.1429 | 0.23 | 0.23 | 0.12092
| -slab | 2 | 3.9374 | 1.9293 | 0.075 | 1.1394
|  | 2 | 3.0479 | 1.9293 | 0.075 | 0.88203
| -column | 4 | 0.23 | 0.23 | 0.68577 | 0.14511
| Sub-total |  |  |  |  | 3.6635 | cum | 13957.29 | 51131.9232
| -13% VAT for cement | [7 empty] | 2482.402
| -13% VAT for aggregate | [7 empty] | 1349.5096
| -13% VAT for sand | [7 empty] | 643.2223
| -13% VAT for water | [7 empty] | 26.67
| -13% VAT for diesel | [7 empty] | 187.1279
| -13% VAT for petrol | [7 empty] | 6.7389
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -beam | 2 | 4.5718 |  | 0.46 | 4.206
|  | 4 | 2.9717 |  | 0.46 | 5.4678
| -upper beam | 2 | 2.4901 |  | 0.46 | 2.2909
|  | 2 | 1.1429 |  | 0.46 | 1.0515
| -slab | 2 | 3.9374 | 1.9293 |  | 15.1926
|  | 2 | 3.0479 | 1.9293 |  | 11.7604
| -column | 4 | 0.92 |  | 0.68577 | 2.5236
| Sub-total |  |  |  |  | 42.4929 | sqm | 922.71 | 39208.6389
| -13% VAT for plyboard | [7 empty] | 1108.2419
| -13% VAT for wood | [7 empty] | 736.2631
| -13% VAT for iron props | [7 empty] | 560.009
| -13% VAT for nails | [7 empty] | 182.2946
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit Weight (Kg/m) | Total Weight (Kg)
| -beam | 12 | 4.9272 | 0.88889 | 52.5563 | 0.052556
| -stirrups | 64 | 0.81439 | 0.39506 | 20.5909 | 0.020591
| -beam | 12 | 3.787 | 0.88889 | 40.395 | 0.040395
| -stirrups | 88 | 0.81439 | 0.39506 | 28.3125 | 0.028312
| -upper beam | 12 | 2.8455 | 0.88889 | 30.3517 | 0.030352
| -stirrups | 30 | 0.81439 | 0.39506 | 9.652 | 0.009652
| -upper beam | 12 | 1.9583 | 0.88889 | 20.8888 | 0.020889
| -stirrups | 16 | 0.81439 | 0.39506 | 5.1477 | 0.0051477
| -slab | 12 | 13.9704 | 0.39506 | 66.2302 | 0.06623
|  | 50 | 1.9293 | 0.39506 | 38.1094 | 0.038109
|  | 38 | 1.9293 | 0.39506 | 28.9632 | 0.028963
| -column | 8 | 1.9424 | 0.88889 | 13.8124 | 0.013812
| -stirrups | 24 | 0.71117 | 0.39506 | 6.7429 | 0.0067429
|  | 24 | 0.50798 | 0.39506 | 4.8164 | 0.0048164
| Sub-total |  |  |  |  | 0.36657 | MT | 132360 | 48519.1245
| -13% VAT for TMT rod | [7 empty] | 5003.6722
| -13% VAT for binding wire | [7 empty] | 57.1848
7 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_
| -flooring | 1 | 3.8607 | 2.9717 |  | 11.4727
| Sub-total |  |  |  |  | 11.4727 | sqm | 689.98 | 7915.9388
| -13% VAT for cement | [7 empty] | 252.6564
| -13% VAT for sand | [7 empty] | 70.3995
| -13% VAT for aggregate | [7 empty] | 180.1077
8 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
| -flooring | 1 | 3.8607 | 2.9717 |  | 11.4727
| -for wing walls of stand tap | 4 | 1.2163 |  | 0.6 | 2.9192
| -for side wall of stand tap | 1 | 1.3197 |  | 0.6 | 0.79183
| -stand | 1 | 0.3566 |  | 1.2 | 0.42792
|  | 1 | 0.46 |  | 0.6 | 0.276
| -for floor area | 1 | 1.6763 | 1.6763 |  | 2.81
| Sub-total |  |  |  |  | 18.6977 | sqm | 287.32 | 5372.2128
| -13% VAT for cement | [7 empty] | 168.5056
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for wall continue | 2 | 2.9717 | 0.35 | 1.8805 | 3.9118
|  | 2 | 4.5718 | 0.35 | 1.8805 | 6.0181
| -deduction for door | -1 | 1.5 | 0.35 | 1.0667 | -0.56004
| -deduction for window | -2 | 1.0667 | 0.35 | 1.0667 | -0.79657
| -for wing walls of stand tap | 2 | 1.2163 | 0.23 | 0.6 | 0.3357
| -for side wall of stand tap | 1 | 1.3197 | 0.23 | 0.6 | 0.18212
| -for stand tap | 1 | 0.3566 | 0.23 | 1.2 | 0.098421
| Sub-total |  |  |  |  | 9.1896 | cum | 14491.84 | 133173.6673
| -13% VAT for brick | [7 empty] | 10132.0071
| -13% VAT for cement | [7 empty] | 1089.7176
| -13% VAT for sanda | [7 empty] | 1138.9369
| -13% VAT for water | [7 empty] | 33.45
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -for wall continue | 1 | 16.5133 |  | 3.0479 | 50.33
|  | 1 | 13.6605 |  | 3.0479 | 41.6351
| -deduction for door | -2 | 1.5 |  | 2.1335 | -6.4005
| -deduction for window | -4 | 1.0667 |  | 1.0667 | -4.5518
| -for wing walls of stand tap | 4 | 1.2163 |  | 0.6 | 2.9192
| -for side wall of stand tap | 1 | 1.3197 |  | 0.6 | 0.79183
| -stand | 1 | 0.3566 |  | 1.2 | 0.42792
|  | 1 | 0.46 |  | 0.6 | 0.276
| Sub-total |  |  |  |  | 85.4277 | sqm | 415.5 | 35495.1906
| -13% VAT for cement | [7 empty] | 778.5766
| -13% VAT for sand | [7 empty] | 515.2696
11 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as plaster | 1 |  |  |  | 81.0127
| Sub-total |  |  |  |  | 81.0127 | sqm | 253.8 | 20561.0337
| -13% VAT for aster | [7 empty] | 242.6494
| -13% VAT for weather coat | [7 empty] | 1098.6624
12 | Carved salwood lattice (jali) shutter of carved door/window including wood
| -door | 1 | 1.5 |  | 1.0667 | 1.6001
| -window | 2 | 1.0667 |  | 1.0667 | 2.2759
| Sub-total |  |  |  |  | 3.876 | sqm | 37363.64 | 144822.3751
| -13% VAT for salwood | [7 empty] | 4332.7981
13 | 20mm GI pipe threaded-Medium class
| -for pipe laying | 1 | 1.2 |  |  | 1.2
| sub-total |  |  |  |  | 1.2 | rm | 248 | 297.6
| -13% VAT | [7 empty] | 38.688
14 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
15 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 535761.87
| Total Estimated | 535761.87 |  | 100
| Budget allocated | 700000
| Municipal payment | 665000 |  | 124.1223
| User contribution | -129238.13 |  | -24.1223
| Contingencies | 21000 |  | 3
| Maintanince | 14000 |  | 2

## Sheet1 (hidden)
Foundation size |  |  | Footing size |  |  | Plinth size |  |  | Toe wall |  |  |  | Column size |  |  | Tie beam size |  |  | Tie beam size
Length | Breadth | Depth from GL | Length in PL area | Breadth in PL area | Depth | Length | Breadth | Depth from GL | Length L1 | Ht. H1 | Length L2 | Ht. H2 | Length/B | Ht. upto plinth | Ht. above PL upto ceiling | Length | Width | Height | Length | Width | Height
1.5 | 1.5 | 1.5 | 0.93965 | 0.93965 | 0.35 | 4.267 | 4.267 | 0.45 | 2.3877 | 0.82 | 0.58305 | 1.6 | 0.35 | 1.37 | 3.0722 | 3.567 | 0.23 | 0.23 | -4.7463 | 0.23 | 0.35

## 2.5' ht (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- k~rkfn] led;]g dlGb/ cw'/f] | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark | Water tap size
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | [9 empty] | length | Breadth | thickness | Height 1 | Height 2 | Width of stand tap
| -for stand tap | 1 | 1.6763 | 1.6763 | 0.15 | 0.42151 |  |  |  |  | 1.6763 | 1.6763 | 0.23 | 0.6 | 1.2 | 0.3566
| Sub-total |  |  |  |  | 0.42151 | cum | 674.12 | 284.1459
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for stand tap | 1 | 1.6763 | 1.6763 |  | 2.81
| Sub-total |  |  |  |  | 2.81 | sqm | 1017.47 | 2859.1341
| -13% VAT for brick | [7 empty] | 232.3672
| -13% VAT for sand | [7 empty] | 82.4239
3 | d]lzgsf] k¦of]u u/L hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -!M@M$_
| -for lintel | 2 | 4.5718 | 0.35 | 0.1 | 0.32002
|  | 2 | 2.9717 | 0.35 | 0.1 | 0.20802
| -for stand tap | 1 | 1.6763 | 1.6763 | 0.1 | 0.281
| Sub-total |  |  |  |  | 0.80904 | cum | 12884.61 | 10424.2229
| -13% VAT for cement | [7 empty] | 438.5746
| -13% VAT for aggregate | [7 empty] | 290.2284
| -13% VAT for sand | [7 empty] | 148.7354
| -13% VAT for water | [7 empty] | 3.8284
| -13% VAT for water | [7 empty] | 41.3257
| -13% VAT for water | [7 empty] | 1.4882
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -beam | 2 | 4.5718 | 0.23 | 0.35 | 0.73606
|  | 4 | 2.9717 | 0.23 | 0.35 | 0.95687
| -upper beam | 2 | 2.4901 | 0.23 | 0.23 | 0.26345
|  | 2 | 1.1429 | 0.23 | 0.23 | 0.12092
| -slab | 2 | 4.0262 | 1.8805 | 0.075 | 1.1357
|  | 2 | 3.124 | 1.9293 | 0.075 | 0.90408
| -column | 4 | 0.23 | 0.23 | 0.53337 | 0.11286
| Sub-total |  |  |  |  | 4.23 | cum | 13957.29 | 59038.6897
| -13% VAT for cement | [7 empty] | 2866.2673
| -13% VAT for aggregate | [7 empty] | 1558.1906
| -13% VAT for sand | [7 empty] | 742.6868
| -13% VAT for water | [7 empty] | 30.7941
| -13% VAT for diesel | [7 empty] | 216.0643
| -13% VAT for petrol | [7 empty] | 7.781
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -beam | 2 | 4.5718 |  | 0.7 | 6.4005
|  | 4 | 2.9717 |  | 0.7 | 8.3206
| -upper beam | 2 | 2.4901 |  | 0.46 | 2.2909
|  | 2 | 1.1429 |  | 0.46 | 1.0515
| -slab | 2 | 4.0262 | 1.8805 |  | 15.1428
|  | 2 | 3.124 | 1.9293 |  | 12.0544
| -column | 4 | 0.92 |  | 0.53337 | 1.9628
| Sub-total |  |  |  |  | 47.2235 | sqm | 922.71 | 43573.5925
| -13% VAT for plyboard | [7 empty] | 1231.6184
| -13% VAT for wood | [7 empty] | 818.2285
| -13% VAT for iron props | [7 empty] | 622.3528
| -13% VAT for nails | [7 empty] | 202.5888
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit Weight (Kg/m) | Total Weight (Kg)
| -beam | 8 | 4.8272 | 1.5802 | 61.0248 | 0.061025
|  | 4 | 3.227 | 0.88889 | 11.4739 | 0.011474
| -stirrups | 64 | 0.81439 | 0.39506 | 20.5909 | 0.020591
| -beam | 16 | 3.687 | 1.5802 | 93.2228 | 0.093223
|  | 8 | 3.2055 | 0.88889 | 22.7945 | 0.022794
| -stirrups | 88 | 0.81439 | 0.39506 | 28.3125 | 0.028312
| -upper beam | 12 | 2.7455 | 0.88889 | 29.2851 | 0.029285
| -stirrups | 30 | 0.81439 | 0.39506 | 9.652 | 0.009652
| -upper beam | 12 | 1.8583 | 0.88889 | 19.8221 | 0.019822
| -stirrups | 16 | 0.81439 | 0.39506 | 5.1477 | 0.0051477
| -slab | 11 | 8.0524 | 0.39506 | 34.9932 | 0.034993
|  | 52 | 1.8805 | 0.39506 | 38.632 | 0.038632
|  | 40 | 1.9293 | 0.39506 | 30.4875 | 0.030488
|  | 24 | 3.124 | 0.39506 | 29.6206 | 0.029621
| -column | 8 | 1.7138 | 0.88889 | 12.1869 | 0.012187
| -stirrups | 24 | 0.71117 | 0.39506 | 6.7429 | 0.0067429
|  | 24 | 0.50798 | 0.39506 | 4.8164 | 0.0048164
| Sub-total |  |  |  |  | 0.45881 | MT | 132360 | 60727.5251
| -13% VAT for TMT rod | [7 empty] | 6262.6981
| -13% VAT for binding wire | [7 empty] | 71.5737
7 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_
| -peti area | 2 | 3.6574 | 0.9 |  | 6.5834
|  | 2 | 6.4005 | 0.9 |  | 11.5209
| Sub-total |  |  |  |  | 18.1042 | sqm | 689.98 | 12491.5611
| -13% VAT for cement | [7 empty] | 398.6986
| -13% VAT for sand | [7 empty] | 111.0923
| -13% VAT for aggregate | [7 empty] | 284.2148
7 | !^ dL=dL=u¦]gfO{6, @) dL dL afSnf] !M@ efusf] l;d]G6 d;nfdf 5fkL 3f]6\g] / kflnz ;d]t ug]{
| -flooring inside | 1 | 3.8607 | 2.9717 |  | 11.4727
| Sub-total |  |  |  |  | 11.4727 | sqm | 6851.63 | 78606.7477
| -13% VAT for cement | [7 empty] | 252.6564
| -13% VAT for sand | [7 empty] | 86.7354
| -13% VAT for 16mm granite | [7 empty] | 6460.9342
| -13% VAT for cShflns Pl;8 | [7 empty] | 6.898
| -13% VAT for d}g kflnz | [7 empty] | 6.458
| -13% VAT for tf/k]G6fOg | [7 empty] | 17.7319
| -13% VAT for sfaf]{/08d 9'ª\uf | [7 empty] | 17.8974
8 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
| -for wing walls of stand tap | 4 | 1.2163 |  | 0.6 | 2.9192
| -for side wall of stand tap | 1 | 1.3197 |  | 0.6 | 0.79183
| -stand | 1 | 0.3566 |  | 1.2 | 0.42792
|  | 1 | 0.46 |  | 0.6 | 0.276
| -for floor area | 1 | 1.6763 | 1.6763 |  | 2.81
| -peti area | 2 | 3.6574 | 0.9 |  | 6.5834
|  | 2 | 6.4005 | 0.9 |  | 11.5209
| Sub-total |  |  |  |  | 25.3292 | sqm | 287.32 | 7277.5837
| -13% VAT for cement | [7 empty] | 228.2697
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for wall continue | 2 | 2.9717 | 0.35 | 1.7799 | 3.7026
|  | 2 | 4.5718 | 0.35 | 1.7799 | 5.6963
| -deduction for door | -1 | 1.5 | 0.35 | 1.0667 | -0.56004
| -deduction for window | -2 | 1.0667 | 0.35 | 1.0667 | -0.79657
| -for wing walls of stand tap | 2 | 1.2163 | 0.23 | 0.6 | 0.3357
| -for side wall of stand tap | 1 | 1.3197 | 0.23 | 0.6 | 0.18212
| -for stand tap | 1 | 0.3566 | 0.23 | 1.2 | 0.098421
| Sub-total |  |  |  |  | 8.6585 | cum | 14491.84 | 125477.079
| -13% VAT for brick | [7 empty] | 9546.4417
| -13% VAT for cement | [7 empty] | 1026.7389
| -13% VAT for sanda | [7 empty] | 1073.1136
| -13% VAT for water | [7 empty] | 31.5168
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -for wall continue | 1 | 16.5133 |  | 3.0479 | 50.33
|  | 1 | 13.6605 |  | 1.9811 | 27.0628
| -deduction for door | -2 | 1.5 |  | 2.1335 | -6.4005
| -deduction for window | -4 | 1.0667 |  | 1.0667 | -4.5518
| -roof | 2 | 4.0262 | 1.8805 |  | 15.1428
|  | 2 | 3.124 | 1.9293 |  | 12.0544
| -for wing walls of stand tap | 4 | 1.2163 |  | 0.6 | 2.9192
| -for side wall of stand tap | 1 | 1.3197 |  | 0.6 | 0.79183
| -stand | 1 | 0.3566 |  | 1.2 | 0.42792
|  | 1 | 0.46 |  | 0.6 | 0.276
| Sub-total |  |  |  |  | 98.0525 | sqm | 415.5 | 40740.8306
| -13% VAT for cement | [7 empty] | 893.6382
| -13% VAT for sand | [7 empty] | 591.4185
10 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -inside face of wall | 1 | 13.6605 |  | 1.0667 | 14.5723
| -deduction for door | -1 | 1.5 |  | 1.0667 | -1.6001
| Sub-total |  |  |  |  | 12.9722 | sqm | 2845.18 | 36908.1179
| -13% VAT for cement | [7 empty] | 123.0602
| -13% VAT for sand | [7 empty] | 81.4589
| -13% VAT for white cement | [7 empty] | 16.8739
| -13% VAT for porcelain glazed tile | [7 empty] | 1137.7198
11 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as plaster | 1 |  |  |  | 93.6376
| Sub-total |  |  |  |  | 93.6376 | sqm | 253.8 | 23765.2297
| -13% VAT for aster | [7 empty] | 280.4634
| -13% VAT for weather coat | [7 empty] | 1269.876
12 | Knfi6/ dfly @) dL=dL= afSnf] emNn/ jf kfgL k§L agfpg] sfd
| -at top | 1 | 20.4206 |  |  | 20.4206
| Sub-total |  |  |  |  | 20.4206 | rm | 144.41 | 2948.9393
| -13% VAT for cement | [7 empty] | 242.1332
| -13% VAT for sand | [7 empty] | 33.741
| -13% VAT for water proofing | [7 empty] | 0.053094
13 | Carved salwood lattice (jali) shutter of carved door/window including wood
| -door | 1 | 1.5 |  | 1.0667 | 1.6001
| -window | 2 | 1.0667 |  | 1.0667 | 2.2759
| Sub-total |  |  |  |  | 3.876 | sqm | 37363.64 | 144822.3751
| -13% VAT for salwood | [7 empty] | 4332.7981
14 | 20mm GI pipe threaded-Medium class
| -for pipe laying | 1 | 1.2 |  |  | 1.2
| sub-total |  |  |  |  | 1.2 | rm | 248 | 297.6
| -13% VAT | [7 empty] | 38.688
7 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ sfd | No. | Length (m) | Unit weight (Kg/m) | Weight (Kg)
| -MS square pipe for post of 3"*3"*1.6mm thickness | 24 | 1.13 | 3.54 | 96.0048 | 96.0048
| -MS square pipe for binding of 80mm*40mm*1.6mm thickness | 1 | 21.9445 | 2.93 | 64.2975 | 64.2975
| Sub-total |  |  |  |  | 160.3023 | Kg | 182.51 | 29256.7673
| -13% VAT for any kind of angles and MS black pipes | [7 empty] | 1938.0544
| -13% VAT for primer | [7 empty] | 121.0308
14 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 60000 | 60000
15 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 783062.292
| Total Estimated | 783062.292 |  | 100
| Budget allocated | 700000
| Municipal payment | 665000 |  | 84.923
| User contribution | 118062.292 |  | 15.077
| Contingencies | 21000 |  | 3
| Maintanince | 14000 |  | 2

## total slope
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- k~rkfn] led;]g dlGb/ cw'/f] | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark | Water tap size
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | [9 empty] | length | Breadth | thickness | Height 1 | Height 2 | Width of stand tap
| -for stand tap | 1 | 1.6763 | 1.6763 | 0.15 | 0.42151 |  |  |  |  | 1.6763 | 1.6763 | 0.23 | 0.6 | 1.2 | 0.3566
| Sub-total |  |  |  |  | 0.42151 | cum | 674.12 | 284.1459
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for stand tap | 1 | 1.6763 | 1.6763 |  | 2.81
| Sub-total |  |  |  |  | 2.81 | sqm | 1017.47 | 2859.1341
| -13% VAT for brick | [7 empty] | 232.3672
| -13% VAT for sand | [7 empty] | 82.4239
3 | d]lzgsf] k¦of]u u/L hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -!M@M$_
| -for lintel | 2 | 4.5718 | 0.35 | 0.1 | 0.32002
|  | 2 | 2.9717 | 0.35 | 0.1 | 0.20802
| -for stand tap | 1 | 1.6763 | 1.6763 | 0.1 | 0.281
| Sub-total |  |  |  |  | 0.80904 | cum | 12884.61 | 10424.2229
| -13% VAT for cement | [7 empty] | 438.5746
| -13% VAT for aggregate | [7 empty] | 290.2284
| -13% VAT for sand | [7 empty] | 148.7354
| -13% VAT for water | [7 empty] | 3.8284
| -13% VAT for diesel | [7 empty] | 41.3257
| -13% VAT for petrol | [7 empty] | 1.4882
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -beam | 2 | 4.5718 | 0.23 | 0.35 | 0.73606
|  | 4 | 2.9717 | 0.23 | 0.35 | 0.95687
| -upper beam | 2 | 1.5239 | 0.23 | 0.23 | 0.16123
|  | 2 | 1.1429 | 0.23 | 0.23 | 0.12092
| -slab | 2 | 2.7812 | 3.2002 | 0.075 | 1.3351
|  | 2 | 2.324 | 2.8955 | 0.075 | 1.0094
| -column | 4 | 0.23 | 0.23 | 0.81286 | 0.172
| Sub-total |  |  |  |  | 4.4915 | cum | 13957.29 | 62689.1269
| -13% VAT for cement | [7 empty] | 3043.4923
| -13% VAT for aggregate | [7 empty] | 1654.5355
| -13% VAT for sand | [7 empty] | 788.6081
| -13% VAT for water | [7 empty] | 32.6981
| -13% VAT for diesel | [7 empty] | 229.4239
| -13% VAT for petrol | [7 empty] | 8.2621
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -beam | 2 | 4.5718 |  | 0.7 | 6.4005
|  | 4 | 2.9717 |  | 0.7 | 8.3206
| -upper beam | 2 | 1.5239 |  | 0.46 | 1.402
|  | 2 | 1.1429 |  | 0.46 | 1.0515
| -slab | 2 | 2.7812 | 3.2002 |  | 17.8008
|  | 2 | 2.324 | 2.8955 |  | 13.458
| -column | 4 | 0.92 |  | 0.58286 | 2.1449
| Sub-total |  |  |  |  | 50.5784 | sqm | 922.71 | 46669.1916
| -13% VAT for plyboard | [7 empty] | 1319.1162
| -13% VAT for wood | [7 empty] | 876.358
| -13% VAT for iron props | [7 empty] | 666.5666
| -13% VAT for nails | [7 empty] | 216.9813
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit Weight (Kg/m) | Total Weight (Kg)
| -beam | 8 | 4.8272 | 1.5802 | 61.0248 | 0.061025
|  | 4 | 3.227 | 0.88889 | 11.4739 | 0.011474
| -stirrups | 64 | 0.81439 | 0.39506 | 20.5909 | 0.020591
| -beam | 16 | 3.687 | 1.5802 | 93.2228 | 0.093223
|  | 8 | 2.2393 | 0.88889 | 15.9239 | 0.015924
| -stirrups | 88 | 0.81439 | 0.39506 | 28.3125 | 0.028312
| -upper beam | 12 | 1.8793 | 0.88889 | 20.0459 | 0.020046
| -stirrups | 14 | 0.81439 | 0.39506 | 4.5043 | 0.0045043
| -upper beam | 12 | 1.9583 | 0.88889 | 20.8888 | 0.020889
| -stirrups | 16 | 0.81439 | 0.39506 | 5.1477 | 0.0051477
| -slab | 20 | 5.5623 | 0.39506 | 43.9493 | 0.043949
|  | 34 | 3.2002 | 0.39506 | 42.986 | 0.042986 |  |  |  |  | 3.2002 | 1.6001
|  | 28 | 2.8955 | 0.39506 | 32.0288 | 0.032029 |  |  |  |  | 2.8955
|  | 36 | 2.324 | 0.39506 | 33.0523 | 0.033052
| -column | 8 | 1.6123 | 0.88889 | 11.4651 | 0.011465
| -stirrups | 20 | 0.71117 | 0.39506 | 5.6191 | 0.0056191
|  | 20 | 0.50798 | 0.39506 | 4.0136 | 0.0040136
| Sub-total |  |  |  |  | 0.45425 | MT | 132360 | 60124.4789
| -13% VAT for TMT rod | [7 empty] | 6200.5072
| -13% VAT for binding wire | [7 empty] | 70.8629
7 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_
| -peti area | 2 | 3.6574 | 0.9 |  | 6.5834
|  | 2 | 6.4005 | 0.9 |  | 11.5209
| Sub-total |  |  |  |  | 18.1042 | sqm | 689.98 | 12491.5611
| -13% VAT for cement | [7 empty] | 398.6986
| -13% VAT for sand | [7 empty] | 111.0923
| -13% VAT for aggregate | [7 empty] | 284.2148
8 | !^ dL=dL=u¦]gfO{6, @) dL dL afSnf] !M@ efusf] l;d]G6 d;nfdf 5fkL 3f]6\g] / kflnz ;d]t ug]{
| -flooring inside | 1 | 3.8607 | 2.9717 |  | 11.4727
| Sub-total |  |  |  |  | 11.4727 | sqm | 6851.63 | 78606.7477
| -13% VAT for cement | [7 empty] | 252.6564
| -13% VAT for sand | [7 empty] | 86.7354
| -13% VAT for 16mm granite | [7 empty] | 6460.9342
| -13% VAT for cShflns Pl;8 | [7 empty] | 6.898
| -13% VAT for d}g kflnz | [7 empty] | 6.458
| -13% VAT for tf/k]G6fOg | [7 empty] | 17.7319
| -13% VAT for sfaf]{/08d 9'ª\uf | [7 empty] | 17.8974
9 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
| -for wing walls of stand tap | 4 | 1.2163 |  | 0.6 | 2.9192
| -for side wall of stand tap | 1 | 1.3197 |  | 0.6 | 0.79183
| -stand | 1 | 0.3566 |  | 1.2 | 0.42792
|  | 1 | 0.46 |  | 0.6 | 0.276
| -for floor area | 1 | 1.6763 | 1.6763 |  | 2.81
| -peti area | 2 | 3.6574 | 0.9 |  | 6.5834
|  | 2 | 6.4005 | 0.9 |  | 11.5209
| Sub-total |  |  |  |  | 25.3292 | sqm | 287.32 | 7277.5837
| -13% VAT for cement | [7 empty] | 228.2697
10 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for wall continue | 2 | 2.9717 | 0.35 | 1.7799 | 3.7026
|  | 2 | 4.5718 | 0.35 | 1.7799 | 5.6963
| -deduction for door | -1 | 1.5 | 0.35 | 1.0667 | -0.56004
| -deduction for window | -2 | 1.0667 | 0.35 | 1.0667 | -0.79657
| -for wing walls of stand tap | 2 | 1.2163 | 0.23 | 0.6 | 0.3357
| -for side wall of stand tap | 1 | 1.3197 | 0.23 | 0.6 | 0.18212
| -for stand tap | 1 | 0.3566 | 0.23 | 1.2 | 0.098421
| Sub-total |  |  |  |  | 8.6585 | cum | 14491.84 | 125477.079
| -13% VAT for brick | [7 empty] | 9546.4417
| -13% VAT for cement | [7 empty] | 1026.7389
| -13% VAT for sanda | [7 empty] | 1073.1136
| -13% VAT for water | [7 empty] | 31.5168
11 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -for wall continue | 1 | 16.5133 |  | 3.0479 | 50.33
|  | 1 | 13.6605 |  | 1.9811 | 27.0628
| -deduction for door | -2 | 1.5 |  | 2.1335 | -6.4005
| -deduction for window | -4 | 1.0667 |  | 1.0667 | -4.5518
| -roof | 2 | 2.7812 | 3.2002 |  | 17.8008
|  | 2 | 2.324 | 2.8955 |  | 13.458
| -for wing walls of stand tap | 4 | 1.2163 |  | 0.6 | 2.9192
| -for side wall of stand tap | 1 | 1.3197 |  | 0.6 | 0.79183
| -stand | 1 | 0.3566 |  | 1.2 | 0.42792
|  | 1 | 0.46 |  | 0.6 | 0.276
| Sub-total |  |  |  |  | 102.1142 | sqm | 415.5 | 42428.4499
| -13% VAT for cement | [7 empty] | 930.6556
| -13% VAT for sand | [7 empty] | 615.917
12 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -inside face of wall | 1 | 13.6605 |  | 1.0667 | 14.5723
| -deduction for door | -1 | 1.5 |  | 1.0667 | -1.6001
| Sub-total |  |  |  |  | 12.9722 | sqm | 2845.18 | 36908.1179
| -13% VAT for cement | [7 empty] | 123.0602
| -13% VAT for sand | [7 empty] | 81.4589
| -13% VAT for white cement | [7 empty] | 16.8739
| -13% VAT for porcelain glazed tile | [7 empty] | 1137.7198
13 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as plaster | 1 |  |  |  | 97.6993
| Sub-total |  |  |  |  | 97.6993 | sqm | 253.8 | 24796.0787
| -13% VAT for aster | [7 empty] | 292.6289
| -13% VAT for weather coat | [7 empty] | 1324.9586
14 | Knfi6/ dfly @) dL=dL= afSnf] emNn/ jf kfgL k§L agfpg] sfd
| -at top | 1 | 20.4206 |  |  | 20.4206
| Sub-total |  |  |  |  | 20.4206 | rm | 144.41 | 2948.9393
| -13% VAT for cement | [7 empty] | 242.1332
| -13% VAT for sand | [7 empty] | 33.741
| -13% VAT for water proofing | [7 empty] | 0.053094
15 | cu¦fv sf7sf] rf}s; agfO hf]8\g] sfd
| -door | 1 | 6.0704 | 0.075 | 0.1 | 0.045528
| -window | 2 | 2.3367 | 0.075 | 0.075 | 0.026288
| Sub-total |  |  |  |  | 0.071816 | cum | 284731.83 | 20448.232
| -13% VAT for salwood | [7 empty] | 2233.3959
16 | Carved salwood lattice (jali) shutter of carved door/window including wood
| -door | 1 | 1.3715 |  | 2.1335 | 2.9262
| -window | 2 | 1.0667 |  | 1.0667 | 2.2759
| Sub-total |  |  |  |  | 5.2021 | cum | 37363.64 | 194367.9907
| -13% VAT for salwood | [7 empty] | 5815.1047
17 | 20mm GI pipe threaded-Medium class
| -for pipe laying | 1 | 1.2 |  |  | 1.2
| sub-total |  |  |  |  | 1.2 | rm | 248 | 297.6
| -13% VAT | [7 empty] | 38.688
18 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ sfd | No. | Length (m) | Unit weight (Kg/m) | Weight (Kg)
| -MS square pipe for post of 3"*3"*1.6mm thickness | 24 | 1.13 | 3.54 | 96.0048 | 96.0048
| -MS square pipe for binding of 80mm*40mm*1.6mm thickness | 1 | 21.9445 | 2.93 | 64.2975 | 64.2975
| Sub-total |  |  |  |  | 160.3023 | Kg | 182.51 | 29256.7673
| -13% VAT for any kind of angles and MS black pipes | [7 empty] | 1938.0544
| -13% VAT for primer | [7 empty] | 121.0308
19 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
20 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Total | [7 empty] | 811738.6324
| Total Estimated | 811738.6324 |  | 100
| Budget allocated | 700000
| Municipal payment | 665000 |  | 81.9229
| User contribution | 146738.6324 |  | 18.0771
| Contingencies | 21000 |  | 3
| Maintanince | 14000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 615013.6081 |  |  |  |  | Total Valuated Amount : |  | 383357.4856
Work Started : | [7 empty] | Work Finished:
Project:- k~rkfn] led;]g dlGb/ cw'/f] | [7 empty] | F.Y:2082/2083
Location:- Shankharapur Municipality 1 | [7 empty] | Date:2083/06/20
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | cum | 0.42151 | 674.12 | 284.1459 | 0 | 674.12 | 0 | -284.1459 |  | 355.1824
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd | sqm | 2.81 | 1017.47 | 2859.1341 | 0 | 1017.47 | 0 | -2859.1341 |  | 3573.9177
| -13% VAT for brick |  |  |  | 232.3672 |  |  | 0 | -232.3672
| -13% VAT for sand |  |  |  | 82.4239 |  |  | 0 | -82.4239
3 | d]lzgsf] k¦of]u u/L hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -!M@M$_ | cum | 0.80904 | 12884.61 | 10424.2229 | 0 | 12884.61 | 0 | -10424.2229 |  | 13030.2786
| -13% VAT for cement |  |  |  | 438.5746 |  |  | 0 | -438.5746 |  | 548.2183
| -13% VAT for aggregate |  |  |  | 290.2284 |  |  | 0 | -290.2284
| -13% VAT for sand |  |  |  | 148.7354 |  |  | 0 | -148.7354
| -13% VAT for water |  |  |  | 3.8284 |  |  | 0 | -3.8284
| -13% VAT for diesel |  |  |  | 41.3257 |  |  | 0 | -41.3257
| -13% VAT for petrol |  |  |  | 1.4882 |  |  | 0 | -1.4882
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | cum | 4.4915 | 13957.29 | 62689.1269 | 5.4161 | 13957.29 | 75594.0031 | 12904.8762 |  | 78361.4086
| -13% VAT for cement |  |  |  | 3043.4923 |  |  | 3670.0107 | 626.5184 |  | 3804.3654
| -13% VAT for aggregate |  |  |  | 1654.5355 |  |  | 1995.13 | 340.5946
| -13% VAT for sand |  |  |  | 788.6081 |  |  | 950.9471 | 162.339
| -13% VAT for water |  |  |  | 32.6981 |  |  | 39.4292 | 6.7311
| -13% VAT for diesel |  |  |  | 229.4239 |  |  | 276.6519 | 47.2281
| -13% VAT for petrol |  |  |  | 8.2621 |  |  | 9.9629 | 1.7008
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd | sqm | 50.5784 | 922.71 | 46669.1916 | 64.7947 | 922.71 | 59786.7571 | 13117.5655 |  | 58336.4895
| -13% VAT for plyboard |  |  |  | 1319.1162 |  |  | 1689.8875 | 370.7712 |  | 1648.8953
| -13% VAT for wood |  |  |  | 876.358 |  |  | 1122.6807 | 246.3227
| -13% VAT for iron props |  |  |  | 666.5666 |  |  | 853.9221 | 187.3555
| -13% VAT for nails |  |  |  | 216.9813 |  |  | 277.9694 | 60.9881
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | MT | 0.45425 | 132360 | 60124.4789 | 0.56765 | 132360 | 75134.3703 | 15009.8914 |  | 75155.5986
| -13% VAT for TMT rod |  |  |  | 6200.5072 |  |  | 7748.4448 | 1547.9376 |  | 7750.634
| -13% VAT for binding wire |  |  |  | 70.8629 |  |  | 88.5537 | 17.6907
7 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_ | sqm | 18.1042 | 689.98 | 12491.5611 | 0 | 689.98 | 0 | -12491.5611 |  | 15614.4514
| -13% VAT for cement |  |  |  | 398.6986 |  |  | 0 | -398.6986 |  | 498.3732
| -13% VAT for sand |  |  |  | 111.0923 |  |  | 0 | -111.0923
| -13% VAT for aggregate |  |  |  | 284.2148 |  |  | 0 | -284.2148
8 | !^ dL=dL=u¦]gfO{6, @) dL dL afSnf] !M@ efusf] l;d]G6 d;nfdf 5fkL 3f]6\g] / kflnz ;d]t ug]{ | sqm | 11.4727 | 6851.63 | 78606.7477 | 0 | 6851.63 | 0 | -78606.7477 |  | 98258.4346
| -13% VAT for cement |  |  |  | 252.6564 |  |  | 0 | -252.6564 |  | 315.8206
| -13% VAT for sand |  |  |  | 86.7354 |  |  | 0 | -86.7354
| -13% VAT for 16mm granite |  |  |  | 6460.9342 |  |  | 0 | -6460.9342
| -13% VAT for cShflns Pl;8 |  |  |  | 6.898 |  |  | 0 | -6.898
| -13% VAT for d}g kflnz |  |  |  | 6.458 |  |  | 0 | -6.458
| -13% VAT for tf/k]G6fOg |  |  |  | 17.7319 |  |  | 0 | -17.7319
| -13% VAT for sfaf]{/08d 9'ª\uf |  |  |  | 17.8974 |  |  | 0 | -17.8974
9 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd | sqm | 25.3292 | 287.32 | 7277.5837 | 0 | 287.32 | 0 | -7277.5837 |  | 9096.9796
| -13% VAT for cement |  |  |  | 228.2697 |  |  | 0 | -228.2697 |  | 285.3372
10 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | cum | 8.6585 | 14491.84 | 125477.079 | 6.4717 | 14491.84 | 93786.2961 | -31690.7829 |  | 156846.3488
| -13% VAT for brick |  |  |  | 9546.4417 |  |  | 7135.3702 | -2411.0715 |  | 11933.0522
| -13% VAT for cement |  |  |  | 1026.7389 |  |  | 767.4233 | -259.3156
| -13% VAT for sanda |  |  |  | 1073.1136 |  |  | 802.0855 | -271.0281
| -13% VAT for water |  |  |  | 31.5168 |  |  | 23.5569 | -7.96
11 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | sqm | 102.1142 | 415.5 | 42428.4499 | 73.6146 | 415.5 | 30586.8827 | -11841.5671 |  | 53035.5623
| -13% VAT for cement |  |  |  | 930.6556 |  |  | 670.9143 | -259.7413 |  | 1163.3196
| -13% VAT for sand |  |  |  | 615.917 |  |  | 444.0177 | -171.8993
12 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd . | sqm | 12.9722 | 2845.18 | 36908.1179 | 0 | 2845.18 | 0 | -36908.1179 |  | 46135.1474
| -13% VAT for cement |  |  |  | 123.0602 |  |  | 0 | -123.0602 |  | 153.8253
| -13% VAT for sand |  |  |  | 81.4589 |  |  | 0 | -81.4589
| -13% VAT for white cement |  |  |  | 16.8739 |  |  | 0 | -16.8739
| -13% VAT for porcelain glazed tile |  |  |  | 1137.7198 |  |  | 0 | -1137.7198
13 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd | sqm | 97.6993 | 253.8 | 24796.0787 | 73.6146 | 253.8 | 18683.3955 | -6112.6832 |  | 30995.0984
| -13% VAT for aster |  |  |  | 292.6289 |  |  | 220.4906 | -72.1383 |  | 365.7861
| -13% VAT for weather coat |  |  |  | 1324.9586 |  |  | 998.3323 | -326.6263
14 | Knfi6/ dfly @) dL=dL= afSnf] emNn/ jf kfgL k§L agfpg] sfd | rm | 20.4206 | 144.41 | 2948.9393 | 0 | 144.41 | 0 | -2948.9393 |  | 3686.1742
| -13% VAT for cement |  |  |  | 242.1332 |  |  | 0 | -242.1332 |  | 302.6665
| -13% VAT for sand |  |  |  | 33.741 |  |  | 0 | -33.741
| -13% VAT for water proofing |  |  |  | 0.053094 |  |  | 0 | -0.053094
15 | cu¦fv sf7sf] rf}s; agfO hf]8\g] sfd | cum | 0.071816 | 284731.83 | 20448.232 | 0 | 37363.64 | 0 | -20448.232 |  | 25560.29
| -13% VAT for salwood |  |  |  | 2233.3959 |  |  | 0 | -2233.3959 |  | 2791.7449
17 | 20mm GI pipe threaded-Medium class | rm | 1.2 | 248 | 297.6 | 0 | 248 | 0 | -297.6 |  | 372
| -13% VAT |  |  |  | 38.688 |  |  | 0 | -38.688 |  | 48.36
18 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ sfd | Kg | 160.3023 | 182.51 | 29256.7673 | 0 | 182.51 | 0 | -29256.7673 |  | 36570.9592
| -13% VAT for any kind of angles and MS black pipes |  |  |  | 1938.0544 |  |  | 0 | -1938.0544 |  | 2422.5681
| -13% VAT for primer |  |  |  | 121.0308 |  |  | 0 | -121.0308
19 | Provisional sum for unforseen works | PS | 1 | 5000 | 5000 | 0 | 5000 | 0 | -5000 |  | 6250
20 | Information board (सुचना पाटि) | no. | 1 | 1000 | 1000 | 0 | 1000 | 0 | -1000
| Total |  |  |  | 615013.6081 |  |  | 383357.4856 | -231656.1225 |  |  | 0.62333

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- k~rkfn] led;]g dlGb/ cw'/f] | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date: 2083/06/20
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark | Water tap size
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | [9 empty] | length | Breadth | thickness | Height 1 | Height 2 | Width of stand tap
| -for stand tap | 0 | 1.6763 | 1.6763 | 0.15 | 0 |  |  |  |  | 1.6763 | 1.6763 | 0.23 | 0.6 | 1.2 | 0.3566
| Sub-total |  |  |  |  | 0 | cum | 674.12 | 0
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for stand tap | 0 | 1.6763 | 1.6763 |  | 0
| Sub-total |  |  |  |  | 0 | sqm | 1017.47 | 0
| -13% VAT for brick | [7 empty] | 0
| -13% VAT for sand | [7 empty] | 0
3 | d]lzgsf] k¦of]u u/L hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -!M@M$_
| -for lintel | 0 | 4.5718 | 0.35 | 0.1 | 0
|  | 0 | 2.9717 | 0.35 | 0.1 | 0
| -for stand tap | 0 | 1.6763 | 1.6763 | 0.1 | 0
| Sub-total |  |  |  |  | 0 | cum | 12884.61 | 0
| -13% VAT for cement | [7 empty] | 0
| -13% VAT for aggregate | [7 empty] | 0
| -13% VAT for sand | [7 empty] | 0
| -13% VAT for water | [7 empty] | 0
| -13% VAT for water | [7 empty] | 0
| -13% VAT for water | [7 empty] | 0
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -beam | 2 | 4.5718 | 0.23 | 0.3 | 0.63091
|  | 2 | 2.9442 | 0.23 | 0.3 | 0.4063
|  | 2 | 2.9442 | 0.23 | 0.3 | 0.4063
| -upper beam | 2 | 1.3715 | 0.23 | 0.23 | 0.14511
|  | 2 | 0.99055 | 0.23 | 0.23 | 0.1048
| -slab | 2 | 3.2383 | 2.4509 | 0.075 | 1.1905 |  |  |  |  | 2.451 | 8.0413 | 2.4509
|  | 2 | 3.6955 | 2.1335 | 0.075 | 1.1827 |  |  |  |  | 3.6955 | 12.1244
| -column | 4 | 0.23 | 0.23 | 1.2191 | 0.25797
| -cantilever | 2 | 6 | 0.71117 | 0.075 | 0.64005
|  | 2 | 4.3888 | 0.68577 | 0.075 | 0.45146
| Sub-total |  |  |  |  | 5.4161 | cum | 13957.29 | 75594.0031
| -13% VAT for cement | [7 empty] | 3670.0107
| -13% VAT for aggregate | [7 empty] | 1995.13
| -13% VAT for sand | [7 empty] | 950.9471
| -13% VAT for water | [7 empty] | 39.4292
| -13% VAT for diesel | [7 empty] | 276.6519
| -13% VAT for petrol | [7 empty] | 9.9629
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -beam | 2 | 4.5718 |  | 0.6 | 5.4861
|  | 2 | 2.9442 |  | 0.6 | 3.5331
|  | 2 | 2.9442 |  | 0.6 | 3.5331
| -upper beam | 2 | 1.3715 |  | 0.46 | 1.2618
|  | 2 | 0.99055 |  | 0.46 | 0.91131
|  | 1 | 3.8098 |  | 0.23 | 0.87626
| -slab | 2 | 3.2383 | 2.3368 |  | 15.1346
|  | 2 | 3.6955 | 2.032 |  | 15.0186
| -column | 4 | 0.92 |  | 1.2191 | 4.4864
| -cantilever | 2 | 6 | 0.71117 |  | 8.534
|  | 2 | 4.3888 | 0.68577 |  | 6.0194
| Sub-total |  |  |  |  | 64.7947 | sqm | 922.71 | 59786.7571
| -13% VAT for plyboard | [7 empty] | 1689.8875
| -13% VAT for wood | [7 empty] | 1122.6807
| -13% VAT for iron props | [7 empty] | 853.9221
| -13% VAT for nails | [7 empty] | 277.9694
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit Weight (Kg/m) | Total Weight (Kg)
| -beam | 4 | 6.13 | 0.88889 | 21.7956 | 0.021796 |  |  |  |  | 19.3579
|  | 4 | 4.5209 | 0.88889 | 16.0742 | 0.016074
| -stirrups | 70 | 0.81439 | 0.39506 | 22.5213 | 0.022521
| -beam | 8 | 5 | 0.88889 | 35.5556 | 0.035556
|  | 8 | 3.5559 | 0.88889 | 25.2866 | 0.025287
| -stirrups | 56 | 0.81439 | 0.39506 | 18.017 | 0.018017
| -upper beam | 8 | 1.7272 | 0.88889 | 12.2824 | 0.012282
| -stirrups | 20 | 0.81439 | 0.39506 | 6.4347 | 0.0064347
| -upper beam | 8 | 1.8034 | 0.88889 | 12.8243 | 0.012824
| -stirrups | 20 | 0.81439 | 0.39506 | 6.4347 | 0.0064347
| -column | 16 | 2.2097 | 0.88889 | 31.4267 | 0.031427
| -stirrups | 40 | 0.71117 | 0.39506 | 11.2382 | 0.011238
| -at first floor level catilever-slab | 8 | 6.3751 | 0.61728 | 31.4819 | 0.031482
|  | 6 | 5.9942 | 0.61728 | 22.2008 | 0.022201
|  | 48 | 1.7017 | 0.61728 | 50.4212 | 0.050421
|  | 46 | 0.81276 | 0.61728 | 23.0784 | 0.023078
|  | 6 | 5.1304 | 0.61728 | 19.0017 | 0.019002
|  | 8 | 6.3751 | 0.61728 | 31.4819 | 0.031482
|  | 30 | 1.0033 | 0.61728 | 18.5787 | 0.018579
|  | 36 | 1.3207 | 0.61728 | 29.3497 | 0.02935
| -at upper floor | 40 | 2.3368 | 0.61728 | 57.6985 | 0.057698
|  | 36 | 2.032 | 0.61728 | 45.1556 | 0.045156
|  | 28 | 0.55867 | 0.61728 | 9.656 | 0.009656
|  | 28 | 0.55867 | 0.61728 | 9.656 | 0.009656
| Sub-total |  |  |  |  | 0.56765 | MT | 132360 | 75134.3703
| -13% VAT for TMT rod | [7 empty] | 7748.4448
| -13% VAT for binding wire | [7 empty] | 88.5537
7 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_
| -peti area | 0 | 3.6574 | 0.9 |  | 0
|  | 0 | 6.4005 | 0.9 |  | 0
| Sub-total |  |  |  |  | 0 | sqm | 689.98 | 0
| -13% VAT for cement | [7 empty] | 0
| -13% VAT for sand | [7 empty] | 0
| -13% VAT for aggregate | [7 empty] | 0
8 | !^ dL=dL=u¦]gfO{6, @) dL dL afSnf] !M@ efusf] l;d]G6 d;nfdf 5fkL 3f]6\g] / kflnz ;d]t ug]{
| -flooring inside | 0 | 3.8607 | 2.9717 |  | 0
| Sub-total |  |  |  |  | 0 | sqm | 6851.63 | 0
| -13% VAT for cement | [7 empty] | 0
| -13% VAT for sand | [7 empty] | 0
| -13% VAT for 16mm granite | [7 empty] | 0
| -13% VAT for cShflns Pl;8 | [7 empty] | 0
| -13% VAT for d}g kflnz | [7 empty] | 0
| -13% VAT for tf/k]G6fOg | [7 empty] | 0
| -13% VAT for sfaf]{/08d 9'ª\uf | [7 empty] | 0
9 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
| -for wing walls of stand tap | 0 | 1.2163 |  | 0.6 | 0
| -for side wall of stand tap | 0 | 1.3197 |  | 0.6 | 0
| -stand | 0 | 0.3566 |  | 1.2 | 0
|  | 0 | 0.46 |  | 0.6 | 0
| -for floor area | 0 | 1.6763 | 1.6763 |  | 0
| -peti area | 0 | 3.6574 | 0.9 |  | 0
|  | 0 | 6.4005 | 0.9 |  | 0
| Sub-total |  |  |  |  | 0 | sqm | 287.32 | 0
| -13% VAT for cement | [7 empty] | 0
10 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for wall continue | 2 | 2.9464 | 0.35 | 1.3715 | 2.8287 |  |  |  |  | 9.66 | 66.75 | 54 | 12.75 | 1.0625
|  | 2 | 4.5718 | 0.35 | 1.3715 | 4.3892 |  |  |  |  | 3.8718
| -deduction for door | -1 | 1.2 | 0.35 | 1.0667 | -0.44803
| -deduction for window | -2 | 0.6 | 0.35 | 0.71015 | -0.29826
| -for wing walls of stand tap | 0 | 1.2163 | 0.23 | 0.6 | 0
| -for side wall of stand tap | 0 | 1.3197 | 0.23 | 0.6 | 0
| -for stand tap | 0 | 0.3566 | 0.23 | 1.2 | 0
| Sub-total |  |  |  |  | 6.4717 | cum | 14491.84 | 93786.2961
| -13% VAT for brick | [7 empty] | 7135.3702
| -13% VAT for cement | [7 empty] | 767.4233
| -13% VAT for sanda | [7 empty] | 802.0855
| -13% VAT for water | [7 empty] | 23.5569
11 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -for wall continue | 1 | 16.5133 |  | 3.0479 | 50.33
|  | 1 | 13.6605 |  | 1.9811 | 27.0628
| -deduction for door | -1 | 1.2 |  | 2.4383 | -2.9259
| -deduction for window | -2 | 0.6 |  | 0.71015 | -0.85218
| -roof | 0 | 3.2383 | 2.3368 |  | 0
|  | 0 | 3.6955 | 2.032 |  | 0
| -for wing walls of stand tap | 0 | 1.2163 |  | 0.6 | 0
| -for side wall of stand tap | 0 | 1.3197 |  | 0.6 | 0
| -stand | 0 | 0.3566 |  | 1.2 | 0
|  | 0 | 0.46 |  | 0.6 | 0
| Sub-total |  |  |  |  | 73.6146 | sqm | 415.5 | 30586.8827
| -13% VAT for cement | [7 empty] | 670.9143
| -13% VAT for sand | [7 empty] | 444.0177
12 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -inside face of wall | 0 | 13.6605 |  | 1.0667 | 0
| -deduction for door | 0 | 1.2 |  | 1.0667 | 0
| Sub-total |  |  |  |  | 0 | sqm | 2845.18 | 0
| -13% VAT for cement | [7 empty] | 0
| -13% VAT for sand | [7 empty] | 0
| -13% VAT for white cement | [7 empty] | 0
| -13% VAT for porcelain glazed tile | [7 empty] | 0
13 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as plaster | 0 |  |  |  | 73.6146
| Sub-total |  |  |  |  | 73.6146 | sqm | 253.8 | 18683.3955
| -13% VAT for aster | [7 empty] | 220.4906
| -13% VAT for weather coat | [7 empty] | 998.3323
14 | Knfi6/ dfly @) dL=dL= afSnf] emNn/ jf kfgL k§L agfpg] sfd
| -at top | 0 | 20.4206 |  |  | 0
| Sub-total |  |  |  |  | 0 | rm | 144.41 | 0
| -13% VAT for cement | [7 empty] | 0
| -13% VAT for sand | [7 empty] | 0
| -13% VAT for water proofing | [7 empty] | 0
15 | cu¦fv sf7sf] rf}s; agfO hf]8\g] sfd
| -door | 1 | 6.0704 | 0.075 | 0.1 | 0.045528
| -window | 2 | 2.3367 | 0.075 | 0.075 | 0.026288
| Sub-total |  |  |  |  | 0.071816 | cum | 284731.83 | 20448.232
| -13% VAT for salwood | [7 empty] | 2233.3959
16 | Carved salwood lattice (jali) shutter of carved door/window including wood
| -door | 0 | 1.2 |  | 2.1335 | 0
| -window | 0 | 0.6 |  | 0.71015 | 0
| Sub-total |  |  |  |  | 0 | sqm | 37363.64 | 0
| -13% VAT for salwood | [7 empty] | 0
17 | 20mm GI pipe threaded-Medium class
| -for pipe laying | 0 | 1.2 |  |  | 0
| sub-total |  |  |  |  | 0 | rm | 248 | 0
| -13% VAT | [7 empty] | 0
18 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ sfd | No. | Length (m) | Unit weight (Kg/m) | Weight (Kg)
| -MS square pipe for post of 3"*3"*1.6mm thickness | 0 | 1.13 | 3.54 | 0 | 0
| -MS square pipe for binding of 80mm*40mm*1.6mm thickness | 0 | 21.9445 | 2.93 | 0 | 0
| Sub-total |  |  |  |  | 0 | Kg | 182.51 | 0
| -13% VAT for any kind of angles and MS black pipes | [7 empty] | 0
| -13% VAT for primer | [7 empty] | 0
19 | Provisional sum for unforseen works | 0 |  |  |  | 0 | PS | 5000 | 0
20 | Information board (सुचना पाटि) | 0 |  |  |  | 0 | no. | 1000 | 0
| Total | [7 empty] | 406039.1136
| Total Valuated | 406039.1136 |  | 100
| Budget allocated | 700000
| Municipal payment | 332627.2418 |  | 81.92
| User contribution | 73411.8717 |  | 18.08
| Contingencies | 21000 |  | 3
| Maintanince | 14000 |  | 2

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- k~rkfn] led;]g dlGb/ cw'/f] | [9 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [9 empty] | Date: 2083/06/20
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark | Water tap size
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | [9 empty] | length | Breadth | thickness | Height 1 | Height 2 | Width of stand tap
| -for stand tap | 0 | 1.6763 | 1.6763 | 0.15 | 0 |  |  |  |  | 1.6763 | 1.6763 | 0.23 | 0.6 | 1.2 | 0.3566
| Sub-total |  |  |  |  | 0 | cum | 674.12 | 0
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for stand tap | 0 | 1.6763 | 1.6763 |  | 0
| Sub-total |  |  |  |  | 0 | sqm | 1017.47 | 0
| -13% VAT for brick | [7 empty] | 0
| -13% VAT for sand | [7 empty] | 0
3 | d]lzgsf] k¦of]u u/L hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -!M@M$_
| -for lintel | 0 | 4.5718 | 0.35 | 0.1 | 0
|  | 0 | 2.9717 | 0.35 | 0.1 | 0
| -for stand tap | 0 | 1.6763 | 1.6763 | 0.1 | 0
| Sub-total |  |  |  |  | 0 | cum | 12884.61 | 0
| -13% VAT for cement | [7 empty] | 0
| -13% VAT for aggregate | [7 empty] | 0
| -13% VAT for sand | [7 empty] | 0
| -13% VAT for water | [7 empty] | 0
| -13% VAT for water | [7 empty] | 0
| -13% VAT for water | [7 empty] | 0
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -beam | 2 | 4.5718 | 0.23 | 0.3 | 0.63091
|  | 2 | 2.9442 | 0.23 | 0.3 | 0.4063
|  | 2 | 2.9442 | 0.23 | 0.3 | 0.4063
| -upper beam | 2 | 1.3715 | 0.23 | 0.23 | 0.14511
|  | 2 | 0.99055 | 0.23 | 0.23 | 0.1048
| -slab | 2 | 3.2383 | 2.4509 | 0.075 | 1.1905 |  |  |  |  | 2.451 | 8.0413 | 2.4509
|  | 2 | 3.6955 | 2.1335 | 0.075 | 1.1827 |  |  |  |  | 3.6955 | 12.1244
| -column | 4 | 0.23 | 0.23 | 1.2191 | 0.25797
| -cantilever | 2 | 6 | 0.71117 | 0.075 | 0.64005
|  | 2 | 4.3888 | 0.68577 | 0.075 | 0.45146
| Sub-total |  |  |  |  | 5.4161 | cum | 13957.29 | 75594.0031
| -13% VAT for cement | [7 empty] | 3670.0107
| -13% VAT for aggregate | [7 empty] | 1995.13
| -13% VAT for sand | [7 empty] | 950.9471
| -13% VAT for water | [7 empty] | 39.4292
| -13% VAT for diesel | [7 empty] | 276.6519
| -13% VAT for petrol | [7 empty] | 9.9629
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -beam | 2 | 4.5718 |  | 0.6 | 5.4861
|  | 2 | 2.9442 |  | 0.6 | 3.5331
|  | 2 | 2.9442 |  | 0.6 | 3.5331
| -upper beam | 2 | 1.3715 |  | 0.46 | 1.2618
|  | 2 | 0.99055 |  | 0.46 | 0.91131
|  | 1 | 3.8098 |  | 0.23 | 0.87626
| -slab | 2 | 3.2383 | 2.3368 |  | 15.1346
|  | 2 | 3.6955 | 2.032 |  | 15.0186
| -column | 4 | 0.92 |  | 1.2191 | 4.4864
| -cantilever | 2 | 6 | 0.71117 |  | 8.534
|  | 2 | 4.3888 | 0.68577 |  | 6.0194
| Sub-total |  |  |  |  | 64.7947 | sqm | 922.71 | 59786.7571
| -13% VAT for plyboard | [7 empty] | 1689.8875
| -13% VAT for wood | [7 empty] | 1122.6807
| -13% VAT for iron props | [7 empty] | 853.9221
| -13% VAT for nails | [7 empty] | 277.9694
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit Weight (Kg/m) | Total Weight (Kg)
| -beam | 4 | 6.13 | 0.88889 | 21.7956 | 0.021796 |  |  |  |  | 19.3579
|  | 4 | 4.5209 | 0.88889 | 16.0742 | 0.016074
| -stirrups | 70 | 0.81439 | 0.39506 | 22.5213 | 0.022521
| -beam | 8 | 5 | 0.88889 | 35.5556 | 0.035556
|  | 8 | 3.5559 | 0.88889 | 25.2866 | 0.025287
| -stirrups | 56 | 0.81439 | 0.39506 | 18.017 | 0.018017
| -upper beam | 8 | 1.7272 | 0.88889 | 12.2824 | 0.012282
| -stirrups | 20 | 0.81439 | 0.39506 | 6.4347 | 0.0064347
| -upper beam | 8 | 1.8034 | 0.88889 | 12.8243 | 0.012824
| -stirrups | 20 | 0.81439 | 0.39506 | 6.4347 | 0.0064347
| -column | 16 | 2.2097 | 0.88889 | 31.4267 | 0.031427
| -stirrups | 40 | 0.71117 | 0.39506 | 11.2382 | 0.011238
| -at first floor level catilever-slab | 8 | 6.3751 | 0.61728 | 31.4819 | 0.031482
|  | 6 | 5.9942 | 0.61728 | 22.2008 | 0.022201
|  | 48 | 1.7017 | 0.61728 | 50.4212 | 0.050421
|  | 46 | 0.81276 | 0.61728 | 23.0784 | 0.023078
|  | 6 | 5.1304 | 0.61728 | 19.0017 | 0.019002
|  | 8 | 6.3751 | 0.61728 | 31.4819 | 0.031482
|  | 30 | 1.0033 | 0.61728 | 18.5787 | 0.018579
|  | 36 | 1.3207 | 0.61728 | 29.3497 | 0.02935
| -at upper floor | 40 | 2.3368 | 0.61728 | 57.6985 | 0.057698
|  | 36 | 2.032 | 0.61728 | 45.1556 | 0.045156
|  | 28 | 0.55867 | 0.61728 | 9.656 | 0.009656
|  | 28 | 0.55867 | 0.61728 | 9.656 | 0.009656
| Sub-total |  |  |  |  | 0.56765 | MT | 132360 | 75134.3703
| -13% VAT for TMT rod | [7 empty] | 7748.4448
| -13% VAT for binding wire | [7 empty] | 88.5537
7 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_
| -peti area | 0 | 3.6574 | 0.9 |  | 0
|  | 0 | 6.4005 | 0.9 |  | 0
| Sub-total |  |  |  |  | 0 | sqm | 689.98 | 0
| -13% VAT for cement | [7 empty] | 0
| -13% VAT for sand | [7 empty] | 0
| -13% VAT for aggregate | [7 empty] | 0
8 | !^ dL=dL=u¦]gfO{6, @) dL dL afSnf] !M@ efusf] l;d]G6 d;nfdf 5fkL 3f]6\g] / kflnz ;d]t ug]{
| -flooring inside | 0 | 3.8607 | 2.9717 |  | 0
| Sub-total |  |  |  |  | 0 | sqm | 6851.63 | 0
| -13% VAT for cement | [7 empty] | 0
| -13% VAT for sand | [7 empty] | 0
| -13% VAT for 16mm granite | [7 empty] | 0
| -13% VAT for cShflns Pl;8 | [7 empty] | 0
| -13% VAT for d}g kflnz | [7 empty] | 0
| -13% VAT for tf/k]G6fOg | [7 empty] | 0
| -13% VAT for sfaf]{/08d 9'ª\uf | [7 empty] | 0
9 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
| -for wing walls of stand tap | 0 | 1.2163 |  | 0.6 | 0
| -for side wall of stand tap | 0 | 1.3197 |  | 0.6 | 0
| -stand | 0 | 0.3566 |  | 1.2 | 0
|  | 0 | 0.46 |  | 0.6 | 0
| -for floor area | 0 | 1.6763 | 1.6763 |  | 0
| -peti area | 0 | 3.6574 | 0.9 |  | 0
|  | 0 | 6.4005 | 0.9 |  | 0
| Sub-total |  |  |  |  | 0 | sqm | 287.32 | 0
| -13% VAT for cement | [7 empty] | 0
10 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for wall continue | 2 | 2.9464 | 0.35 | 1.3715 | 2.8287 |  |  |  |  | 9.66 | 66.75 | 54 | 12.75 | 1.0625
|  | 2 | 4.5718 | 0.35 | 1.3715 | 4.3892 |  |  |  |  | 3.8718
| -deduction for door | -1 | 1.2 | 0.35 | 1.0667 | -0.44803
| -deduction for window | -2 | 0.6 | 0.35 | 0.71015 | -0.29826
| -for wing walls of stand tap | 0 | 1.2163 | 0.23 | 0.6 | 0
| -for side wall of stand tap | 0 | 1.3197 | 0.23 | 0.6 | 0
| -for stand tap | 0 | 0.3566 | 0.23 | 1.2 | 0
| Sub-total |  |  |  |  | 6.4717 | cum | 14491.84 | 93786.2961
| -13% VAT for brick | [7 empty] | 7135.3702
| -13% VAT for cement | [7 empty] | 767.4233
| -13% VAT for sanda | [7 empty] | 802.0855
| -13% VAT for water | [7 empty] | 23.5569
11 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -for wall continue | 1 | 16.5133 |  | 3.0479 | 50.33
|  | 1 | 13.6605 |  | 1.9811 | 27.0628
| -deduction for door | -1 | 1.2 |  | 2.4383 | -2.9259
| -deduction for window | -2 | 0.6 |  | 0.71015 | -0.85218
| -roof | 0 | 3.2383 | 2.3368 |  | 0
|  | 0 | 3.6955 | 2.032 |  | 0
| -for wing walls of stand tap | 0 | 1.2163 |  | 0.6 | 0
| -for side wall of stand tap | 0 | 1.3197 |  | 0.6 | 0
| -stand | 0 | 0.3566 |  | 1.2 | 0
|  | 0 | 0.46 |  | 0.6 | 0
| Sub-total |  |  |  |  | 73.6146 | sqm | 415.5 | 30586.8827
| -13% VAT for cement | [7 empty] | 670.9143
| -13% VAT for sand | [7 empty] | 444.0177
12 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -inside face of wall | 0 | 13.6605 |  | 1.0667 | 0
| -deduction for door | 0 | 1.2 |  | 1.0667 | 0
| Sub-total |  |  |  |  | 0 | sqm | 2845.18 | 0
| -13% VAT for cement | [7 empty] | 0
| -13% VAT for sand | [7 empty] | 0
| -13% VAT for white cement | [7 empty] | 0
| -13% VAT for porcelain glazed tile | [7 empty] | 0
13 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as plaster | 0 |  |  |  | 73.6146
| Sub-total |  |  |  |  | 73.6146 | sqm | 253.8 | 18683.3955
| -13% VAT for aster | [7 empty] | 220.4906
| -13% VAT for weather coat | [7 empty] | 998.3323
14 | Knfi6/ dfly @) dL=dL= afSnf] emNn/ jf kfgL k§L agfpg] sfd
| -at top | 0 | 20.4206 |  |  | 0
| Sub-total |  |  |  |  | 0 | rm | 144.41 | 0
| -13% VAT for cement | [7 empty] | 0
| -13% VAT for sand | [7 empty] | 0
| -13% VAT for water proofing | [7 empty] | 0
15 | cu¦fv sf7sf] rf}s; agfO hf]8\g] sfd
| -door | 1 | 6.0704 | 0.075 | 0.1 | 0.045528
| -window | 2 | 2.3367 | 0.075 | 0.075 | 0.026288
| Sub-total |  |  |  |  | 0.071816 | cum | 284731.83 | 20448.232
| -13% VAT for salwood | [7 empty] | 2233.3959
16 | Carved salwood lattice (jali) shutter of carved door/window including wood
| -door | 0 | 1.2 |  | 2.1335 | 0
| -window | 0 | 0.6 |  | 0.71015 | 0
| Sub-total |  |  |  |  | 0 | sqm | 37363.64 | 0
| -13% VAT for salwood | [7 empty] | 0
17 | 20mm GI pipe threaded-Medium class
| -for pipe laying | 0 | 1.2 |  |  | 0
| sub-total |  |  |  |  | 0 | rm | 248 | 0
| -13% VAT | [7 empty] | 0
18 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ sfd | No. | Length (m) | Unit weight (Kg/m) | Weight (Kg)
| -MS square pipe for post of 3"*3"*1.6mm thickness | 0 | 1.13 | 3.54 | 0 | 0
| -MS square pipe for binding of 80mm*40mm*1.6mm thickness | 0 | 21.9445 | 2.93 | 0 | 0
| Sub-total |  |  |  |  | 0 | Kg | 182.51 | 0
| -13% VAT for any kind of angles and MS black pipes | [7 empty] | 0
| -13% VAT for primer | [7 empty] | 0
19 | Provisional sum for unforseen works | 0 |  |  |  | 0 | PS | 5000 | 0
20 | Information board (सुचना पाटि) | 0 |  |  |  | 0 | no. | 1000 | 0
| Total | [7 empty] | 406039.1136
| Total Valuated | 406039.1136 |  | 100
| Budget allocated | 700000
| Municipal payment | 332627.2418 |  | 81.92
| User contribution | 73411.8717 |  | 18.08
| Contingencies | 21000 |  | 3
| Maintanince | 14000 |  | 2

## 2.667'column height (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- k~rkfn] led;]g dlGb/ cw'/f] | [6 empty] | F.Y.: 2082/2083
Location:- Shankharapur Municipality 1 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark | Water tap size
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | [9 empty] | length | Breadth | thickness | Height 1 | Height 2 | Width of stand tap
| -for stand tap | 1 | 1.6763 | 1.6763 | 0.15 | 0.42151 |  |  |  |  | 1.6763 | 1.6763 | 0.23 | 0.6 | 1.2 | 0.3566
| Sub-total |  |  |  |  | 0.42151 | cum | 674.12 | 284.1459
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for stand tap | 1 | 1.6763 | 1.6763 |  | 2.81
| Sub-total |  |  |  |  | 2.81 | sqm | 1017.47 | 2859.1341
| -13% VAT for brick | [7 empty] | 232.3672
| -13% VAT for sand | [7 empty] | 82.4239
3 | d]lzgsf] k¦of]u u/L hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -!M@M$_
| -for lintel | 2 | 4.5718 | 0.35 | 0.1 | 0.32002
|  | 2 | 2.9717 | 0.35 | 0.1 | 0.20802
| -for stand tap | 1 | 1.6763 | 1.6763 | 0.1 | 0.281
| Sub-total |  |  |  |  | 0.80904 | cum | 12884.61 | 10424.2229
| -13% VAT for cement | [7 empty] | 438.5746
| -13% VAT for aggregate | [7 empty] | 290.2284
| -13% VAT for sand | [7 empty] | 148.7354
| -13% VAT for water | [7 empty] | 3.8284
| -13% VAT for water | [7 empty] | 41.3257
| -13% VAT for water | [7 empty] | 1.4882
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -beam | 2 | 4.5718 | 0.23 | 0.35 | 0.73606
|  | 4 | 2.9717 | 0.23 | 0.35 | 0.95687
| -upper beam | 2 | 1.5239 | 0.23 | 0.23 | 0.16123
|  | 2 | 1.1429 | 0.23 | 0.23 | 0.12092
| -slab | 2 | 3.7717 | 2.1082 | 0.075 | 1.1927
|  | 2 | 3.124 | 1.9049 | 0.075 | 0.89265
| -column | 4 | 0.23 | 0.23 | 0.81286 | 0.172
| Sub-total |  |  |  |  | 4.2325 | cum | 13957.29 | 59073.7754
| -13% VAT for cement | [7 empty] | 2867.9707
| -13% VAT for aggregate | [7 empty] | 1559.1166
| -13% VAT for sand | [7 empty] | 743.1282
| -13% VAT for water | [7 empty] | 30.8124
| -13% VAT for diesel | [7 empty] | 216.1927
| -13% VAT for petrol | [7 empty] | 7.7856
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -beam | 2 | 4.5718 |  | 0.7 | 6.4005
|  | 4 | 2.9717 |  | 0.7 | 8.3206
| -upper beam | 2 | 1.5239 |  | 0.46 | 1.402
|  | 2 | 1.1429 |  | 0.46 | 1.0515
| -slab | 2 | 3.7717 | 2.1082 |  | 15.9031
|  | 2 | 3.124 | 1.9049 |  | 11.902
| -column | 4 | 0.92 |  | 0.58286 | 2.1449
| Sub-total |  |  |  |  | 47.1247 | sqm | 922.71 | 43482.402
| -13% VAT for plyboard | [7 empty] | 1229.0408
| -13% VAT for wood | [7 empty] | 816.5162
| -13% VAT for iron props | [7 empty] | 621.0503
| -13% VAT for nails | [7 empty] | 202.1648
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit Weight (Kg/m) | Total Weight (Kg)
| -beam | 8 | 4.8272 | 1.5802 | 61.0248 | 0.061025
|  | 4 | 3.227 | 0.88889 | 11.4739 | 0.011474
| -stirrups | 64 | 0.81439 | 0.39506 | 20.5909 | 0.020591
| -beam | 16 | 3.687 | 1.5802 | 93.2228 | 0.093223
|  | 8 | 2.2393 | 0.88889 | 15.9239 | 0.015924
| -stirrups | 88 | 0.81439 | 0.39506 | 28.3125 | 0.028312
| -upper beam | 12 | 1.8793 | 0.88889 | 20.0459 | 0.020046
| -stirrups | 14 | 0.81439 | 0.39506 | 4.5043 | 0.0045043
| -upper beam | 12 | 1.9583 | 0.88889 | 20.8888 | 0.020889
| -stirrups | 16 | 0.81439 | 0.39506 | 5.1477 | 0.0051477
| -slab | 13 | 7.5434 | 0.39506 | 38.7416 | 0.038742
|  | 48 | 2.1082 | 0.39506 | 39.9777 | 0.039978 |  |  |  |  | 3.2002 | 1.6001
|  | 40 | 1.9049 | 0.39506 | 30.1022 | 0.030102 |  |  |  |  | 2.8955
|  | 24 | 3.124 | 0.39506 | 29.6206 | 0.029621
| -column | 8 | 1.8144 | 0.88889 | 12.9021 | 0.012902
| -stirrups | 20 | 0.71117 | 0.39506 | 5.6191 | 0.0056191
|  | 20 | 0.50798 | 0.39506 | 4.0136 | 0.0040136
| Sub-total |  |  |  |  | 0.44211 | MT | 132360 | 58517.9963
| -13% VAT for TMT rod | [7 empty] | 6034.8342
| -13% VAT for binding wire | [7 empty] | 68.9695
7 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -#* dL=dL=_
| -peti area | 2 | 3.6574 | 0.9 |  | 6.5834
|  | 2 | 6.4005 | 0.9 |  | 11.5209
| Sub-total |  |  |  |  | 18.1042 | sqm | 689.98 | 12491.5611
| -13% VAT for cement | [7 empty] | 398.6986
| -13% VAT for sand | [7 empty] | 111.0923
| -13% VAT for aggregate | [7 empty] | 284.2148
7 | !^ dL=dL=u¦]gfO{6, @) dL dL afSnf] !M@ efusf] l;d]G6 d;nfdf 5fkL 3f]6\g] / kflnz ;d]t ug]{
| -flooring inside | 1 | 3.8607 | 2.9717 |  | 11.4727
| Sub-total |  |  |  |  | 11.4727 | sqm | 6851.63 | 78606.7477
| -13% VAT for cement | [7 empty] | 252.6564
| -13% VAT for sand | [7 empty] | 86.7354
| -13% VAT for 16mm granite | [7 empty] | 6460.9342
| -13% VAT for cShflns Pl;8 | [7 empty] | 6.898
| -13% VAT for d}g kflnz | [7 empty] | 6.458
| -13% VAT for tf/k]G6fOg | [7 empty] | 17.7319
| -13% VAT for sfaf]{/08d 9'ª\uf | [7 empty] | 17.8974
8 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
| -for wing walls of stand tap | 4 | 1.2163 |  | 0.6 | 2.9192
| -for side wall of stand tap | 1 | 1.3197 |  | 0.6 | 0.79183
| -stand | 1 | 0.3566 |  | 1.2 | 0.42792
|  | 1 | 0.46 |  | 0.6 | 0.276
| -for floor area | 1 | 1.2163 | 1.4463 |  | 1.7592
| -peti area | 2 | 3.6574 | 0.9 |  | 6.5834
|  | 2 | 6.4005 | 0.9 |  | 11.5209
| Sub-total |  |  |  |  | 24.2783 | sqm | 287.32 | 6975.6508
| -13% VAT for cement | [7 empty] | 218.7993
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for wall continue | 2 | 2.9717 | 0.35 | 1.7799 | 3.7026
|  | 2 | 4.5718 | 0.35 | 1.7799 | 5.6963
| -deduction for door | -1 | 1.5 | 0.35 | 1.0667 | -0.56004
| -deduction for window | -2 | 1.0667 | 0.35 | 1.0667 | -0.79657
| -for wing walls of stand tap | 2 | 1.2163 | 0.23 | 0.6 | 0.3357
| -for side wall of stand tap | 1 | 1.3197 | 0.23 | 0.6 | 0.18212
| -for stand tap | 1 | 0.3566 | 0.23 | 1.2 | 0.098421
| Sub-total |  |  |  |  | 8.6585 | cum | 14491.84 | 125477.079
| -13% VAT for brick | [7 empty] | 9546.4417
| -13% VAT for cement | [7 empty] | 1026.7389
| -13% VAT for sanda | [7 empty] | 1073.1136
| -13% VAT for water | [7 empty] | 31.5168
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -for wall continue | 1 | 16.5133 |  | 3.0479 | 50.33
|  | 1 | 13.6605 |  | 1.9811 | 27.0628
| -deduction for door | -2 | 1.5 |  | 2.1335 | -6.4005
| -deduction for window | -4 | 1.0667 |  | 1.0667 | -4.5518
| -roof | 2 | 3.7717 | 2.1082 |  | 15.9031
|  | 2 | 3.124 | 1.9049 |  | 11.902
| -for wing walls of stand tap | 4 | 1.2163 |  | 0.6 | 2.9192
| -for side wall of stand tap | 1 | 1.3197 |  | 0.6 | 0.79183
| -stand | 1 | 0.3566 |  | 1.2 | 0.42792
|  | 1 | 0.46 |  | 0.6 | 0.276
| Sub-total |  |  |  |  | 98.6605 | sqm | 415.5 | 40993.4258
| -13% VAT for cement | [7 empty] | 899.1788
| -13% VAT for sand | [7 empty] | 595.0853
10 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -inside face of wall | 1 | 13.6605 |  | 1.0667 | 14.5723
| -deduction for door | -1 | 1.5 |  | 1.0667 | -1.6001
| Sub-total |  |  |  |  | 12.9722 | sqm | 2845.18 | 36908.1179
| -13% VAT for cement | [7 empty] | 123.0602
| -13% VAT for sand | [7 empty] | 81.4589
| -13% VAT for white cement | [7 empty] | 16.8739
| -13% VAT for porcelain glazed tile | [7 empty] | 1137.7198
11 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as plaster | 1 |  |  |  | 66.4405
| Sub-total |  |  |  |  | 66.4405 | sqm | 253.8 | 16862.5897
| -13% VAT for aster | [7 empty] | 199.0025
| -13% VAT for weather coat | [7 empty] | 901.039
12 | Knfi6/ dfly @) dL=dL= afSnf] emNn/ jf kfgL k§L agfpg] sfd
| -at top | 1 | 20.4206 |  |  | 20.4206
| Sub-total |  |  |  |  | 20.4206 | rm | 144.41 | 2948.9393
| -13% VAT for cement | [7 empty] | 242.1332
| -13% VAT for sand | [7 empty] | 33.741
| -13% VAT for water proofing | [7 empty] | 0.053094
13 | Highly Carved salwood lattice (jali) shutter of carved door/window including wood
| -door | 1 | 1.5 |  | 2.1335 | 3.2002
| -window | 2 | 1.0667 |  | 1.0667 | 2.2759
| Sub-total |  |  |  |  | 5.4761 | sqm | 37363.64 | 204608.7543
| -13% VAT for salwood | [7 empty] | 6121.488
14 | 20mm GI pipe threaded-Medium class
| -for pipe laying | 1 | 1.2 |  |  | 1.2
| sub-total |  |  |  |  | 1.2 | rm | 248 | 297.6
| -13% VAT | [7 empty] | 38.688
7 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ sfd | No. | Length (m) | Unit weight (Kg/m) | Weight (Kg)
| -MS square pipe for post of 3"*3"*1.6mm thickness | 24 | 1.13 | 3.54 | 96.0048 | 96.0048
| -MS square pipe for binding of 80mm*40mm*1.6mm thickness | 1 | 21.9445 | 2.93 | 64.2975 | 64.2975
| Sub-total |  |  |  |  | 160.3023 | Kg | 182.51 | 29256.7673
| -13% VAT for any kind of angles and MS black pipes | [7 empty] | 1938.0544
| -13% VAT for primer | [7 empty] | 121.0308
14 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 25000 | 25000
15 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 799735.9263
| Total Estimated | 799735.9263 |  | 100
| Budget allocated | 700000
| Municipal payment | 665000 |  | 83.1524
| User contribution | 134735.9263 |  | 16.8476
| Contingencies | 21000 |  | 3
| Maintanince | 14000 |  | 2